## Project Plan
# | Activities | Owner | Status (RAG) | Planned Start date | Actual Start date | Planned End date | Actual End date | % completion | Comments
1 | Walkthrough of checklist pertaining to necessary access & pre-reqs required | Daison | G | 2026-01-21 | 2026-01-20 | 2026-01-23 | 2026-01-20 | 100%
2 | CAP360 Decom Analyzer tool configured in Nationwide | Daison | R | 2026-01-21 | 2026-01-21 | 2026-01-23 |  | 20% | Daison is following up with Frank & Prasad
3 | Create stakeholder matrix with SMEs availability | Sumithra | A | 2026-01-21 | 2026-01-20 | 2026-01-23 |  | 50% | Awaiting SMEs leave plan
4 | Identify interfacing application SME | Senthil | A | 2026-01-21 | 2026-01-21 | 2026-01-23 |  | 0%
5 | Walkthrough of questionnaire to NW | Sumithra | G | 2026-01-21 | 2026-01-21 | 2026-01-21 | 2026-01-21 | 100%
6 | Block tentative slots for workshops with app SMEs | Senthil | A | 2026-01-28 | 2026-01-29 | 2026-01-28 |  | 6.329% | Started with Commercial lines on 30th Jan
7 | Gather & extract data from existing documentations from NW SME and Planning Guide/Master Data | Senthil | G | 2026-01-23 | 2026-01-23 | 2026-01-23 | 2026-01-23 | 100% | received master data
8 | Decom analyzer tool customization | Daison |  | 2026-02-02 |  | 2026-02-06 |  |  | Scripts can be customized in CG environment atleast
9 | Record Retention Centre KT | Sridevi | G | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 100%
10 | Gather data archival & retrieval requirements | Sridevi | A | 2026-02-02 | 2026-02-03 | 2026-02-05
11 | Gather regulatory requirements, data handling rules | Sridevi | A | 2026-02-02 | 2026-02-03 | 2026-02-05
12 | Sign off of master repo | Senthil |  | 2026-02-12 |  | 2026-02-12
13 | Decom analysis - dependency, criticality, portability etc | Senthil |  | 2026-02-12 |  | 2026-02-20
14 | Dependency matrix validation with NW | Senthil |  | 2026-02-23 |  | 2026-02-23
15 | Pattern & Sequencing validation with NW | Daison |  | 2026-02-27 |  | 2026-02-27
16 | Create Job cards | Kuladeepa |  | 2026-02-27 |  | 2026-02-27
17 | Create Roadmap | Senthil |  | 2026-03-05 |  | 2026-03-10
18 | Create Onboarding checklist | Daison |  | 2026-02-27 |  | 2026-02-27
19 | Create Decom handbook | Sailza |  | 2026-02-27 |  | 2026-03-11
20 | Assessment outcome presentation deck | Sumithra |  | 2026-03-12 |  | 2026-03-19
21 | Assessment outcome walkthrough to NW | Sumithra |  | 2026-03-20 |  | 2026-03-20
22 | Milestone 1: Deliverable - Assessment / Discovery Completion — All discovery deliverables accepted (Baseline inventory, Dependency matrix, Initial sequence/patterns, archival & retrieval needs, stakeholder feedback report). | Senthil |  | 2026-03-20 |  | 2026-03-20
23 | Milestone 2: Deliverable-Master Decommissioning Repository baselined — Job Cards per app, finalized decommissioning plan & sequence/patterns, communication plan, and sign-off. | Senthil |  | 2026-03-25 |  | 2026-03-25

## Roles & Responsibility
Senthil (9 tasks) | Daison (5 tasks) | Sumithra (4 tasks) | Sridevi (3 tasks)
Access & Pre-reqs | Tool Configuration | Stakeholder Matrix | Retention Centre KT | Senthil: Will coordinate with the interfacing application SMEs, block tentative slots for the required workshops, and gather essential information from existing NW documentation, Planning Guides, and Master Data. I will drive the completion and sign‑off of the master repository, perform the decommission analysis covering dependencies, criticality, and portability, and validate the dependency matrix with the NW team. Additionally, I will create the decommission roadmap and ensure delivery of the two key milestones — completing the Assessment/Discovery deliverables and finalizing the Master Decommissioning Repository with job cards, sequencing, communication plan, and sign‑off.
App SME Identification | Tool Customization | Questionnaire Walkthrough | Data Archival Requirements | Daison: Walkthrough of checklist pertaining to necessary access & pre-reqs required, CAP360 Decom Analyzer tool configured in Nationwide, Decom analyzer tool customization, Pattern & Sequencing validation with NW, Create Onboarding checklist
Data Gathering | Pattern Validation | Outcome Presentation | Regulatory Requirements | Sumithra: Create stakeholder matrix with SMEs availability, Walkthrough of questionnaire to NW, Assessment outcome presentation deck, Assessment outcome walkthrough to NW.
Master Repo Sign-off | Onboarding Checklist | Outcome Workshop |  | Sridevi: Record Retention Centre KT, Gather data archival & retrieval requirements, Send MoM for Daily stand-up calls.
Decom Analysis & Validation | Workshop Blocking |  |  | Kuladeepa: Analysing and filling the Questionnaire for applications
Roadmap Creation |  |  |  | Sailza: Analysing and filling the Questionnaire for applications

## Overall Status
Current Status Summary
Phase | Tasks | Green | Amber | Red | Duration
Discovery & Pre-reqs | 7 | 3 | 3 | 1 | Jan 21 – Jan 28
Analysis & Customization | 8 | 0 | 0 | 0 | Feb 2 – Feb 23
Deliverables & Planning | 6 | 0 | 0 | 0 | Feb 27 – Mar 20
Milestones | 2 | 0 | 0 | 0 | Mar 20 & Mar 25