## Questionnaire Sample (hidden)
Category -> | General (Business & Functional) | [21 empty] | Risk | [5 empty] | Application Dependency | [10 empty] | Data | [9 empty] | Compliance |  |  | Operation | [7 empty] | Infra |  |  |  | Third party/vendor |  |  | Financial
Questions -> | Application ID | Not present in master sheet | Application Name | Application Description | Line of Business - application type | App Legacy Suite in NW context | App Owner - Name | Business Owner - Name | Information Filled in by (Name) tech lead | Is the application in-house developed or a 3rd Party product / COTS product? | Application Category | Application Type | Is this application / product in scope for decommissioning ? C Column from master | What is the Target Decommissioning date? | Is this application being decommissioned due to non-usage by business or because of modernization? If any other reason, please provide details | Tech stack of the application BG Column from master | Business Criticality of the application? (Based on the biz. Processes involved) | Size of the application based on Lines of Code (LoC) | What is database of the application AE Column from master | Database/Data Store description; Type of data | Point of Arrival (POA) / Target Application Name | Point of Arrival (POA)/ Target Application readiness date | Is this application active or isolated in current portfolio of Nationwide? | What is the age of this application? | Minimum expected life for the application / product? | Does this application handles any Legal Compliances /Audit requirement on its own? | Does this Application interface with any other application which satisfy regulatory compliance need? | Revenue /user impact if this application is down? | Is this a single application or a group of applications? | Access - Batch/Bulk <NW Context. Ask for clarity> | Does the application have connectivity with external application (applications outside the customer landscape)? | Do external applications (applications outside the customer landscape) access data directly or via APIs from this applications' / business functions' database? | Names of Incoming Internal Dependent Applications | Count of Incoming Interfaces from other applications | List the incoming type of interface (FTP, DB calls, MQ, API, any other) | Names of Outgoing Dependent Applications | No. of Outgoing Interfaces to other applications | List the outgoing type of interface (FTP, DB calls, MQ, API, any other) | No. of reports and their frequency this application generates | Size of the current database | Application data is owned by? | Does this application have pre-archived (historical) data? | How long the historical data need to be maintained as per regulations? AJ Column from master | Does this application have pre-archived (historical) data? Replacement of AQ column from this sheet and AI Column from master | Database backup frequency | Is there a pre- defined data purge policy? | Preferred Data treatment Option | What is the SLA slab for retrieving the archived data? | What is the SLA slab for retrieving historical data? | Is there any source code archival policy for this application (Not the data archival). | Period for advance notice to the Technology Owners (Infrastructure team, DR team) reg. shutting down this application? | What is the hardware / software release procedure and communication model at Nationwide? | No. of internal users of this application | No. of external users of this application | Are there any timeframe defined to migrate the existing external users / customers to access the new application before shutting down this application? If yes, what is the defined timeframe? | Are there any ongoing projects (enhancement/changes) in this application? | Level of documentation for this application | What is the level of app team's knowledge on the application? | What is the support level rendered to this application? (Shared team /Dedicated team) | What are the FTE & Contractor count for production support & maintenance for this application? | Does this application use shared or dedicated server? | Count of application servers | Count of data servers | Number of other applications sharing the same server with this application | Provide all the Third party tools used by this application | License renewal period for the tools being used by this application | Any legal agreements between the tool vendors / hardware vendors and client | Monthly application run cost in USD
Guidelines -> | <Free Text> Enter your Application ID |  | <Free Text> Enter the name of application | <Free Text> Enter description of your application in a few lines | <Free Text> Which business area does the application belong to | <Free Text> Please mention whether the application is from PCIO or HV | <Free Text> Name of the designated owner accountable for the application. | <Free Text> Name of the business owner accountable for the application. | <Free Text> Name of the App tech SME completing this questionnaire | <Free text> Whether the app is custom developed, acquired, 3rd Party product or COTS product? | <Select from Drop-Down> Front end, Back end, Both | <Free text> E.g. Web Service, Desktop, Legacy application, IT Service, Infrastructure Service, Utility, 3rd Party | <Free text> E.g. Yes/No/Already decommissioned/Decommissioning in progress | <Free text> | <Free Text> | <Free Text> (e.g., Mainframe COBOL, AS400, Java VB, DB2, C on Mainframes, .NET, SAP) | <Select from Drop-Down> (1-Very Low, 2-Low, 3-medium, 4-high, 5-very high) Business criticality of the application. E.g. Very high criticality - core-apps, High - disruptions impact operations, Medium- non-core business apps (support functions), Low - peripheral business functions with low revenue impact Very low criticality- Desktop apps and productivity tools | <Select from Drop-Down> 1-Very Low (Less than 5000 LoC) 2-Low (5000-10000 LoC) 3-Medium (10000-25000 LoC) 4-High (25000-50000 LoC) 5-Very High (>50000 LoC) | <Free Text> (e.g. DB2, VSAM, SQL Server ,Oracle, MongoDB) |  | <Free Text> Target application or point of arrival to which the application is being migrated / modernized / consolidated | <Free Text> Date/Quarter Date on which the application target / PoA will be ready | <Free text> Active-not isolated, Active-isolated, Not active-not isolated, not active-Isolated | <Select from Drop down> Number of years since initial production go‑live. 1 - 0 to 5 Years 2 - 5 to 10 Years 3 - 10-15 Years 4 - 15-20 years 5 - >20 Years | <Select from Drop-Down> How long are these applications expected to stay before they are decommissioned? Ideally should be before the decom target date | <Select from Drop-Down> Yes/no | <Free text> Yes/No | <Select from dropdown> (1-Low, 2-Medium, 3-High,4-Very High) | <Select from Drop-Down> | <Free text> Yes/No | <Free text> Yes/No If yes, please mention the names of the applications | <Free text> Yes/No If yes, please mention the names of the applications | <Free Text> Names of Incoming Dependent Applications within Nationwide | <Free text> Number of FTPs, DB calls, MQs, API calls | <Free Text> List of interface types | <Free Text> Names of outgoing Dependent Applications within Nationwide | <Free text> Number of FTPs, DB calls, MQs, API calls | <Free Text> List of interface types | <Free Text> | <Select from Drop-Down> (1- <10GB, 2- 10-30GB, 3- 30-70GB, 4- 70-100GB, 5- >100GB) | <Free Text> System of records | <Select from Drop-Down> Yes/No | <Free Text> | Archive/discarded(Replacement of AQ column) | <Select Drop Down List> Self- Explanatory (1-> Daily, 2-> Weekly, 3-> Monthly, 4-> Fortnightly) Priority - Monthly. If any of the tables has monthly backup frequency, mark this as monthly | <Free Text> If yes, please mention the retention duration and purge policy | <Select from Drop-Down> (Archival, Purge, Retain) | <Free Text> | <Free Text> | <Select from Drop-Down> Eg: For mainframe apps, whether the source code to be stored inside or outside mainframe like GitHub | <Free Text> | <Free Text> E.g. Release procedure via ServiceNow or mail | Select from Drop-Down | Select from Drop-Down | <Free Text> | Select from Drop-Down | Select from Drop-Down | Select from Drop-Down | Select from Drop-Down | <Free Text> | <Free Text> | <Free Text> If application & data uses same server, please mention it as part of application server count | <Free Text> | <Free Text> | <Free Text> | <Free Text> | Select from Drop-Down | <Free Text> Monthly BAU/run cost for operations and support
Must have/ Good to have | Must have |  | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have |  | Must have | Must have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have |  | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Must have | Good to have | Good to have | Good to have | Must have | Good to have | Good to have | Good to have | Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Good to have
Sample Answer - Mainframe | 313 |  | Policy Billing Mainframe | Core mainframe system responsible for policy billing, premium calculation, and invoicing | Billing | PCIO | Colleen |  | Frank | In‑house developed | Back End | Legacy Mainframe Application | Yes | 4/31/26 | Modernization to distributed platform | COBOL, JCL, CICS, DB2, VSAM, z/OS | Very High | Very High | DB2 |  | Duck Creek | Q3 2026 | Active – Isolated | 0 to 5 Years | < 3 Months | Yes | Yes | Very High | Group | Yes | No | Yes | Claims, CRM | 5 | FTP, MQ | Fraud System | 8 | MQ | 15 reports monthly | less than 10GB | Policy Data | Yes | 7 Years |  | Weekly | No | Archive | 10 days | 10 days | Mainframe CAB process | 15 days | ServiceNow | 1 - 10 Users | > 30 Users | 2 months | No | Minimal Documentation | Has only basic information | Shared | 4 | Dedicated | 3 | 2 | 1 | IBM Omegamon | NA | No | 45,000 USD
Sample Answer - Distributed | 7 |  | Claims Portal | Web‑based portal for end‑to‑end claims processing | Claims | HV | Colleen |  | Scott | COTS with customization | Both | Web Application | Yes | 12/31/26 | Business consolidation | ASP.NET Core, SQL Server, IIS, Azure | High | Medium | SQL Server |  | Duck Creek | Q3 2026 | Active – Isolated | 15-20 years | < 3 Months | No | No | High | Single | No | Yes | No | NA | 2 | REST API | Claims System | 3 | REST API | 30 reports daily | 10-30GB | Claims function | No | 3 Years |  | Daily | Yes | Purge | 10 days | 10 days | NA | 30 days | Via Mailer | > 30 Users | 1 - 10 Users | No | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | 6 | 4 | 3 | New Relic, Splunk | Annual | No | 25,000 USD
Application #1 | 451 |  | Pathway (DSM) | Maintains customer information at the name and address level |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | DB2 Tables | DB2 Tables- Around 20 Tables | [9 empty] | TBD | [10 empty] | TBD |  | N/A | Discard
Application #2 | 909 |  | Mainframe Business Auto | Policy processing system for Business Auto Policies. | Policy | PCIO | Esposito, Colleen M |  | Michael Hansen |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM rate files, class files, edit files and tablebase VSAM files for entry, master and quotes. Also automatic renewal VSAM files VSAMC.PPV.DATA.ENTRY.INDEX VSAMC.PPV.DATA.ENTRY.MASTER VSAMC.PPV.INDEX VSAMC.PPV.MASTER VSAMC.PPV.LIVE.RATE VSAMC.PPV.QUOTE.PRINT.INDEX VSAMC.PPV.QUOTE.PRINT.MASTER VSAM1.PPV.ACCTDIST.MASTER VSAM1.PPV.CLASS VSAM1.PPV.QUOTE.INDEX VSAM1.PPV.QUOTE.INDEX.PRIOR VSAM1.PPV.QUOTE.MASTER.PRIOR VSAM1.PPV.QUOTE.MASTER VSAM1.PPV.QUOTE.INDEX.CURRENT VSAM1.PPV.QUOTE.MASTER.CURRENT VSAM1.PPV.RECYCLE.INDEX VSAM1.PPV.RECYCLE.MASTER VSAM1.PPV.RENEW.INDEX VSAM1.PPV.RENEW.MASTER VSAM1.PPV.VEHICLE.MAKE VSAM files used for inquiry during the nightly batch cycle VSAMN.PPV.DATA.ENTRY.INDEX VSAMN.PPV.DATA.ENTRY.MASTER VSAMN.PPV.INDEX VSAMN.PPV.INDEX.AFMR VSAMN.PPV.LIVE.RATE VSAMN.PPV.MASTER VSAMN.PPV.MASTER.AFMR VSAMN.PPV.QUOTE.PRINT.INDEX VSAMN.PPV.QUOTE.PRINT.MASTER | [9 empty] | Yes | [10 empty] | Mainframe Business Auto |  | Indefinite | Archive
Application #3 | 910 |  | Mainframe General Liability (GLS) | Policy Processing system for General Liability policy types. | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy and quote data in the index, master, data entry and quoue hold files. Also VSAM rates, rate date and class code files VSAM Files – Index - VSAMC.GLS.INDEX Master - SAMC.GLS.MASTER history index - VSAMC.GLS.HISTORY.INDEX history master - VSAMC.GLS.HISTORY.MASTER data entry - VSAMC.GLS.DATA.ENTRY quote - VSAMC.GLS.QUOTE.HOLD Quote print - VSAMC.GLS.QUOTE.PRT Rate date - VSAMC.GLS.POL.RATE.DATE rate file - VSAMC.GLS.LIVE.RATE,VSAM1.GLS.PSEUDO.RATE class code file - VSAMC.GLS.LIVE.CLASS quote file - VSAMC.GLS.QUOTE.HOLD Renewal data entry - VSAMC.GLS.DATA.ENTRY.RENEW, VSAMC.GLS.DATA.ENTRY.WORK Renewal rate date - VSAMC.GLS.RATE.DATE.RENEW,VSAMC.GLS.RATE.DATE.WORK Tape Files - Policy data is in the below tape files AID01.GLS.FINAL.YTD.INDEX.PURGE AID01.GLS.FINAL.YTD.MASTER.PURGE AID01.GLS.YTD.INDEX.PURGE AID01.GLS.YTD.MASTER.PURGE DB2 Tables – General Liability does not own any DB2 tables. Hercules - Data in Index and Master file is ingested to Hercules | [9 empty] | Yes | [10 empty] | Mainframe General Liability (GLS) |  | Indefinite | Archive
Application #4 | 911 |  | Mainframe Commercial Property | Policy processing system for the Commercial Property Line of Business | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM rate files and tablebase VSAM files – Index - VSAMC.CPS.INDEX Master - VSAMC.CPS.MASTER Data entry - VSAMC.CPS.DATA.ENTRY Rates - VSAMC.CPS.RATE.FILE Renewal Data Entry - VSAMC.CPS.DATA.ENTRY.RENEW Quotes - VSAMC.CPS.QUOTE.ENTRY Quote print - VSAMC.CPS.QUOTE.PRINT Account Dist - VSAMC.CPS.ACCTDIST DB2 Tables – Commercial Property does not own any DB2 table Tape Files - AID01.CPS.FINAL.YTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules" | [9 empty] | Yes | [10 empty] | Mainframe Commercial Property |  | Indefinite | Archive
Application #5 | 912 |  | Mainframe Package Control | Policy processing system for the commercial package control system. | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM edit files and tablebase VSAM files for entry, master and quotes. Also automatic renewal VSAM files VSAMC.PPZ.DATA.ENTRY.INDEX VSAMC.PPZ.DATA.ENTRY.MASTER VSAMC.PPZ.INDEX VSAMC.PPZ.MASTER VSAMC.PPZ.QUOTE.INDEX VSAMC.PPZ.QUOTE.MASTER VSAMC.PPZ.QUOTE.PRINT.INDEX VSAMC.PPZ.QUOTE.PRINT.MASTER VSAM1.PPZ.RENEW.INDEX VSAM1.PPZ.RENEW.MASTER VSAM1.PPZ.DAILY.EDIT.ERRORS VSAM1.PPZ.DATA.ENTRY.INDEX.CURRENT VSAM1.PPZ.DATA.ENTRY.MASTER.CURRENT VSAM1.PPZ.DATA.ENTRY.INDEX.PRIOR VSAM1.PPZ.DATA.ENTRY.MASTER.PRIOR VSAM1.PPZ.QUOTE.INDEX.CURRENT VSAM1.PPZ.QUOTE.MASTER.CURRENT VSAM1.PPZ.QUOTE.INDEX.PRIOR VSAM1.PPZ.QUOTE.MASTER.PRIOR VSAM1.PPZ.RECYCLE.INDEX VSAM1.PPZ.RECYCLE.MASTER VSAM files used in the Pak money FMR process VSAMC.PPZ.RECYCLE.ERROR VSAM1.PPZ.BATCH.SUSPENSE.NUMBER VSAM files used for inquiry during the nightly batch cycle VSAMN.PPZ.DATA.ENTRY.INDEX VSAMN.PPZ.DATA.ENTRY.MASTER VSAMN.PPZ.INDEX VSAMN.PPZ.INDEX.AFMR VSAMN.PPZ.INDEX.AMFMR VSAMN.PPZ.MASTER VSAMN.PPZ.MASTER.AFMR VSAMN.PPZ.MASTER.AMFMR VSAMN.PPZ.QUOTE.INDEX VSAMN.PPZ.QUOTE.MASTER VSAMN.PPZ.QUOTE.PRINT.INDEX VSAMN.PPZ.QUOTE.PRINT.MASTER VSAMN.PPZ.RECYCLE.ERROR | [9 empty] | Yes | [10 empty] | Mainframe Package Control |  | Indefinite | Archive
Application #6 | 921 |  | Mainframe Farm | Policy processing system for Farm policies | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy,quote and rate data; database inflation factor, farm credit, RCE VSAM Files – Index - VSAMC.FMP.INDEX Policy - VSAMC.FMP.POLICY Quote - VSAMC.FMP.QUOTE.HOLD data entry - VSAMC.FMP.DATA.ENTRY quote print - VSAMC.FMP.QUOTE.PRINT Worksheet - VSAMC.FMP.TEMP.WRKSHEET.FILE accounting/distribution - VSAM1.FMP.ACCTDIST rate data - VSAMC.FMP.RATES DB2 Tables – FB2T0070_RES_INFL_FCTR (Inflation Factors) FB2T0050_CRDT_INFO (Farm Credit) FB2T0030_CHS_DIVD (Farm Dividend) FB2T0300_RCE_GENERAL(RCE) FB2T0310_RCE_STRUCTURE(RCE) FB2T0320_RCE_COMPONENT(RCE) Tape Files - AID01.FMP.FINAL.YTD.PURGE AID01.FMP.YTD.PURGE AID01.FMP.MTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules | [9 empty] | Yes | [10 empty] | Mainframe Farm (WINS) |  | Indefinite | Archive
Application #7 | 923 |  | Mainframe Business Owners (SBO) | Policy Processing System for Commercial Business Owners policies. | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy and quote data in the index, master, data entry and quoue hold files. Also VSAM rates, class code and the accounting/distribution files VSAM files – Index - VSAMC.SBO.INDEX Master - VSAMC.SBO.MASTER Data entry - VSAMC.SBO.DATA.ENTRY class codes -VSAMC.SBO.LIVE.CLASS rates - VSAMC.SBO.LIVE.RATE Renewal index - VSAMC.SBO.DATA.ENTRY.RENEW Prior Index - VSAMC.SBO.PRIOR.INDEX Quotes - VSAMC.SBO.QUOTE.HOLD Quote print - VSAMC.SBO.QUOTE.PRINT Account Dist - VSAM1.SBO.ACCTDIST BOP Index after FMR - VSAM1.SBO.INDEX.AFMR BOP Master after FMR - VSAM1.SBO.MASTER.AFMR DB2 Tables – Businessowners does not own any DB2 table PPH_STATE_ZIP_INFLT_FCTR – State Zip Code Tape Files - AID01.SBO.FINAL.YTD.* AID01.SBO.YTD.* | [9 empty] | Yes | [10 empty] | Mainframe Business Owners (SBO) |  | Indefinite | Archive
Application #8 | 924 |  | Mainframe Policy Entry | Policy Processing System for Inland Marine, Crime, Commercial Umbrella, and Personal Umbrella policies | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM policy and quote data on our index, master, MOT and data entry files. VSAM Renewal index, master, MOT and data entry. VSAM files – Index (Policies and Quotes) - VSAM1.PCS.INDEX Master (Policies and Quotes) - VSAM1.PCS.POLICY Data entry (trigger record only for NB/REN)- VSAM1.PCS.DATA.ENTRY MOT (trigger record only for changes) - VSAM1.PCS.MOT class codes , forms-VSAM1.PCS.TABLE rates - no rate file for Policy Entry Renewal index - VSAM1.PCS.RENEW.INDEX Renewal Master - VSAMC.PCS.RENEW.POLICY Renewal Data Entry - VSAM1.PCS.RENEW.DATA.ENTRY DB2 Tables – Policy Entry does not own any DB2 table Tape Files - AID01.PCS.FINAL.YTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules" | [9 empty] | Yes | [10 empty] | Mainframe Policy Entry |  | Indefinite | Archive
Application #9 | 926 |  | Mainframe Workers Comp | Policy processing systems for Workers Compensation policies. | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | VSAM files - index, master, data entry, MOT, class code descriptions, rates, unit stat, dividends, renewal index/master/data entry VSAM files – Index - VSAMC.WCS.INDEX Master - VSAMC.WCS.MASTER Data entry - VSAMC.WCS.DATA.ENTRY MOT - VSAMC.WCS.MOT class code descriptions - VSAMC.WCS.DESC rates - VSAMC.WCS.RATE.ENTRY, VSAMC.WCS.RATES unit stat - VSAMC.WCS.US.MASTER dividends - VSAMC.WCS.PARPLAN.MASTER Renewal index - VSAMC.WCS.RENEW.INDEX, VSAMC.WCS.INDEX.WORK Renewal master - VSAMC.WCS.RENEW.MASTER, VSAMC.WCS.INDEX.MASTER Renewal data entry - VSAMC.WCS.RENEW.DATA.ENTRY, VSAMC.WCS.DATA.ENTRY.WORK Endorsements - VSAM1.WCS.END.EDITS DB2 Tables – Work comp does not own any DB2 tables Tape Files - AID01.WCS.FINAL.YTD.PURGE AID01.WCS.YTD.PURGE.HISTORY Hercules - Data in Index and Master file is ingested to Hercules | [9 empty] | Yes | [10 empty] | Mainframe Workers Comp |  | Indefinite | Archive
Application #10 | 940 |  | Allied Endorsements | Repository of policy endorsements available to Service Advantage policy systems, billing and TCS |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | Yes - VSAM | Endorsements by prefix/state with the start/end date of use. | [9 empty] | No | [10 empty] | TBD |  | Indefinite | Archive
Application #11 | 1208 |  | Alpha Search | Maintains customer information by policy at the customer name and address level |  | PCIO | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  |  |  |  | No | Customer data | [9 empty] | No | [10 empty] | TBD |  | N/A | Discard
Application #12 | 1214 |  | Error Message | Maintains a VSAM based common message file for the Service Avantage policy systems. The policy system requests a type of message and gets back a specific error correctly worded. |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | No | 0 | [9 empty] | TBD | [10 empty] | TBD |  | N/A | N/A
Application #13 | 1220 |  | Policy Reload | Central point for customers to request a policy to be reloaded from back up files onto online policy systems. |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | SQL Server |  |  | No | Used to notify policy admin systems to reload a policy from backup tapes | [20 empty] | TBD |  | Transfer to Flex | Archive
Application #14 | 1418 |  | Policy Expirations | Process expiring policies. EXP on a monthly basis(end of month processing(EOM)) selects policies that are 105 days or less from expiring and generates reports such as NON-RENEWLs list, EXPIRATION list, etc. EXP also creates a monthly file of expiring policies that gets processed daily and any policy that is 73 days or less from expiring is written to EFILE and EFILE is sent to Columbus for further processing. |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 03/31/26 |  |  |  |  | No | Policies coming up for renewal 11/09/2025 - will review opportunity to decommission earlier, but need time to review. Not a big rock | [20 empty] | TBD |  | N/A | Discard
Application #15 | 1660 |  | Commercial Umbrella | Online calculator for Commercial Umbrella policies. This application is being used by Commercial Underwriters in PCIO Exclusive and Independent. | TBD | PCIO | Esposito, Colleen M |  | Bill Mardis |  |  |  | In Progress - Planning | 03/31/26 |  |  |  |  | Yes | Cloud SQL Server database COMUDB has 30 tables that are a combination of Umbrella quote data entered in the tool along with tables that contain app rules/class codes/rates 1/14-Preliminary discussion started,its calculator | [9 empty] | Yes | [10 empty] | TBD |  | MAX 5 years for quotes, need to determine | Archive
Application #16 | 2887 |  | Commercial Rate Step Maintenance | Rate Step Maintenance Application used by Commercial to maintain rate Steps for BOP, BA, & Farm. Also, this project may go with a Minor Release sometime after the PC4.0-08 Release. |  | PCIO | Esposito, Colleen M | [5 empty] | In Progress - Planning | 03/31/26 |  |  |  |  | Yes | Updates/reads mainframe DB2 tables that are ultimately used by PCIO mainframe policy systems PPHDP001 PPH_COBOL_STEP PPH_COBOL_STEP_CRITR PPH_CVRG_DM PPH_ITEM_GRP_DM PPH_ITEM_MAPPING_DM PPH_ORG_DM PPH_PRODUCT_DM PPH_RT_STEP PPH_RT_STEP_CRITR PPH_STATE_DM PPH_SUBPRODUCT_DM PPH_UNIT_DM PPH_VALID_CVRG_DM PPH_VALID_PREFX_DM PPH_WKSHT_DSC_DM 1/14-Turn of Web App in second week of Feb | [9 empty] | No | [10 empty] | MF PCIO - PAK |  | Data Retention will be done as per PCIO Mainframe , getting rid of UI | N/A
Application #17 | 2918 |  | CCRF Agent Center | Allows agents to submit Commercial Change Requests via the Agent Center. |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | Yes | Cloud SQL Server Database PH4DD001 - 29 tables starting with PH4* that contain amendment details keyed into the app. When user submits an amendment, the details are put in a PDF and sent to processing via eFile. There is no direct connection between the data entered/stored in CCRF with the PCIO mainframe policy systems. All data is manually keyed in CCRF and then manually keyed in PCIO mainframe. | [20 empty] | CCRF Agent Center |  | N/A | Discard
Application #18 | 4245 |  | Commercial Mainframe COI | Commercial Mainframe COI processing/printing. |  | PCIO | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  |  |  |  | No | Cert of Insurance from Agent Center, still utilized. Is this used for PC COI? Should not be on the decom list, need to verify it's the same tool used for PC because it needs to remain. Request comes from Agent Center COI | [9 empty] | Yes | [10 empty] | MF PCIO - PAK |  | N/A | N/A
Application #19 | 4260 |  | Commercial Renewal Reporting DB | PCIO - Stores the U/W renewal rules and statistics to report against it. The database we own is for business driven Brio Reports measuring policies that Renew without being touched by underwriters. It also measures renewal errors that are triggering Underwriter activities to determine if the renewal rules need to be adjusted to meet the business needs. There are also reports that measure regional office renewal volume and premium. |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 03/31/26 |  |  |  |  | Yes | Renewal data from PCIO Automatic Renewal process | [20 empty] | TBD |  | N/A | N/A
Application #20 | 4261 |  | Commercial Underwriting DB | Marketing/Pricing/Underwriting Database - Monitors IA Agents productivity and IA Agents Quote to Issue Premium Variations. Owned by Underwriting. Web front-end that is owned by CIQ. Also produces and stores reports for Marketing, Pricing and Underwriting. Includes several BRIO queries. Underwriting owns BRIO queries |  | PCIO | Esposito, Colleen M | [5 empty] | Not Started | 03/31/26 |  |  |  |  | Yes | 0 | [9 empty] | TBD | [10 empty] | TBD |  | N/A | Discard
Application #21 | 5281 |  | HV-Accounts Receivable | Accounts Receivable Also known as Agent Balance and Reconciliation Recieves feeds from Billing System and PNC lockbox | Financial | HV | Esposito, Colleen M |  | MSA |  |  |  | In Progress - Planning | 04/01/27 |  |  |  |  | Yes | DB2 tables - contain accounts receivable data. prod.ARCV_STMNT_ELMNT prod.ARCV_ACCT_STMNT | [9 empty] | No | [10 empty] | 5281 HV-Accounts Receivable |  | FMA170 – Accounting Records -7 years | Archive
Application #22 | 5282 |  | HV-Agency Bill Account Current | This application is used to bill agents (monthly) and track their balances due the company. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  |  |  |  | No | N/A | [20 empty] | 5296 HV-Legacy Billing |  | N/A | N/A
Application #23 | 5283 |  | HV-Agency Systems | Includes Agency Performance, Agency Commissions, Agency Master, Expiration, and Mainframe Portion of Agency Download | Producer/Agency |  | Esposito, Colleen M |  | MSA |  |  |  | In Progress - Planning | 04/01/27 |  |  |  |  | Yes | Harleysville legacy system including Agency Master, Agency Performance, and Agency Download batch processing and CICS. VSAM files Agency Master file: CORP00PV.AGCY.NEW.ADSK..C Master file contains all agency info including appointments Agency Performance: CORP00PV.AGCY.PERFORM.C HV agency data is fed over to AMF and DPIM | [9 empty] | TBD | [10 empty] | 5283 HV Agency Systems |  | INS1020 – Agency Administration - Active + 7 years | Archive
Application #24 | 5285 |  | HV-CCMS & Score | Used for assignment of policy numbers for manual policies and to link them in the Insured Account Database. In addition, if any of these policies are brought into automation at renewal, CCMS would be used to set up the renewal conversion. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | MF |  |  | Yes | Vsam - Policy number assignment for manual policies COMM00PV.CCMS.MASTER.C | [9 empty] | No | [10 empty] | 5285-HV-CCMS & Score |  | NA | Discard
Application #25 | 5290 |  | HV-Direct Bill Commission | Monthly application that creates agent's commission payments for Direct Bill policies. | Financial | HV | Esposito, Colleen M |  | MSA |  |  |  | In Progress - Planning | 04/01/27 |  |  |  |  | No | agent commissions, pull data from stat and accounting records and feed to SAP, data returned and do check print, processing, commissions payments, check statements FMA170 – Accounting Records | [22 empty] | FMA170 – Accounting Records -7 years | Archive
Application #26 | 5296 |  | HV-Legacy Billing Systems | The Agency bill system supports the monthly billing and collection from each agent on a net premium basis (premium less commission). The agency bill premiums are for accounts of $50,000 or more. The system provides a history of collection activity and provides detailed Information on all outstanding unpaid premium by agent.The Direct Bill system supports the billing and collection directly from the customer, of P&C insurance premium written by Harleysville Insurance operations. | Financial | HV | Esposito, Colleen M |  | MSA |  |  |  | In Progress - Planning | 04/01/27 |  | win 2019 SQL and Windows, batch |  |  | Yes | Accounts/Policies/Cash transactions/Audit trail, VSAM BILL00PV.DRCT.B1.MASTER.C BILL00PV.DRCT.B2.MASTER.C BILL00PV.DRCT.B3.MASTER.C BILL00PV.DRCT.B4.MASTER.C BILL00PV.DRCT.ACCT.AUDIT.TRAIL.C BILL00PV.DRCT.AUDIT.TRAIL.C FMA170 – Accounting Records Images stored in IR and will go to RRC with ImageRight decom | [9 empty] | No | [10 empty] | 5296 HV-Legacy Billing |  | FMA170 – Accounting Records -7 years | Archive
Application #27 | 5306 |  | HV-Personal Lines Legacy | Policy adminstration for Personal lines Homeowners, Automobile, Blanket Excess, Inland Marine, and Shipmate on the mainframe | Policy | HV | Esposito, Colleen M |  | MSA |  |  |  | In Progress - Planning | 04/01/27 |  | Win2019, SQL2019 |  |  | Yes | Personal lines policy information for Harleysville including Auto, Home, Dwelling and Unbrella lines of businesss on the mainframe. There is a database for Auto, Home, and Umbrella PLAU00PV.AUTO.POL.CTRL.PROD.MSTR.C PLAU00PV.AUTO.POL.DTL1.MSTR.C PLAU00PV.AUTO.POL.DTL2.MSTR.C PLAU00PV.AUTO.POL.DTL3.MSTR.C PLAU00PV.AUTO.POL.DTL4.MSTR.C PLPP00PV.HOME.CONTROL.MSTR.C PLPP00PV.HOME.POL.DTL.MSTR.C PLPP00PV.HOME.HO61.MSTR.C PLPP00PV.DWEL.POL.DTL.MSTR.C PLPP00PV.SHIP.POL.DTL.MSTR.C PLPP00PV.BLEX.POL.DTL.MSTR.C | [9 empty] | Yes | [10 empty] | HV-Personal Lines Legacy |  | POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Archive
Application #28 | 5307 |  | HV-Commercial Lines Legacy | App will be decom with MF. | Policy | HV | Esposito, Colleen M |  | MSA |  |  |  | In Progress - Planning | 04/01/27 |  | Win2019, SQL2019 |  |  | Yes | 5/17/22 from Terry; There is VSAM data associated with this application which should still be in existence for inquiry purposes. Colleen and I discussed this app last night and this data should be made available in Alcides as it may be required for future Claims reporting. There should be inquiry functionality supporting this application with no transactional capability. Cindy Budka is knowledgeable on this app and would be able to speak to file layouts/content. COMM00PV.CAUT.CA.CONTROL.MASTER.C COMM00PV.CAUT.CA.DETAIL.MASTER.C COMM00PV.CAUT.PU.DETAIL.MASTER.C COMM00PV.WCOM.WC.CONTROL.MASTER.C COMM00PV.WCOM.WC.DETAIL.MASTER.C COMM00PV.WCOM.PU.DETAIL.MASTER.C COMM00PV.BEXC.BE.CONTROL.MASTER.C COMM00PV.BEXC.BE.DETAIL.MASTER.C COMM00PV.BEXC.PU.DETAIL.MASTER.C COMM00PV.MONO.CP.CONTROL.MASTER.C COMM00PV.MONO.CP.DETAIL.MASTER.C COMM00PV.MONO.GL.CONTROL.MASTER.C COMM00PV.MONO.GL.DETAIL.MASTER.C COMM00PV.MONO.BO.CB.CONTROL.MASTER.C COMM00PV.MONO.BO.CB.DETAIL.MASTER.C COMM00PV.MONO.PU.DETAIL.MASTER.C COMM00PV.MULT.IM.CONTROL.MASTER.C COMM00PV.MULT.IM.DETAIL.MASTER.C COMM00PV.MULT.MP.CONTROL.MASTER.C COMM00PV.MULT.MP.DETAIL.MASTER.C COMM00PV.MULT.CR.CONTROL.MASTER.C COMM00PV.MULT.CR.DETAIL.MASTER.C COMM00PV.MULT.PU.DETAIL.MASTER.C | [9 empty] | Yes | [10 empty] | HV-Commercial Lines Legacy |  | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Archive
Application #29 | 5308 |  | HV-Commercial Lines DMV | Used for reporting vehicle information to various state DMV agencies |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | Desktop |  |  | Yes | Feeds to/from Verisk - CL | [20 empty] | 5307 - HVCommercial Lines |  | N/A | Discard
Application #30 | 5309 |  | HV-Midstream Stat Creation | Creation of Accouting/Stat to be processed downstream systems |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 04/01/27 |  |  |  |  | No | AQS / DCT are the source | [22 empty] | N/A | N/A
Application #31 | 5385 |  | HV-AccessWeb - UWRulesEngineWeb App | User interface for accepting and responding to binding authority questions an rules. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | WIN2019 |  |  | Yes | Uses xml Binding Authority blobs for Questions and Answers. | [9 empty] | No | [10 empty] | HV-URE, HV-Quote, IADB |  | UND120 – Commercial Lines, Property, Casualty -Indefinite | Archive
Application #32 | 5390 |  | HV-Audit Upload Manager | Audits discrepancies in policy premium caused by quote and billing date issues. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | WIN2022, SQL2019 |  |  | Yes | Database is the audit control file | [20 empty] | AQS |  | N/A | Discard
Application #33 | 5408 |  | HV-Renewal Automation | Renewal automation is a batch process (.net/sq.) that runs in the background on a nightly basis. The job gathers data from both legacy and AQS and flags 90 day expiration candidates for renewal. Some can issue automatically, others are flagged for manual intervention. Web Methods is the intermediary link between all the function. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | Win2019, SQL2019 |  |  | Yes | Renewal control db | [20 empty] | AQS |  | N/A | Discard
Application #34 | 5413 |  | HV-Underwriting Rules Engine (URE) | The tool used to assign rules around potential customer's provided information. This rules engine will determine if the policy can be bindable, determining account-level renewal authority, determing applicable product, system and line of business.. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | Win2019, SQL2019 |  |  | Yes | Stores Protocol data and uses xml blob saved for prior referrals generated.Quote and IADB db's used to populate Blaze and .net objects. | [9 empty] | No | [10 empty] | HV-URE, HV-Quote, IADB |  | UND120 – Commercial Lines, Property, Casualty -Indefinite | Archive
Application #35 | 5415 |  | HV-ACE - Premium Audit | Premium audit. Commercial policy so much for the year. Premium is estimated. Your premium should be or less or more. Feeds from policy systems |  | HV | Esposito, Colleen M |  | Michael Kelly |  |  |  | Not Started | 12/31/26 |  | Win2019, SQL2019 |  |  | Yes | Audit Data | [9 empty] | No | [10 empty] | HV AQS |  | UND120 – Commercial Lines, Property, Casualty - indefinite Und 100 - | Archive
Application #36 | 5426 |  | HV-Clarify | CRM Tool for Contact Center and Service Center |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | Win2016 |  |  | Yes | CRM data - data is sent to HV Direct Bill Mainframe - URA (User Remarks Area) - we stopped send sending this when Zoom replaced Clarify. Clarify still collects this data but no longer sends it to ZOOM | [9 empty] | Yes | [10 empty] | HV - Billing |  | N/A | Discard
Application #37 | 5427 |  | HV-COGNOS | Query report and analysis capabilities for all type of data. A component of COGNOS is Analyst Studio, which also needs to be tested whenever any type of upgrade occurs. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | Win2019, SQL2019 |  |  | Yes | Policy Holder, Conformed Demisions and Claims master BI Reporting, Audit Store and Content Store | [9 empty] | Yes - feeds to Cognos | [10 empty] | HV-Legacy Claims (5297) |  | N/A | Discard
Application #38 | 5442 |  | HV-ImageRight | Imaging and workflow management system from Vertafore. This system is used to capture policy, underwriting and claims workflow and documentation. Images can be introduced into this system in various ways such as scanning, printing, and email. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 07/01/27 |  | MF, VSAM, CICS |  |  | Yes | Stores Output from DCT, AQS, Claims, Billing, Accounting Reports (retire after all HV apps retired or docs moved) 6/30/21 Also used as an input to ClaimCenter, see notes for more info | [9 empty] | Yes | [10 empty] | ImageRight |  | N/A | Discard
Application #39 | 5444 |  | HV-Informatica | ETL Tool |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 07/01/27 |  | Win2019, SQL2019 |  |  | Yes | ETL software that stores repository data and meta data (no policy data is stored) | [9 empty] | Yes | [10 empty] | HV - Informatica |  | N/A | Discard
Application #40 | 5454 |  | HV-Rules Maintenance Application (RMA) | Development platform to write business rules. These rules are then used by the URE application. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | Win2019, SQL2019 |  |  | Yes | Uses database rules repository to store rule updates, templates and rule's information | [9 empty] | No | [10 empty] | HV-URE |  | UND120 – Commercial Lines, Property, Casualty - indefinite | Archive
Application #41 | 5463 |  | HV-UWWB - Underwriter WorkBench | This is a Workbench for task completion. documentation, and making underwriting decisions for Underwriters. Processing uses this workbench for task completion and documentation as well. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  | Win2019 |  |  | Yes | Underwriter_Workbench database is used as its own db by the application. SQL | [9 empty] | No | [10 empty] | 5463-HV-UWWB - Underwriter WorkBench |  | N/A | N/A
Application #42 | 5464 |  | HV-VOIP Services | Web service to provide insured and agent data back to the agent or call center representative. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | SFTP, VSAM |  |  | No | reads HV Clarify database, decom with clarify | [9 empty] | No | [10 empty] | HV -Clarify |  | N/A | N/A
Application #43 | 5465 |  | HV-webMethods | webMethods is the backbone of Harleysville SOA- and EDA-enablement and provides support for HTTP/s, FTP/s and SMTP transport protocols, messaging, SOAP web service, synch/asynch, service orchestration, logging, standardized error handling, etc. The webMethods Integration Platform enables realime and batch service integration between Harleysville's core insurance applications on both the Windows and IBM mainframe environments. SOA application. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 07/01/27 |  |  |  |  | Yes | database is self supporting, creates its own db to store configuration. | [9 empty] | No | [10 empty] | HV - All |  | N/A | Discard
Application #44 | 5478 |  | HV-Agent Portal | Portal for agents to view his book of business, begin new business transaction and launch into applicable policy systems, gather agency reports, etc. | Support | HV | Esposito, Colleen M |  | Tony Brnic |  |  |  | Not Started | 12/31/26 |  | Download |  |  | Yes | IADB - account-level data | [9 empty] | Yes | [10 empty] | HV AQS |  | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Archive
Application #45 | 5479 |  | HV-AQS | Policy administration for commercial lines. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  | SFTP, Flat File |  |  | Yes | HR_AQS_Policy, HR_AQS_Resource, HR_AQS_ResourceEdit,HR_AQS_ResourceTest, HR_AQS_Document, HR_AQS_DocumentEdit, HR_AQS_Repository, HR_AQS_System, IADB, Global_IADB | [9 empty] | Yes | [10 empty] | TBD |  | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Archive
Application #46 | 5567 |  | HV-Starteam | Source management product that we have licensed for AQS. Need to save the source code. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | SFTP, Flat File |  |  | Yes | Source Code for AQS, data, forms and rates | [9 empty] | No | [10 empty] | Starteam |  | N/A | Discard
Application #47 | 5570 |  | HV-Predictive Modeling | Provides underwriting scoring on accounts based on policy information |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | CICS, win2019, SQL2019 |  |  | Yes | Multilple Databases - collect non PII information that is used during rating/scoring | [9 empty] | Yes | [10 empty] | HV-Predictive Modeling |  | UND120 – Commercial Lines, Property, Casualty - indefinite | Archive
Application #48 | 5666 |  | HV-AIS | Agency SQL database and services used throughout organization for agency validation. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | win2019, SQL2019 |  |  | Yes | copy of mainframe master | [9 empty] | Yes | [10 empty] | HV- Agency Systems |  | N/A | Discard
Application #49 | 5668 |  | HV-Harleysville Enterprise Web Services (HEWS) | Grouping of services, an application service function provided using network address over the web enabling communication between two systems. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | win2019, SQL2019 |  |  | No | Uses various databases used by other apps. Does not have it's own database | [9 empty] | No | [12 empty] | N/A | N/A
Application #50 | 5670 |  | HV-Question Answer Service | Main service component for the URE application to determine questions to ask and then save responses Dependent on adding products. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | win2019, SQL2019 |  |  | Yes | Question, Service_Log | [9 empty] | No | [10 empty] | HV-Question Answer Service |  | UND120 – Commercial Lines, Property, Casualty - indefinite | Archive
Application #51 | 5712 |  | HV-Proxix (Corelogic) | Vendor supplied Geo coding and territory information used by Duck Creek (Core Logic) and Commercial Lines (AQS) |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  | SQL2019, Win2019 |  |  | Yes | Monthly datasets provided by vendor. ,DAT files | [20 empty] | HV-Proxix (Corelogic) |  | N/A | Discard
Application #52 | 5713 |  | HV-Melissa (address check) | Vendor supplied information used to validate and scrub addresses for Duck Creek quotes and policies. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | #N/A |  |  | No | Monthly datasets provided by vendor. ,DAT files | [9 empty] | No | [10 empty] | HV-Melissa |  | N/A | Discard
Application #53 | 5717 |  | HV-Active PDF | HV-Active PDF |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | #N/A |  |  | Yes | pdf images, batch print info | [9 empty] | Yes | [10 empty] | HV-AQS |  | N/A | Discard
Application #54 | 5720 |  | HV-UW Assignment | Web application for updating workflow routing within Image Right for Commercial Lines |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | #N/A |  |  | Yes | HV U/W names and ID's/ SQL | [9 empty] | No | [10 empty] | HV-Imageright |  | N/A | Discard
Application #55 | 6010 |  | HV-Expiration | Policy / Renewal tracking application |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | #N/A |  |  | Yes | Harleysville legacy system (policy summary index) for renewal processing of all personal and commercial policies both automated and manual and CICS, policy info, renewal info, dates, indicators, term info, premium, bill acct, status, etc (VSAM) CORP00PV.AGCY.EXP.REN.MASTER.C CORP00PV.AGCY.EXP.REN.IDX.C | [9 empty] | Yes | [10 empty] | 6010-HV-Expiration |  | N/A | Discard
Application #56 | 6096 |  | HV-AQS Batch Print | This is a custom .net application to package HVAQS Policy Output utilizing Active PDF. This component provides the bar coding on documents for Finishing. It also generates a transactional cover letter per Billing Account,applies the NY ID Card PDF417 bar code and packages new business and renewal output with the Agency Bill Schedule |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | #N/A |  |  | Yes | Input xml received from HV policy systems and images are created using this app and sent to HV-Q Direct for printing, images are fed to Imageright from HV-AQS not HV-BatchPrint. Input PDFs are received from from HV-AQS and HV-Peer Sync (to transfer pdfs to server) | [9 empty] | Yes | [10 empty] | HV-AQS |  | N/A | Discard
Application #57 | 6393 |  | HV-Agency Licensing | Capturing of agency and producer information from CMS G2 onto a SQL database, which is enriched with demographic and banking info from the Harleysville Agency Master file, providing agency licensing validation to Harleysville systems and a regular ETL feed to Nationwide DPIM and AMF systems |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  | #N/A |  |  | No | Producer Data from Vertfore - | [20 empty] | ThirdParty Vertofore |  | N/A | Discard
Application #58 | 6397 |  | HV-ISO PPC | 3rd Party data source that integrates with Duck Creek and CL AQS to supply Property Protection Class base on geographic information |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  | DB2 |  |  | Yes | ISOLocation API product updates stored on the SQL database. Monthly updates received from 3rd party | [9 empty] | Yes | [10 empty] | HV-ISO PPC |  | N/A | Discard
Application #59 | 6405 |  | HV-CoreLogix Quarterly Update | Comparison Utility CoreLogix is a leading provider of consumer, financial and property information, analytics and services to business and government |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  |  |  |  | No | 0 | [9 empty] | Yes | [10 empty] | HV-Proxix (Corelogic) |  | N/A | Discard
Application #60 | 6408 |  | HV-Bill Matrix | 3rd Party Vendor for on line payments -- an online payment system operated by BillMatrix Corporation that is designed to accept payments |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  |  |  |  | No | Credit card processing and one time EFT for Harleysville | [9 empty] | Yes | [12 empty] | N/A | N/A
Application #61 | 6422 |  | HV-Account Proposal | Application that generates Account Proposal for CL agents |  |  | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | Yes | Requests entered via HV CL Agent Portal and Underwriter Workbench to generate real time Account Proposal generated using HV-Documaker. A PDF is returned to requesting user. HV-Documaker does not store the pdf or send it to ImageRight. | [9 empty] | No | [10 empty] | HV-AQS |  | N/A | Discard
Application #62 | 6424 |  | HV-AuditWin Plus | Utility software used by field auditors to manage audit assignments, inventory and scheduling. Audit assignments are downloaded to the AuditWin Plus (formerly known as Field Manager) from Audit Control Environment (ACE). |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | No | Service that retrieves data, no data is stored | [9 empty] | Yes | [10 empty] | HV - ACE Premium Audit |  | N/A | Discard
Application #63 | 6452 |  | HV-ACCESS Collections | 3rd Party Vendor for collections agency -- With Access Collections, LLC you'll have the skill and expertise needed to collect your consumer debt, delivering improved cash flow and reduced days outstanding. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  |  |  |  | No | File exchanges with 3rd party on receivables | [9 empty] | Yes | [12 empty] | N/A | N/A
Application #64 | 6453 |  | HV-PNC Bank Feed | 3rd Party Vendor for agent sweep screens - PNC/Wells Fargo Bank |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  |  |  |  | No | Lockbox for Harleysville for Payments and stubs | [22 empty] | N/A | N/A
Application #65 | 6500 |  | HV-AQS User SecurityLoad | Utility to load new NW/Harleysville agents as Users to AQS. |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | UserSecurityLoad SQL db | [9 empty] | Yes | [10 empty] | AQS |  | N/A | Discard
Application #66 | 6512 |  | HV-AQS - Doc Utility | Doc Utility is used by AQS Configuration Analysts and Developers for adding and updating document data. |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | Yes | AQS_Docs | [9 empty] | No | [10 empty] | AQS |  | N/A | Discard
Application #67 | 6859 |  | HV - eForms Generation App | Generates ACORD COI (Certificate of Insurance) and EOP (Evidence of Property) forms currently used by the Service Center group. Minimal user entry required for form completion |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | EFORM - Acord form data | [9 empty] | No | [10 empty] | HV-eForms Generation App |  | N/A | Discard
Application #68 | 7558 |  | HV-Hazard Grade Matrix (HGM) | Application used by underwriters to get the Matrix Grade; also used by Product staff to update information for use in Underwriting decisions via an admin page. |  | HV | Esposito, Colleen M |  | Joanne Nuzzi |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | Yes | ISOMATRIXHGM - List of all hazard information. | [9 empty] | No | [10 empty] | HV-HGM |  | Indefinite | Archive
Application #69 | 7814 |  | HV-CL Insured Account search tool | CL Insured Account name search tool used by processing groups for a lookup of account and billing account \# info. A Link to Image Right is included |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 12/31/26 |  |  |  |  | No | N/A | [9 empty] | No | [10 empty] | CL Insured Account DB (IADB) |  | N/A | N/A
Application #70 | 7866 |  | HV-U279 Processing Form | New business and renewal communication tool between Underwriting and Processing. Supports instructions for setting up billing and policies. Tool to generate a form for completion and save to Image Right for future updates. | UND | HV | Esposito, Colleen M |  | Joanne Nuzzi |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | No | [10 empty] | N/A |  | #N/A | #N/A
Application #71 | 7944 |  | HV-PowerShell-BuildDeployment-Scripts | Jenkins is the tool we use for developers to initiate the PowerShell scripts to do the build/deployment - This will be used to deploy AQS and WebMethods code (confirm if this is already gone, switch to urban code deploy) |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | No | [10 empty] | N/A |  | #N/A | #N/A
Application #72 | 7954 |  | HV-Core Integration Svc | Collection of web services utilized by numerous applications. A large number are used by UWWB and AQS NB and Renewal process |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | No | [10 empty] | N/A |  | #N/A | #N/A
Application #73 | 7955 |  | HV-MVR Services | Used by AQS and UWWB to request/access driver MVR records. MVR records are then stored in ImageRight. Also contains a batch component, that calls an external service, that scans public records for additional driver data that is then stored in a local database |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  |  |  |  | #N/A | #N/A | [9 empty] | Yes | [10 empty] | AQS |  | #N/A | #N/A
Application #74 | 7956 |  | HV-Core Logic Svc | Services that handle Hazard data for Property policies. Used by NB and Renewal processes |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | No | [10 empty] | N/A |  | #N/A | #N/A
Application #75 | 7957 |  | HV-Billing Svc | Services that support Billing |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | No | [10 empty] | N/A |  | #N/A | #N/A
Application #76 | 7959 |  | HV-Update AQS Stat Feed | nightly batch job (EDR0090 |  | HV | Esposito, Colleen M | [5 empty] | In Progress - Planning | 04/01/27 |  |  |  |  | #N/A | #N/A | [9 empty] | Yes | [10 empty] | N/A |  | #N/A | #N/A
Application #77 | 8039 |  | HV-CLManuscripts | HV-CLManuscripts CL Manuscripts (or CL Corporate Form) templates publish from CL Forms Sharepoint library to AgentPortal, UWWB, and AQS.Agent Portal –Supplemental applications and Questionaires, versions, and link to retrieve those forms once selected UWWB – Manuscript Templates – Forms/endorsements, versions, and a link to retrieve forms (same forms used for AQS) AQS – Manuscript endorsement titles and wording is used for AQS forms |  | HV | Esposito, Colleen M | [5 empty] | Not Started | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | No | [10 empty] | N/A |  | #N/A | #N/A
Application #78 | 9999 |  | Commercial Auto | All policy and quote data in BA, this is a supporting app with rates. | Support | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 12/31/26 |  |  |  |  | #N/A | #N/A | [9 empty] | Yes | [10 empty] | TBD |  | #N/A | #N/A
Application #79 | 0000 |  | Policy Management System (PMS) CalFarm | Old CalFarm company acquired. | Policy | PCIO | Esposito, Colleen M |  | Prasad Penchala |  |  |  | In Progress - Planning | 03/31/26 |  |  |  |  | Yes | Files and backup tapes from acquisition of CalFarm Insurance 4/1/1999. Migration was during 2000 - 2001 | [9 empty] | No | [10 empty] | TBD |  | 0 | Archive

## ReadMe
Instructions
This questionnaire must be completed for all individual applications in-scope of decommissioning, under PCIO and HV platform. The information you provide is essential for Capgemini team to perform a thorough decommissioning assessment and creating decommissioning handbook covering: -Sizing the overall application landscape -Grouping applications based on ownership, Target application status, and current status -Planning stakeholder meetings, workshops in a structured and efficient manner -Capturing the dependencies to be remediated / taken-care of before entire application is decommissioned -Capture data archival requirements Each response is required to assess the application in terms of technical feasibility, risk and criticality, PoA alignment. At the end of the analysis phase, Capgemini will consolidate and share the master decom repository with all relevant stakeholders for data validation. To simplify data entry, Capgemini has provided dropdown lists & sample responses Questionnaire Structure: The questions are broadly categorized into the following sections: General (Business & Functional) Risks Application Dependency Data Compliance Operations Infra Vendor Financial
Last updated: 27 Jan 2026 79 Apps in scope for decom: CLS Decom Master 2024.xlsx filter the column 'Decommissioning Planning Status' > select the following Not Started In Progress - Planning Out of 79, following 3 apps are being decommd this week (week of 27 Jan 2026) by NW HV-Proxix (Corelogic) HV-CoreLogix Quarterly Update HV-Update AQS Stat Feed

## Questionnaire
Category -> | General (Business & Functional) | [21 empty] | Risk | [5 empty] | Application Dependency | [12 empty] | Data | [9 empty] | Compliance |  |  | Operation | [7 empty] | Infra |  |  |  | Third party/vendor |  |  | Financial
# | Application ID | Application Name | Application Description | Line of Business | App Legacy Suite in NW context | App Owner - Name | Business Owner - SME Name | App SME/Tech lead | Is the application in-house developed or a 3rd Party product / COTS product? | Application Category | Application Type | Application Category | Access - UI <Data from NW master sheet> | Is this application / product in scope for decommissioning ? | Target decom end date based on WBS | Is this application being decommissioned due to non-usage by business or because of modernization? If any other reason, please provide details | Tech stack of the application | Business Criticality of the application? (Based on the biz. Processes involved) | Size of the application based on Lines of Code (LoC) | What is database of the application | Point of Arrival (POA) / Target Application Name | Point of Arrival (POA)/ Target Application readiness date | Is this application active or isolated in current portfolio of Nationwide? | What is the age of this application? | Minimum expected life for the application / product? | Does this application handles any Legal Compliances /Audit requirement on its own? | Does this Application interface with any other application which satisfy regulatory compliance need? | Revenue /user impact if this application is down? | Is this a single application or a group of applications? | Access - Batch/Bulk <NW Context; data from master sheet> | Does the application have connectivity with external application (applications outside the customer landscape)? | Do external applications (applications outside the customer landscape) access data directly or via APIs from this applications' / business functions' database? | Names of Incoming Internal Dependent Applications | Count of Incoming Interfaces from other applications | List the incoming type of interface (FTP, DB calls, MQ, API, any other) | Names of Outgoing Dependent Applications | No. of Outgoing Interfaces to other applications | List the outgoing type of interface (FTP, DB calls, MQ, API, any other) | App Suite Dependency | Dependencies (App Level) | No. of reports and their frequency this application generates | Size of the current database | Database/Data Store description; Type of data | Application data is owned by? | Does this application have pre-archived (historical) data? | How long the historical/app data need to be maintained as per regulations? | Database backup frequency | Is there a pre- defined data purge policy? | Preferred Data treatment Option | What is the SLA slab for retrieving the archived data? | What is the SLA slab for retrieving historical data? | Is there any source code archival policy for this application (Not the data archival). | Period for advance notice to the Technology Owners (Infrastructure team, DR team) reg. shutting down this application? | What is the hardware / software release procedure and communication model at Nationwide? | No. of internal users of this application | No. of external users of this application | Are there any timeframe defined to migrate the existing external users / customers to access the new application before shutting down this application? If yes, what is the defined timeframe? | Are there any ongoing projects (enhancement/changes) in this application? | Level of documentation for this application | What is the level of app team's knowledge on the application? | What is the support level rendered to this application? (Shared team /Dedicated team) | What are the FTE & Contractor count for production support & maintenance for this application? | Does this application use shared or dedicated server? | Count of application servers | Count of data servers | Number of other applications sharing the same server with this application | Provide all the Third party tools/vendors used by this application | License renewal period for the tools being used by this application | Any legal agreements between the tool vendors / hardware vendors and client | Monthly application run cost in USD | Planning Guide Document | Planning Guide Doc Lead | Next Steps | Archive Pattern | Archive Storage | Data Access to Archive Data | Must have( Present) | Must have (Not present) | Good to have (Present) | Good to have (Not Present) | Progress Percentage | In scope for analysis | Signed off by App SMEs
Guidelines -> | <Free Text> Enter your Application ID | <Free Text> Enter the name of application | <Free Text> Enter description of your application in a few lines | <Free Text> Which business area does the application belong to | <Free Text> Please mention whether the application is from PCIO or HV //Info missing for some apps | <Free Text> Name of the designated owner accountable for the application. | <Free Text> Name of the business owner accountable for the application. //Info missing for few apps | <Free Text> Name of the designated SME who can help with providing additional info about the app //Info missing for few apps | <Free text> Whether the app is custom developed, acquired, 3rd Party product or COTS product? | <Select from Drop-Down> Front end, Back end, Both | <Free text> E.g. Web Service, Desktop, Legacy application, IT Service, Infrastructure Service, Utility, 3rd Party | <From NW Master Data> | <From NW Master Data> //Info missing for few apps | <Free text> E.g. Yes/No/Already decommissioned/Decommissioning in progress //Based on the Master Data shared by NW on 23 Jan 2026 | <Free text MM/DD/YY> //Based on the WBS on Feb 19th 2026 | <Free Text> | <Free Text> (e.g., Mainframe COBOL, AS400, Java VB, DB2, C on Mainframes, .NET, SAP) //Need more details | <Select from Drop-Down> (1-Very Low, 2-Low, 3-medium, 4-high, 5-very high) Business criticality of the application. E.g. Very high criticality - core-apps, High - disruptions impact operations, Medium- non-core business apps (support functions), Low - peripheral business functions with low revenue impact Very low criticality- Desktop apps and productivity tools | <Select from Drop-Down> 1-Very Low (Less than 5000 LoC) 2-Low (5000-10000 LoC) 3-Medium (10000-25000 LoC) 4-High (25000-50000 LoC) 5-Very High (>50000 LoC) | <Free Text> (e.g. DB2, VSAM, SQL Server ,Oracle, MongoDB) //Need more details | <Free Text> Target application or point of arrival to which the application is being migrated / modernized / consolidated | <Free Text> Date/Quarter Date on which the application target / PoA will be ready | <Free text> Active-not isolated, Active-isolated, Not active-not isolated, not active-Isolated | <Select from Drop down> Number of years since initial production go‑live. 1 - 0 to 5 Years 2 - 5 to 10 Years 3 - 10-15 Years 4 - 15-20 years 5 - >20 Years | <Select from Drop-Down> How long are these applications expected to stay before they are decommissioned? Ideally should be before the decom target date | <Select from Drop-Down> Yes/no | <Free text> Yes/No | <Select from dropdown> (1-Low, 2-Medium, 3-High,4-Very High) | <Select from Drop-Down> | <Free text> Yes/No | <Free text> Yes/No If yes, please mention the names of the applications | <Free text> Yes/No If yes, please mention the names of the applications | <Free Text> Names of Incoming Dependent Applications within Nationwide | <Free text> Number of FTPs, DB calls, MQs, API calls | <Free Text> List of interface types | <Free Text> Names of outgoing Dependent Applications within Nationwide | <Free text> Number of FTPs, DB calls, MQs, API calls | <Free Text> List of interface types | <From NW Master Data> //Need breakdown of incoming & outgoing | <From NW Master Data> //Need breakdown of incoming & outgoing | <Free Text> | <Select from Drop-Down> (1- <10GB, 2- 10-30GB, 3- 30-70GB, 4- 70-100GB, 5- >100GB) | <From NW Master Data> | <Free Text> System of records //Missing for some apps | <Select from Drop-Down> Yes/No | <Free Text> //Data filled from NW master sheet - Retention Requirement. Is it same for historical & app data? | <Select Drop Down List> Self- Explanatory (1-> Daily, 2-> Weekly, 3-> Monthly, 4-> Fortnightly, 5-> Annual) If any of the tables has monthly backup frequency, mark this as annual | <Free Text> If yes, please mention the retention duration and purge policy | <Data from NW master - database disposition> (Archival, Purge, Retain) //Info from NW Master data. is this same for historical & app data? | <Free Text> | <Free Text> | <Select from Drop-Down> Eg: For mainframe apps, whether the source code to be stored inside or outside mainframe like GitHub | <Free Text> | <Free Text> E.g. Release procedure via ServiceNow or mail | Select from Drop-Down | Select from Drop-Down | <Free Text> | Select from Drop-Down | Select from Drop-Down | Select from Drop-Down | Select from Drop-Down | <Free Text> | <Free Text> | <Free Text> If application & data uses same server, please mention it as part of application server count | <Free Text> | <Free Text> | <Free Text> | <Free Text> | Select from Drop-Down | <Free Text> Monthly BAU/run cost for operations and support | <From NW Master Data> | <From NW Master Data> | <From NW Master Data> | <From NW Master Data> | <From NW Master Data> | <From NW Master Data>
Must have/ Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Good to have | Must have |  | Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Good to have | Must have | Must have | Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Must have | Good to have | Good to have | Good to have | Must have | Good to have | Good to have | Good to have | Good to have | Must have | Must have | Must have | Must have | Must have | Must have | Must have | Good to have | Good to have | Good to have | Good to have | Good to have | Good to have | Good to have
Sample Answer - Mainframe | 313 | Policy Billing Mainframe | Core mainframe system responsible for policy billing, premium calculation, and invoicing |  | PCIO | Colleen |  |  | In‑house developed | Back End | Legacy Mainframe Application |  |  | Yes |  | Modernization to distributed platform | COBOL, JCL, CICS, DB2, VSAM, z/OS | Very High | Very High | DB2 | Duck Creek | Q3 2026 | Active – Isolated | 0 to 5 Years | < 3 Months | Yes | Yes | Very High | Group | Yes | No | Yes | Claims, CRM | 5 | FTP, MQ | Fraud System | 8 | MQ |  |  | 15 reports monthly | less than 10GB |  | Policy Data | Yes | 7 Years | Weekly | No | Archive | 10 days | 10 days | Mainframe CAB process | 15 days | ServiceNow | 1 - 10 Users | > 30 Users | 2 months | No | Minimal Documentation | Has only basic information | Shared | 4 | Dedicated | 3 | 2 | 1 | IBM Omegamon | NA | No | 45,000 USD
Sample Answer - Distributed | 7 | Claims Portal | Web‑based portal for end‑to‑end claims processing |  | HV | Colleen |  |  | COTS with customization | Both | Web Application |  |  | Yes |  | Business consolidation | ASP.NET Core, SQL Server, IIS, Azure | High | Medium | SQL Server | Duck Creek | Q3 2026 | Active – Isolated | 15-20 years | < 3 Months | No | No | High | Single | No | Yes | No | NA | 2 | REST API | Claims System | 3 | REST API |  |  | 30 reports daily | 10-30GB |  | Claims function | No | 3 Years | Daily | Yes, 3 years retention and purge the data | Purge | 10 days | 10 days | NA | 30 days | Via Mailer | > 30 Users | 1 - 10 Users | No | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | 6 | 4 | 3 | New Relic, Splunk | Annual | No | 25,000 USD
Application #1 | 451 | Pathway (DSM) | Maintains customer information at the name and address level | Personal Lines PCIO Commercial Lines | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Patty West | In-house | Both | Application | Support | Yes | Not Started | 2026-11-06 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | DB2, CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs, | High | High | DB2 Tables | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | No | Yes | Low | Part of Group | Yes | No | No | AID01.FPP.CONVERT.PATH.FILE.NBP.PC FTP(RECEIVE) AID01.DISK.PAS.NIGHTUP.PYCR.FILE FTP(RECEIVE) AID01.DISK.PATH.POLICY.INTFCE.TO.ECIF FTP(RECEIVE) Mainframe Bonds - 913 Mainframe Commercial Property - 911 Mainframe Farm - 921 Mainframe General Liability (GLS) - 910 Foreign Assets-OFAC 1215 Mainframe Policy Entry - 924 Mainframe Package Control - 912 Mainframe Business Auto - 909 Mainframe Business Owners (SBO) - 923 Mainframe Workers Comp - 926 DB2 - Base - 5060 | 17 | FTP,Flat Files, GDGs, VSAM | Mainframe Farm - 921 Mainframe Policy Entry - 924 DUDE.NIGHTUP.FTP.PATH.HSHLD.UPDT (GM1) DUDE.NIGHTUP.FTP.PATH.DATALOAD.FMP(GM1) ECIF.NIGHTUP.FTP.PATH.DATALOAD.FMP(GM1) | 5 | FTP,Flat Files, GDGs, VSAM | 912 Mainframe Package Control | Specified in AH and AK | Zero | 10-30GB | DB2 Tables- Around 20 Tables | Personal Lines, PCIO Commercial Lines | No | N/A | Daily | Purges Data that is over 4 years old | Discard | N/A | N/A | Source code is stored in Changeman. Documentation is stored in Sharepoint. | 30 days - App Specific | NA | 20 - 30 Users | 1 - 10 Users | N/A | No | Outdated Documentation | Has operational & business knowledge | Dedicated | 2 | Shared | NA | NA | NA | NA | YES | Yes | Combined | Pathway (DSM) | Patty/The Mechanics | 10/30-Not sure it is being used for householding ,Lisa and team to do more research on tables and ecosystem | N/A | N/A | N/A | 52 | 0 | 23 | 0 | 100%
Application #2 | 909 | Mainframe Business Auto | Policy processing system for Business Auto Policies. | Mainframe Business Auto | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Mike Hansen | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | zOS, CICS, DB2 on zOS, COBOL, JCL, SQL, Batch Jobs, Files, Tapes, Tablebase, Verisk reporting (MVR), Lexus Nexus, Changeman, UAC | High | High | DB2 on zOS, SQL, VSAM, Tape | CL Policy Center | The last policies on the system expire on 5/1/2026 and will migrate between 1/1/2026 and 11/1/2026 depending on the success of the migration. Target Application is Active from 2020 | Active, Not isolated? | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | Agent Master File (993),Bureau Shared Systems (1416),CIC TS for zOS (5759),DW Eproduct (3905),Flex Billing (1009),Workload Engineering Solutions (8923), Mainframe Package Control(912), Policy Reload (1220),Mainframe Business Owners (923) | 35 | FTP, MQ,API, Flat Files, VSAM | Advice System (1207),Alpha Search (1208),Infogix ACR (7358),Claims Batch (P&C)(4433),DW Eproduct (6861),Edit Daily (1415), Policy Expirations (1418),Form Letter Correspondence incl. Proof of Mail (1211),Workload Engineering Solutions (8923),Pathway(DSM)(451), Mainframe Package Control(912), Commercial PAK Print (4246),Remarks System (941),AG_AMI_AI_Download (882) | 90 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 20 (Most of the reports are monthly, Some are annual) | 10-30GB | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM rate files, class files, edit files and tablebase VSAM files for entry, master and quotes. Also automatic renewal VSAM files VSAMC.PPV.DATA.ENTRY.INDEX VSAMC.PPV.DATA.ENTRY.MASTER VSAMC.PPV.INDEX VSAMC.PPV.MASTER VSAMC.PPV.LIVE.RATE VSAMC.PPV.QUOTE.PRINT.INDEX VSAMC.PPV.QUOTE.PRINT.MASTER VSAM1.PPV.ACCTDIST.MASTER VSAM1.PPV.CLASS VSAM1.PPV.QUOTE.INDEX VSAM1.PPV.QUOTE.INDEX.PRIOR VSAM1.PPV.QUOTE.MASTER.PRIOR VSAM1.PPV.QUOTE.MASTER VSAM1.PPV.QUOTE.INDEX.CURRENT VSAM1.PPV.QUOTE.MASTER.CURRENT VSAM1.PPV.RECYCLE.INDEX VSAM1.PPV.RECYCLE.MASTER VSAM1.PPV.RENEW.INDEX VSAM1.PPV.RENEW.MASTER VSAM1.PPV.VEHICLE.MAKE VSAM files used for inquiry during the nightly batch cycle VSAMN.PPV.DATA.ENTRY.INDEX VSAMN.PPV.DATA.ENTRY.MASTER VSAMN.PPV.INDEX VSAMN.PPV.INDEX.AFMR VSAMN.PPV.LIVE.RATE VSAMN.PPV.MASTER VSAMN.PPV.MASTER.AFMR VSAMN.PPV.QUOTE.PRINT.INDEX VSAMN.PPV.QUOTE.PRINT.MASTER | Mainframe Business Auto | Yes | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE. Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase, Verisk (DMV & 3rd Party reporting), MVR | YES | Yes | Combined | Mainframe Business Auto | Prasad/ Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #3 | 910 | Mainframe General Liability (GLS) | Policy Processing system for General Liability policy types. | Mainframe General Liability (GLS) | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Prasad Penchala | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | zOS, DB2, CICS, COBOL, JCL, SQL Changeman | High | High | DB2 on zOS, SQL, VSAM, Tape | CL Policy Center | 7/31/2026 - Last policy has migrated to PC on 01/02/2026 Target Application is Active from 2020 | Active, Not isolated? | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | Agent Master File (993),Alpha Search (1208),Bureau Shared Systems (1416),CICS TS for zOS (5759),Mainframe Commercial Property (911), DW Eproduct (3905),Flex Billing (1009),Workload Engineering Solutions (8923),Mainframe Package Control(912), Commercial PAK Print (4246), Policy Reload (1220) | 15 | FTP, MQ,API, Flat Files, VSAM | Advice System (1207),Infogix ACR (7358),Claims Batch (P&C)(4433),CICS TS for zOS (5759),DW Eproduct (3905),Edit Daily (1415), Workload Engineering Solutions (8923),Policy Expirations (1418),Form Letter Correspondence incl. Proof of Mail (1211), Pathway (DSM) (451),Mainframe Package Control(912), Commercial PAK Print (4246),Remarks System (941),AG_AMI_AI_Download (882) | 60 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 10 ( Most of the reports are monthly, Some are annual) | 10-30GB | VSAM policy and quote data in the index, master, data entry and quoue hold files. Also VSAM rates, rate date and class code files VSAM Files – Index - VSAMC.GLS.INDEX Master - SAMC.GLS.MASTER history index - VSAMC.GLS.HISTORY.INDEX history master - VSAMC.GLS.HISTORY.MASTER data entry - VSAMC.GLS.DATA.ENTRY quote - VSAMC.GLS.QUOTE.HOLD Quote print - VSAMC.GLS.QUOTE.PRT Rate date - VSAMC.GLS.POL.RATE.DATE rate file - VSAMC.GLS.LIVE.RATE,VSAM1.GLS.PSEUDO.RATE class code file - VSAMC.GLS.LIVE.CLASS quote file - VSAMC.GLS.QUOTE.HOLD Renewal data entry - VSAMC.GLS.DATA.ENTRY.RENEW, VSAMC.GLS.DATA.ENTRY.WORK Renewal rate date - VSAMC.GLS.RATE.DATE.RENEW,VSAMC.GLS.RATE.DATE.WORK Tape Files - Policy data is in the below tape files AID01.GLS.FINAL.YTD.INDEX.PURGE AID01.GLS.FINAL.YTD.MASTER.PURGE AID01.GLS.YTD.INDEX.PURGE AID01.GLS.YTD.MASTER.PURGE DB2 Tables – General Liability does not own any DB2 tables. Hercules - Data in Index and Master file is ingested to Hercules | Mainframe General Liability (GLS) | Yes | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE. Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | AUSUM, Tablebase, Verisk reporting (MVR), Lexus Nexus, | YES | Yes | Combined | Mainframe General Liability (GLS) | Prasad/ Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #4 | 911 | Mainframe Commercial Property | Policy processing system for the Commercial Property Line of Business | Commercial Property | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Rhonda Giedd | In-house | Both | Legacy Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | zOS, DB2, CICS, COBOL, JCL, SQL , Tape, VSAM, GDG, UAC Changeman | High | High | Tape, DB2, VSAM, GDG | CL Policy Center | 7/31/2026 Last policy has migrated to PC on 01/02/2026 Target Application is Active from 2020 | Active, Not isolated | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | AG2_2 – Agent Master file(993) BSC-Bureau Shared Systems(1416) CIC_2-CICS TS for zOS(5759) DWS-DW Eproduct(3905) DMP-Run Services(6861) FPP-FLEX Billing(1009) MIS-Workload Engineering Solutions(8923) PPH_2-Coml PAK Print(4246) PPJB005B-?? PPZ-Mainframe Package Control(912) RLS-Policy Reload(1220) SBO-Mainframe Business Owners(923) | 25 | FTP, MQ,API, Flat Files | ADV-Advice System(1207) BAL-Infogix ACR(7358) BOJ-Claims Batch(4433) CIC_2- CICS TS for zOS(5759) CP2-Run services App DB2 Internal Activity(6861) DWS- DW Eproduct(3905) EDS_2-Edit Daily(1415) EOG-Claims Batch(4433) EXP-Policy Expirations(1418) GLS-Mainframe General Liability(910) MIS-Workload Engineering Solutions(8923) MK2-Pathway-DesMoines(451) PPH_2- Coml PAK Print(4246) PPZ- Mainframe Package Control(912) RMS-Remarks System(941) TAD_2- AG_AMI_AI_ Download(882) | 80 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 27 ( Most of the reports are monthly, Some are annual) | 10-30GB | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM rate files and tablebase VSAM files – Index - VSAMC.CPS.INDEX Master - VSAMC.CPS.MASTER Data entry - VSAMC.CPS.DATA.ENTRY Rates - VSAMC.CPS.RATE.FILE Renewal Data Entry - VSAMC.CPS.DATA.ENTRY.RENEW Quotes - VSAMC.CPS.QUOTE.ENTRY Quote print - VSAMC.CPS.QUOTE.PRINT Account Dist - VSAMC.CPS.ACCTDIST DB2 Tables – Commercial Property does not own any DB2 table Tape Files - AID01.CPS.FINAL.YTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules" | Mainframe Commercial Property | Yes | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE. Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase, Verisk reporting, Changeman | YES | Yes | Combined | Mainframe Commercial Property | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #5 | 912 | Mainframe Package Control | Policy processing system for the commercial package control system. | Mainframe Package Control | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Mike Hansen | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | zOS, CICS, DB2 on zOS, COBOL, JCL, SQL, Batch Jobs, Files, Tapes, Tablebase, Verisk reporting (MVR), Lexus Nexus, Changeman, UAC | High | High | DB2 on zOS, SQL, VSAM, Tape | CL Policy Center | 7/31/2026 Last policy has migrated to PC on 01/02/2026 Target Application is Active from 2020 | Active, Not isolated? | >20 Years | 3-6 Months | No | Yes | High | Part of Group | Yes | Yes | No | Agent Master File (993),Bureau Shared Systems (1416),CIC TS for zOS (5759),DW Eproduct (3905),Flex Billing (1009),Workload Engineering Solutions (8923), Mainframe Package Control(912), Policy Reload (1220),Mainframe Business Owners (923) | 172 | FTP, MQ,API, Flat Files, VSAM | TBD | 210 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 115 (Most of the reports are monthly, Some are annual) | 10-30GB | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM edit files and tablebase VSAM files for entry, master and quotes. Also automatic renewal VSAM files VSAMC.PPZ.DATA.ENTRY.INDEX VSAMC.PPZ.DATA.ENTRY.MASTER VSAMC.PPZ.INDEX VSAMC.PPZ.MASTER VSAMC.PPZ.QUOTE.INDEX VSAMC.PPZ.QUOTE.MASTER VSAMC.PPZ.QUOTE.PRINT.INDEX VSAMC.PPZ.QUOTE.PRINT.MASTER VSAM1.PPZ.RENEW.INDEX VSAM1.PPZ.RENEW.MASTER VSAM1.PPZ.DAILY.EDIT.ERRORS VSAM1.PPZ.DATA.ENTRY.INDEX.CURRENT VSAM1.PPZ.DATA.ENTRY.MASTER.CURRENT VSAM1.PPZ.DATA.ENTRY.INDEX.PRIOR VSAM1.PPZ.DATA.ENTRY.MASTER.PRIOR VSAM1.PPZ.QUOTE.INDEX.CURRENT VSAM1.PPZ.QUOTE.MASTER.CURRENT VSAM1.PPZ.QUOTE.INDEX.PRIOR VSAM1.PPZ.QUOTE.MASTER.PRIOR VSAM1.PPZ.RECYCLE.INDEX VSAM1.PPZ.RECYCLE.MASTER VSAM files used in the Pak money FMR process VSAMC.PPZ.RECYCLE.ERROR VSAM1.PPZ.BATCH.SUSPENSE.NUMBER VSAM files used for inquiry during the nightly batch cycle VSAMN.PPZ.DATA.ENTRY.INDEX VSAMN.PPZ.DATA.ENTRY.MASTER VSAMN.PPZ.INDEX VSAMN.PPZ.INDEX.AFMR VSAMN.PPZ.INDEX.AMFMR VSAMN.PPZ.MASTER VSAMN.PPZ.MASTER.AFMR VSAMN.PPZ.MASTER.AMFMR VSAMN.PPZ.QUOTE.INDEX VSAMN.PPZ.QUOTE.MASTER VSAMN.PPZ.QUOTE.PRINT.INDEX VSAMN.PPZ.QUOTE.PRINT.MASTER VSAMN.PPZ.RECYCLE.ERROR | Mainframe Package Control | Yes | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE. Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Manuscripts must be kept for XX years. | 30 days - App Specific | NA |  |  |  | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase | YES | Yes | Combined | Mainframe Package Control | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 51 | 1 | 20 | 3 | 94.67% |  | Signed off by Prasad on 02-18-2026
Application #6 | 921 | Mainframe Farm | Policy processing system for Farm policies covering property and liability. | Mainframe Farm | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Prasad Penchala | In-house | Both | Legacy Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | zOS, DB2, CICS, COBOL, JCL, SQL , Tape, VSAM, GDG, UAC Changeman | High | High | Tape, DB2, VSAM, GDG | CL Policy Center | 7/31/2026 Last policy has migrated to PC on 01/02/2026 Target Application is Active from 2020 | Active, Not isolated | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | Claims Batch (P&C) (4433),Agent Master File (993),CICS TS for zOS (5759),Flex Billing (1009),Workload Engineering Solutions (8923), Mainframe Package Control(912), Commercial PAK Print (4246),Policy Reload (1220) | 25 | FTP, MQ,API, Flat Files | Advice System (1207),Infogix ACR (7358),Mainframe Commercial Property (911),DW Eproduct (3905),Edit Daily (1415),Policy Expirations (1418), Run Services Application DB2 Internal Activity (6861),Workload Engineering Solutions (8923),Pathway(DSM)(451),Form Letter Correspondence incl. Proof of Mail (1211), Mainframe Package Control(912), Commercial PAK Print (4246),AG_AMI_AI_Download (882) | 30 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 20 ( Most of the reports are monthly, Some are annual) | 10-30GB | VSAM policy,quote and rate data; database inflation factor, farm credit, RCE VSAM Files – Index - VSAMC.FMP.INDEX Policy - VSAMC.FMP.POLICY Quote - VSAMC.FMP.QUOTE.HOLD data entry - VSAMC.FMP.DATA.ENTRY quote print - VSAMC.FMP.QUOTE.PRINT Worksheet - VSAMC.FMP.TEMP.WRKSHEET.FILE accounting/distribution - VSAM1.FMP.ACCTDIST rate data - VSAMC.FMP.RATES DB2 Tables – FB2T0070_RES_INFL_FCTR (Inflation Factors) FB2T0050_CRDT_INFO (Farm Credit) FB2T0030_CHS_DIVD (Farm Dividend) FB2T0300_RCE_GENERAL(RCE) FB2T0310_RCE_STRUCTURE(RCE) FB2T0320_RCE_COMPONENT(RCE) Tape Files - AID01.FMP.FINAL.YTD.PURGE AID01.FMP.YTD.PURGE AID01.FMP.MTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules | Mainframe Farm (WINS) | Yes | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE/Last Changed date Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase, Verisk reporting (MVR) | Yes | Yes | Combined | Mainframe Farm | Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #7 | 923 | Mainframe Business Owners (SBO) | Policy Processing System for Commercial Business Owners policies. | Mainframe Business Owners (SBO)? | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Prasad Penchala | In-house | Both | Legacy Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | zOS, DB2, CICS, COBOL, VSAM, Tape, GDG, JCL, SQL,Copybooks, MQ, UAC, Changeman | High | High | Tape, DB2, VSAM, GDG | CL Policy Center | 7/31/2026 Last policy has migrated to PC on 01/02/2026 Target Application is Active from 2020 | Active, Not isolated | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | Workload Engineering Solutions (8923),Agent Master File (993),CICS TS for zOS (5759),Flex Billing (1009),Mainframe Package Control(912), Commercial PAK Print (4246), Bureau Shared Systems (1416),Policy Reload (1220) | 20 | FTP, MQ,API, Flat Files | Advice System (1207),Alpha Search (1208),Infogix ACR (7358),DW Commercial - eproduct (7597),CICS TS for zOS (5759),Mainframe Commercial Property (911), DW Eproduct (3905),Edit Daily (1415),Allied Endorsements (940),Claims Batch (P&C) (4433),Policy Expirations (1418),Workload Engineering Solutions (8923), Pathway (DSM) (451),Code Cards-Manual Processing (1209),Mainframe Package Control(912), Commercial PAK Print (4246),Remarks System (941),AG_AMI_AI_Download (882) | 105 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 20 ( Most of the reports are monthly, Some are annual) | 10-30GB | VSAM policy and quote data in the index, master, data entry and quoue hold files. Also VSAM rates, class code and the accounting/distribution files VSAM files – Index - VSAMC.SBO.INDEX Master - VSAMC.SBO.MASTER Data entry - VSAMC.SBO.DATA.ENTRY class codes -VSAMC.SBO.LIVE.CLASS rates - VSAMC.SBO.LIVE.RATE Renewal index - VSAMC.SBO.DATA.ENTRY.RENEW Prior Index - VSAMC.SBO.PRIOR.INDEX Quotes - VSAMC.SBO.QUOTE.HOLD Quote print - VSAMC.SBO.QUOTE.PRINT Account Dist - VSAM1.SBO.ACCTDIST BOP Index after FMR - VSAM1.SBO.INDEX.AFMR BOP Master after FMR - VSAM1.SBO.MASTER.AFMR DB2 Tables – Businessowners does not own any DB2 table PPH_STATE_ZIP_INFLT_FCTR – State Zip Code Tape Files - AID01.SBO.FINAL.YTD.* AID01.SBO.YTD.* | Mainframe Business Owners (SBO) | Yes. It is assumed that the archive system of choice will contain all of the necessary data for the BOP system. This includes data from ‘final.ytd.purge’ tapes. Therefore, all BOP backup tapes will be deleted. | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE/Last Changed date Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase, Verisk reporting | Yes | Yes | Combined | Mainframe Business Owners (SBO) | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #8 | 924 | Mainframe Policy Entry | Policy Processing System for Inland Marine, Crime, Commercial Umbrella, and Personal Umbrella policies | Mainframe Policy Entry | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Rhonda Giedd | In-house | Both | Legacy Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | zOS, DB2, CICS, COBOL, JCL, SQL , Tape, VSAM, GDG, UAC Changeman | High | High | Tape, DB2, VSAM, GDG | CL Policy Center | 7/31/2026 Last policy has migrated to PC on 01/02/2026 Target Application is Active from 2020 | Active, Not isolated | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | AC2_2– Claims Batch(P&C)-4433 CIC_2- CICS TS for zOS(5759) FPP- FLEX Billing(1009) MIS- Workload Engineering Solutions(8923) PPH_2- Coml PAK Print(4246) PPZ- Mainframe Package Control(912) RLS- Policy Reload(1220) | 10 | FTP, MQ,API, Flat Files | ADV- Advice System(1207) BAL- Infogix ACR(7358) CIC_2- CICS TS for zOS(5759) DWS- DW Eproduct(3905) EDS_2-Edit Daily(1415) EOG- Claims Batch(4433) EXP- Policy Expirations(1418) MK2- Pathway-DesMoines(451) PE2-Rus Services App DB2 Internal Activity(6861) PPH_2- Coml PAK Print(4246) PPZ- Mainframe Package Control(912) Rem-Reminders(1221) RMS- Remarks System(941) TAD_2-AG_AMI_AI_ Download(882) WCS-Mainframe Workers Comp(926) | 75 | FTP, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 34( Most of the reports are daily and monthly) | 10-30GB | VSAM policy and quote data on our index, master, MOT and data entry files. VSAM Renewal index, master, MOT and data entry. VSAM files – Index (Policies and Quotes) - VSAM1.PCS.INDEX Master (Policies and Quotes) - VSAM1.PCS.POLICY Data entry (trigger record only for NB/REN)- VSAM1.PCS.DATA.ENTRY MOT (trigger record only for changes) - VSAM1.PCS.MOT class codes , forms-VSAM1.PCS.TABLE rates - no rate file for Policy Entry Renewal index - VSAM1.PCS.RENEW.INDEX Renewal Master - VSAMC.PCS.RENEW.POLICY Renewal Data Entry - VSAM1.PCS.RENEW.DATA.ENTRY DB2 Tables – Policy Entry does not own any DB2 table Tape Files - AID01.PCS.FINAL.YTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules" | Mainframe Policy Entry | Yes | Indefinite | Daily | Policies are purged one year after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE/Last Changed date Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase, Changeman | Yes | Yes | Combined | Mainframe Policy Entry | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #9 | 926 | Mainframe Workers Comp | Policy processing systems for Workers Compensation policies. | Workers Compensation | PCIO | Esposito, Colleen | Michael Martin / Angie Pike | Prasad Penchala | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | COBOL, JCL, SQL, CICS, zOS | High | High | DB2 on zOS, SQL, VSAM, Tape | CL Policy Center | 7/31/2026 Last policy has migrated to PC on 10/30/2025 Target Application is Active from 2020 | Active, Not isolated | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | Yes | No | Mainframe Package Control(912), Commercial PAK Print (4246),Policy Reload (1220),Mainframe Business Owners (923) | 25 | FTP, MQ,API, Flat Files | Advice System (1207),Alpha Search (1208),Infogix ACR (7358),Claims Batch (P&C)(4433),DW Eproduct (6861),Edit Daily (1415), Policy Expirations (1418),Form Letter Correspondence incl. Proof of Mail (1211),Workload Engineering Solutions (8923),Pathway(DSM)(451), Mainframe Package Control(912), Commercial PAK Print (4246),Remarks System (941),AG_AMI_AI_Download (882) | 85 | FTP, MQ,API, Flat Files | 912 Mainframe Package Control | Specified in AH and AK | 48 ( Most of the reports are monthly, Some are annual) | 10-30GB | VSAM files - index, master, data entry, MOT, class code descriptions, rates, unit stat, dividends, renewal index/master/data entry VSAM files – Index - VSAMC.WCS.INDEX Master - VSAMC.WCS.MASTER Data entry - VSAMC.WCS.DATA.ENTRY MOT - VSAMC.WCS.MOT class code descriptions - VSAMC.WCS.DESC rates - VSAMC.WCS.RATE.ENTRY, VSAMC.WCS.RATES unit stat - VSAMC.WCS.US.MASTER dividends - VSAMC.WCS.PARPLAN.MASTER Renewal index - VSAMC.WCS.RENEW.INDEX, VSAMC.WCS.INDEX.WORK Renewal master - VSAMC.WCS.RENEW.MASTER, VSAMC.WCS.INDEX.MASTER Renewal data entry - VSAMC.WCS.RENEW.DATA.ENTRY, VSAMC.WCS.DATA.ENTRY.WORK Endorsements - VSAM1.WCS.END.EDITS DB2 Tables – Work comp does not own any DB2 tables Tape Files - AID01.WCS.FINAL.YTD.PURGE AID01.WCS.YTD.PURGE.HISTORY Hercules - Data in Index and Master file is ingested to Hercules | Mainframe Workers Comp | Yes | Indefinite | Daily | Policies are purged 2 years after expiration date from master files. Purged policy data is written to the tape files. Purged policy data is retained Indefinitely. DELETE QUOTES 18 MONTHS AFTER EFFECTIVE DATE/Last Changed date Purge Quote after 90 days if the quote is converted to policy. | Archive | SLA is defined based on the type of user ( Power User, General User). Please refer RRC documenation for SLA details. | 2 days | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase Changeman | Yes | Yes | Combined | Mainframe Workers Comp | Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Glacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #10 | 940 | Allied Endorsements | Repository of policy endorsements available to Service Advantage policy systems, billing and TCS |  | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Toni Crowder | In-house | Both | Application | Support, Endorsement | Yes | Not Started | 2027-02-28 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs | Very High | High | Yes - VSAM | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | Yes | Yes | Medium | Part of Group | Yes | No | No | TBD | TBD | TBD | TBD | TBD | TBD | 912 Mainframe Package Control | SA/PCIO, TADA jobs, DR jobs, UWSW0082 - Rerate running every week. | TBD | 10-30GB | Endorsements by prefix/state with the start/end date of use. | TBD |  | Indefinite |  | TBD | Archive | TBD | TBD | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA |  |  |  | No |  |  |  |  | Shared | NA | NA | NA |  | Yes | Yes |  | Allied Endorsements |  | 10/30-Potential needed to keep, Lisa and team going to do more research on it | S3 | AWS S3 | Inquiry UI, API, Data Extract Process | 37 | 15 | 14 | 9 | 68%
Application #11 | 1208 | Alpha Search | Maintains customer information by policy at the customer name and address level | PCIO Commercial Lines | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Patty West | In-house | Both | Application | Support | Yes | In Progress - Planning | 2027-02-28 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs | Low | High | Yes - VSAM | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | No | No | Low | Part of Group | Yes | No | No | Agent Master File - 993 Claims Batch (P&C) - 4433 Form Letter Correspondence incl. Proof of Mail - 1211Mainframe Bonds - 913 Mainframe Policy Entry - 924 Mainframe Package Control - 912 Mainframe Commercial Property - 911 Mainframe Farm - 921 Mainframe General Liability (GLS) - 910 Mainframe Policy Entry - 924 Mainframe Business Owners (SBO) - 923 Mainframe Workers Comp - 926 Open Text Exstream - Z-OS - 4566 Workload Engineering Solutions - 8923 | 18 | DB2, VSAM, Flat Files | N/A | 0 | 0 | 912 Mainframe Package Control | Specified in AH and AK | Zero | less than 10GB | Customer Quotes | Personal Lines, PCIO Commercial Lines | No | N/A | Daily | Data is kept indefinitely | N/A | N/A | N/A | Source code is stored in Changeman. Documentation is stored in Sharepoint. The assembler source, no longer exists, just the object modules | 30 days - App Specific | NA | 20 - 30 Users | 1 - 10 Users | N/A | No | Outdated Documentation | Has operational & business knowledge | Dedicated | 2 | Shared | NA | NA | NA | NA | Yes | Yes | Combined | Alpha Search | Patty/The Mechanics | 10/30- Lisa and team doing further research John O’Neal confirmed that while there was no activity last week, the team’s new Sprint begins on September 11, and Alpha Search will be prioritized for Planning Guide development. • Planning cards have been created for all three applications, and work is expected to begin with Alpha Search first. 9/19/2025 - Will create the Planning Guide, but no lobor tied to it. Will shut off with PCIO | N/A | N/A | N/A | 52 | 0 | 23 | 0 | 100%
Application #12 | 1214 | Error Message | Maintains a VSAM based common message file for the Service Avantage policy systems. The policy system requests a type of message and gets back a specific error correctly worded. | Personal Lines PCIO Commercial Lines | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Patty West | In-house | Both | Application | Support | Yes | Not Started | 2026-11-06 | Non-usage | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs | Very Low | Low | Yes - VSAM | N/A | N/A | Active, Isolated? | >20 Years | 3-6 Months | No | No | Low | Single | No | No | No | NA | 0 | NA | NA | 0 | 0 | 912 Mainframe Package Control | Specified in AH and AK | Zero | less than 10GB | Error Messages | Personal Lines, PCIO Commercial Lines | No | N/A | Daily | N/A | N/A | N/A | N/A | Source code is stored in Changeman. Documentation is stored in Sharepoint. | 30 days - App Specific | NA | 1 - 10 Users | 1 - 10 Users | N/A | No | Outdated Documentation | Has operational & business knowledge | Dedicated | 2 | Shared | NA | NA | NA | NA | No | No | Combined | Error Message | Patty/The Mechanics | 11/092025 - LSB - reviewing Decom for on-line and need final review of 10/30- Lisa and Team doing more research on it | N/A | N/A | N/A | 52 | 0 | 23 | 0 | 100%
Application #13 | 1220 | Policy Reload | Central point for customers to request a policy to be reloaded from back up files onto online policy systems. |  | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Toni Crowder, Crystal McVey | In-house | Both | Application | Support | Yes | Not Started | 2026-12-31 |  | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs | High | Medium | Yes - VSAM | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | No | No | TBD | TBD | TBD | TBD | TBD | TBD | 912 Mainframe Package Control | PCIO, SA | TBD | less than 10GB | Used to notify policy admin systems to reload a policy from backup tapes | TBD |  | Transfer to Flex |  | TBD | Archive | TBD | TBD | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA |  |  |  | No |  |  |  |  | Shared | NA | NA | NA |  | Yes | Yes |  | Policy Reload |  | 11/14/2025 - used by Flex (go forward app) to retrieve purged billing accounts (look to move into Flex) 11/13/25 - AP - Moved back to Decomm & Discard. Added back to WBS? Needs additional dev before discard. 11/09/2025 - LSB - will evaluate for other options for data loads in Flex. Not a big rock. **PCIO & P&C - uses this. Needed for litigation and need capability to print. 10/30- Lisa and Team do more research Policy Reload – Decommission Planning Update Progress Summary • Policy Reload has been identified as part of the early decommissioning track, currently targeted for March 31, 2026. • John O’Neal confirmed ownership of the application and acknowledged it is included in the decommission planning sheet. • As of the latest update, no active work has started on Policy Reload, but it is expected to be addressed in upcoming planning cycles. • The application will be considered alongside other early decommission candidates such as Alpha Search, Policy Expiration, and Microfilm Indexing, with prioritization based on team capacity and dependency analysis. Next Steps • John to initiate Planning Guide development for Policy Reload in alignment with the early decommission timeline. • Evaluate system dependencies and business impact during planning to confirm feasibility of the March 2026 target. • Coordinate with relevant stakeholders to validate assumptions and identify any retention or integration requirements. | N/A | N/A |  | 37 | 15 | 13 | 10 | 66.67%
Application #14 | 1418 | Policy Expirations | Process expiring policies. EXP on a monthly basis(end of month processing(EOM)) selects policies that are 105 days or less from expiring and generates reports such as NON-RENEWLs list, EXPIRATION list, etc. EXP also creates a monthly file of expiring policies that gets processed daily and any policy that is 73 days or less from expiring is written to EFILE and EFILE is sent to Columbus for further processing. |  | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Toni Crowder | In-house | Back end | Application | Discard | No | Not Started | 2026-11-06 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs,DB2 | Medium | Medium | Yes - VSAM | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | No | Yes | Low | Part of Group | Yes | No | No | TBD | TBD | TBD | TBD | TBD | TBD | 912 Mainframe Package Control | PCIO, eFile | TBD | less than 10GB | Policies coming up for renewal 11/09/2025 - will review opportunity to decommission earlier, but need time to review. Not a big rock | TBD |  | N/A |  | TBD | Discard | TBD | TBD | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA |  |  |  | No |  |  |  |  | Shared | NA | NA | NA |  | Yes | Yes |  | Policy Expirations |  | 10/30- Lisa and team going to research-Is Bonds still tied to this? Should this come off Decom list? Policy Expiration – Decommission Planning Update Policy Expiration is a legacy application tied to the PCIO platform. While no activity was reported as of mid-September, the application is part of the planning card set and is expected to follow the PCIO decommissioning timeline. Recent discussions confirm that the application is still in use and cannot be decommissioned until PCIO-related renewals are complete. Progress Summary Lisa Schillaci-Beane and John O’Neal confirmed the application is still active and required. Decommissioning cannot proceed until PCIO renewals are complete. Next Steps Confirm PCIO Shutdown Timeline Validate renewal completion dates and final shutdown schedule. Ensure Policy Expiration decommissioning aligns with PCIO dependencies. Update Planning Guide Reflect dependency on PCIO and revised decommissioning timeline. Include milestone tracking for renewals and shutdown readiness. | N/A | Decom and Discard | Decom and Discard | 37 | 15 | 14 | 9 | 68%
Application #15 | 1660 | Commercial Umbrella | Online calculator for Commercial Umbrella policies. This application is being used by Commercial Underwriters in PCIO Exclusive and Independent. | Commercial Umbrella | PCIO | Esposito, Colleen | Angie pike | Bill Mardis | In-house | Both | Internal Web App | Policy | Yes | In Progress - Planning | 2026-05-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform. | Java, SQL | Low | Very Low | SQL Server | CL Policy Center | 2026-05-01 | Isolated? | >20 Years | 4 Months | No | No | Low | Single | No | NA | NA | NA | NA | NA | NA | NA | NA | N/A | NA | No | 10-30GB | Cloud SQL Server database COMUDB has 30 tables that are a combination of Umbrella quote data entered in the tool along with tables that contain app rules/class codes/rates 1/14-Preliminary discussion started,its calculator | No | No | MAX 5 years for quotes, need to determine |  | No | To be decided | App Specific | App Specific | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA | 5 | NA | in Jan they were still using it…. | No | Well Documented | Has operational & business knowledge | House Band development line | 4 | Shared | 3 | 1 | to be confirmed | NA | NA | NA | TBD | Commercial Umbrella | Bill Mardis, Chaos Monkeys | 1/20-Planning guide started. Bill reached out to data warehouse. Sounds like they do have the data in data warehouse | Hybrid (data Lakehouse + Gacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 51 | 1 | 22 | 1 | 97.33% |  | Signed off by Prasad on 02-18-2026
Application #16 | 2918 | CCRF Agent Center | Allows agents to submit Commercial Change Requests via the Agent Center. | All LOBs | PCIO | Esposito, Colleen | Angie Pike | Bill Mardis | In-house | Both | Web Application | Policy | Yes | In Progress - Planning | 2026-06-30 | The app is no longer needed once all PCIO accounts have expired. | AWS/Cloud,SQL Server,Java,Github | Low | Low | SQL Server | CL Policy Center |  | Active | >20 Years | 6 Months | No | No | Low | Part of Group | No | No | No | NA | NA | NA | eFile | 1 | SFTP (docs put in a location, then eFile has process to pull in) | Built together with COI (3065), CRN (1613) as CommServicing. These other 2 apps are go-forward apps. | Built together with COI (3065), CRN (1613) as CommServicing. These other 2 apps are go-forward apps. | NA | 10-30GB | Cloud SQL Server Database PH4DD001 - 29 tables starting with PH4* that contain amendment details keyed into the app. When user submits an amendment, the details are put in a PDF and sent to processing via eFile. There is no direct connection between the data entered/stored in CCRF with the PCIO mainframe policy systems. All data is manually keyed in CCRF and then manually keyed in PCIO mainframe. | CCRF Agent Center | No | N/A | Daily | No | Discard | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA | NA | Less than 10 past 30 days | After all PCIO accounts have expired, they'll stop using this for amendments and use go-forward CL PolicyCenter platform for the migrated accounts | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 4 | Shared | 3 | 2 | 3 | NA | NA | No | TBD | CCRF Agent Center | Bill Mardis | 1/20- Bill is going to do more research | N/A | Decom and Discard | Decom and Discard | 51 | 1 | 22 | 1 | 97.33% |  | Signed off by Prasad on 02-18-2026
Application #17 | 4245 | Commercial Mainframe COI | Commercial Mainframe COI processing/printing. | All LOBs except FARM | PCIO | Esposito, Colleen | Cece Moore? | Prasad Penchala | In-house | Back end | Legacy Application | Support | Yes - Java application to request COI | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | COBOL, CICS, zOS,MQ | High | Low | VSAM | CL Policy Center | N/A | Active, Not isolated | >20 Years | 3-6 Months | No | Yes | High | Part of Group | Yes | No | No | Certificate of Insurance Web application | 1 | MQ | Certificate of Insurance Web application | 1 | MQ | 912 Mainframe Package Control | Specified in AH and AK | None | less than 10GB | Cert of Insurance from Agent Center, still utilized. Is this used for PC COI? Should not be on the decom list, need to verify it's the same tool used for PC because it needs to remain. Request comes from Agent Center COI | All PCIO Apps | No | N/A | Daily | N/A | N/A | N/A | N/A | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Well Documented | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | None | Yes | Yes | Combined | Commercial Mainframe COI | Bill Mardis | Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 52 | 0 | 23 | 0 | 100% |  | Signed off by Prasad on 02-18-2026
Application #18 | 4260 | Commercial Renewal Reporting DB | PCIO - Stores the U/W renewal rules and statistics to report against it. The database we own is for business driven Brio Reports measuring policies that Renew without being touched by underwriters. It also measures renewal errors that are triggering Underwriter activities to determine if the renewal rules need to be adjusted to meet the business needs. There are also reports that measure regional office renewal volume and premium. |  | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Michael Adamson | In-house | Back end | Component | Policy | No | Not Started | 2026-11-06 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs,DB2 | Medium | Medium | DB2 | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | No | Yes | Low | Part of Group | Yes | No | No | TBD | TBD | TBD | TBD | TBD | TBD | 912 Mainframe Package Control | TBD | TBD | less than 10GB | Renewal data from PCIO Automatic Renewal process | TBD |  | N/A |  | TBD | N/A | TBD | TBD | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA |  |  |  | No |  |  |  |  | Shared | NA | NA | NA |  | Yes | Yes |  | Commercial Renewal Reporting DB |  | 10/30- Lisa and team will do more research, this may come off DECOM list Commercial Renewal Reporting DB – Progress The application is tied to renewal-related data, and its relationship to Commercial Underwriting rules is being clarified. Initial target for decommissioning is Q1 2026, pending validation of dependencies and business impact. Next Steps: Planning Guide Development: Begin Planning Guide work to clarify system dependencies and validate assumptions. Business Impact Assessment: Evaluate feasibility of early decommissioning based on business needs and system interdependencies. Documentation Alignment: Ensure Planning Guide reflects the distinction between Commercial Underwriting rules and renewal info database. Stakeholder Engagement: Engage business and compliance teams to validate retention requirements and confirm decommissioning readiness. | N/A | Decom and Discard | Decom and Discard | 37 | 15 | 13 | 10 | 66.67%
Application #19 | 4261 | Commercial Underwriting DB | Marketing/Pricing/Underwriting Database - Monitors IA Agents productivity and IA Agents Quote to Issue Premium Variations. Owned by Underwriting. Web front-end that is owned by CIQ. Also produces and stores reports for Marketing, Pricing and Underwriting. Includes several BRIO queries. Underwriting owns BRIO queries |  | PCIO | Schillaci-Beane, Lisa | Michael Martin / Angie Pike | Michael Adamson | In-house | Back end | Component | UW | No | Not Started | 2026-11-06 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform? | CICs, Cobol, Batch, JCL, Changeman, UAC, VSAM, GDGs,DB2 | Medium | High | DB2 | CL Policy Center | Same as PCIO | Active, Not isolated? | >20 Years | 3-6 Months | No | No | Low | Part of Group | Yes | No | No | TBD | TBD | TBD | TBD | TBD | TBD | 912 Mainframe Package Control | TBD | TBD | 10-30GB | 0 | TBD |  | N/A |  | TBD | Discard | TBD | TBD | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | NA |  |  |  | No |  |  |  |  | Shared | NA | NA | NA |  | Yes | Yes |  | Commercial Underwriting DB |  | 10/30- Lisa and team doing more research Commercial Underwriting DB – Progress Summary The application stores renewal rules, which differ from the renewal info database used elsewhere. This distinction will be clarified during Planning Guide development. Initial decommissioning target is Q1 2026, pending validation of dependencies and business impact. Next Steps: Planning Guide Development: Begin Planning Guide work to clarify system dependencies and validate assumptions. Business Impact Assessment: Evaluate feasibility of early decommissioning based on business needs and system interdependencies. Retention Review: Confirm whether any data retention requirements apply to renewal rules stored in the database. Stakeholder Engagement: Use Planning Guide to engage stakeholders and validate readiness for decommissioning. | N/A | N/A | N/A | 37 | 15 | 13 | 10 | 66.67%
Application #20 | 5281 | HV-Accounts Receivable | Accounts Receivable Also known as Agent Balance and Reconciliation Recieves feeds from Billing System and PNC lockbox | CL,PL | HV | Esposito, Colleen | Day Flanagan, Ricki | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | In-house | Both | Application | Financial | Yes | In Progress - Planning | 2027-04-30 | No longer needed | MF | Medium | 1 | VSAM (DB2 ?) | None | NA | Active, Not isolated | >20 Years | 12-18 Months | No | No | High | Part of Group | Yes | Yes | No | HV-Legacy Billing Systems, HV-PNC Bank Feed(external app?) | 2 apps | SFTP, Files | Frontier (General ledger of NW) | 1 app | SFTP | 5296 HV Legacy Billing Systems | 5296 HV-Legacy Billing Systems, HV-Legacy Billing Systems, HV-PNC Bank Feed(external app?) | 7 (4 Daily, 3 Weekly, 1 Monthly) | less than 10GB | DB2 tables - contain accounts receivable data. prod.ARCV_STMNT_ELMNT prod.ARCV_ACCT_STMNT | 5281 HV-Accounts Receivable | Yes | FMA170 – Accounting Records -7 years | Daily | TBD | Archive | RRC - 3 to 5 hrs SLA for retrieval | RRC - 3 to 5 hrs SLA for retrieval | Changeman - (applicable for gitHub - 1 year retention for NW source code) NOTE: changeman will get migrated to github - to confirm) | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA |  | HV Billing | Colleen Esposito | 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | Glacier | AWS Glacier | RRC | 51 | 1 | 23 | 0 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #21 | 5282 | HV-Agency Bill Account Current | The Agency billing system supports monthly billing and collection from each agent on a net premium basis (premium less commission). The agency bill premiums are for accounts of $50,000 or more. The system provides a history of collection activity and provides detailed Information on all outstanding unpaid premium by agent. HV Legacy Billing Systems is a term used to describe both the agency and direct billing systems. In the agency billing setup, the insurer sends a monthly bill to the agent. The agent collects the premium from the customer and then forwards the payment to the insurer. | CL,PL | HV | Esposito, Colleen | Ricki Day | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | In-house | Both | Application | Financial | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | Medium | 1 | N/A | Flex Bill | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | High | Part of Group | Yes | No | No | SurePay | 1 | FTP | NA | 0 | NA | 5296 HV Legacy Billing Systems | 5281 HV- Accounts Receivable | 7 ( which includes Daily, Weekly, Monthly) | less than 10GB | N/A | 5296 HV-Legacy Billing | Yes | FMA170 – Accounting Records -7 years | Daily | TBD | N/A | TBD | tbd | Changeman | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA |  | HV Billing | Colleen Esposito | 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 49 | 3 | 22 | 1 | 94.67% |  | Frank provided signed off on 02-18-2026
Application #22 | 5283 | HV-Agency Systems | This application is a legacy mainframe based platform consists of 4 key sub systems. which are Agency Master, Interface/Downloads, Performace, Expiration. | CL,PL | HV | Esposito, Colleen | Christina Ledbedder | Venkata Ranga Mahesh, Padarthi | In-house | Both | Application | Producer/Agency | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | Medium | 1 | VSAM | AMF | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Part of Group | Yes | No | No | HV-Informatica, HV-Claims, HV-Legacy Billing Systems | 3 | File | NA | NA | NA | 5479 HV AQS | all HV systems | 10 ( Approx) | less than 10GB | Harleysville legacy system including Agency Master, Agency Performance, and Agency Download batch processing and CICS. VSAM files Agency Master file: CORP00PV.AGCY.NEW.ADSK..C Master file contains all agency info including appointments Agency Performance: CORP00PV.AGCY.PERFORM.C HV agency data is fed over to AMF and DPIM | 5283 HV Agency Systems | No | INS1020 – Agency Administration - Active + 7 years |  | No | Archive | NA | NA | Changeman | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA |  |  | Frank Unger | 10/30- Joy and Colleen are working on the requirements 11/4- Frank to provide some samples to Joy 11/10 - INS1020 – Agency Administration - Active + 7 years Set up meeting with Kristi on aligning on next steps and status. | Glacier | AWS Glacier | RRC | 51 | 1 | 21 | 2 | 96% |  | Frank provided signed off on 02-18-2026
Application #23 | 5285 | HV-CCMS & Score | Used for assignment of policy numbers for manual policies and to link them in the Insured Account Database. In addition, if any of these policies are brought into automation at renewal, CCMS would be used to set up the renewal conversion. | CL | HV | Esposito, Colleen | Angie Pike; Michael Martin | Venkata Ranga Mahesh, Padarthi | In-house | Both | Application | Support | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | Very Low | 1 | VSAM | CL Policy Center | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | Low | Part of Group | No | No | No | HV-STAT | 0 | VSAM | Underwriting team | 1 | VSAM | 5303 HV Stat | HV-Midstream Stat | 10 ( Approx) | less than 10GB | Vsam - Policy number assignment for manual policies COMM00PV.CCMS.MASTER.C | 5285-HV-CCMS & Score | No | NA | Daily | No | Discard | NA | NA | Changeman | 30 days - App Specific | CLS release management Team | 1 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA |  | MF Doc |  | 10/30- Colleen to review and see accelerated timelines Set up meeting with Kristi on aligning on next steps and status. | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #24 | 5290 | HV-Direct Bill Commission | The Direct Bill system receives premium transactional data directly from the Commercial lines system and from the manual policy entry system from HUB processing on a daily basis. AQS is the front-end policy system for HV commercial lines which will be the source for billing system, Billing system maintains accounting entries for all the premium received in Account receivable and for all the refunds payments in account payable. Billing System provides input to the finance system to maintain the general ledger entries . | CL,PL | HV | Esposito, Colleen | Ricki Day | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | In-house | Both | Application | Financial | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | Medium | 1 | VSAM | Flex Bill | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | High | Part of Group | Yes | No | No | HV-Agency Billing system, HV-STAT | 0 | FTP, Flat Files | NW General Ledger | 1 | FTP, Flat Files | 5303 HV Stat | HV-Stat | 10 ( Approx) | less than 10GB | agent commissions, pull data from stat and accounting records and feed to SAP, data returned and do check print, processing, commissions payments, check statements FMA170 – Accounting Records |  | Yes | FMA170 – Accounting Records -7 years | Daily | No | Archive | TBD | TBD | Changeman | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA |  | HV Billing | Colleen Esposito | 11/6: 7 year retention requirement - FMA170 – Accounting Records 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | Glacier | AWS Glacier | RRC | 49 | 3 | 22 | 1 | 94.67% |  | Frank provided signed off on 02-18-2026
Application #25 | 5296 | HV-Legacy Billing Systems | The Agency bill system supports the monthly billing and collection from each agent on a net premium basis (premium less commission). The agency bill premiums are for accounts of $50,000 or more. The system provides a history of collection activity and provides detailed Information on all outstanding unpaid premium by agent.The Direct Bill system supports the billing and collection directly from the customer, of P&C insurance premium written by Harleysville Insurance operations. | CL,PL | HV | Esposito, Colleen | Boyer, Tricia <BOYERT3@nationwide.com>; Mc Clain, Tracy L <tracy.mcclain@nationwide.com>; Mixdorf, Matthew C <MIXDORM@nationwide.com>Kristen Troxel | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | In-house | Both | Application | Financial | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | High | 2 | DB2 on zOS, GDG, VSAM, Tape | Flex Bill | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | Yes | High | Part of Group | No | Yes | Yes | Flex bill, HV-Informatica, HV-Clarify | 3 | FTP, Flat Files | HV-Access Collection, HV-Bill Matrix, HV-PNC Bank Feed, NW General Ledger | 12 | FTP, Flat Files | 5296 HV Legacy Billing Systems | Policy Systems Agent Portal | 7 ( which includes Daily, Weekly, Monthly) | 10-30GB | Accounts/Policies/Cash transactions/Audit trail, VSAM BILL00PV.DRCT.B1.MASTER.C BILL00PV.DRCT.B2.MASTER.C BILL00PV.DRCT.B3.MASTER.C BILL00PV.DRCT.B4.MASTER.C BILL00PV.DRCT.ACCT.AUDIT.TRAIL.C BILL00PV.DRCT.AUDIT.TRAIL.C FMA170 – Accounting Records Images stored in IR and will go to RRC with ImageRight decom | 5296 HV-Legacy Billing | Yes | FMA170 – Accounting Records -7 years | Monthly | These files are purged differently from 1.5 to 5 years.If a policy has a balance it does not get purged until the balance is satisfied, then it is purged. | Archive | TBD | TBD | Changeman | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | BillMatrix, Access Collections LLC, PNC Bank Feed, Clarify CRM, VOIP Services, SurePay | NA | NA | 7822.5 | HV Billing | Colleen Esposito | 11/6: 7 year retention requirement - FMA170 – Accounting Records 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | Glacier | AWS Glacier | RRC | 50 | 2 | 23 | 0 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #26 | 5306 | HV-Personal Lines Legacy | Policy adminstration for Personal lines Homeowners, Automobile, Blanket Excess, Inland Marine, and Shipmate on the mainframe | PL | HV | Esposito, Colleen | Joanne Cartwright | Dennis Schell | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | Low | 2 | VSAM and Non‑VSAM files | PL Policy Center | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Single | Yes | No | No | HV-Informatica, HV-Claims, HV-Legacy Billing Systems | 3 | Files | HV-Informatica, HV-STAT, HV-Documerge | 3 | Files | Mainframe Retirement Holistically | TBD | 0 | 10-30GB | Personal lines policy information for Harleysville including Auto, Home, Dwelling and Unbrella lines of businesss on the mainframe. There is a database for Auto, Home, and Umbrella PLAU00PV.AUTO.POL.CTRL.PROD.MSTR.C PLAU00PV.AUTO.POL.DTL1.MSTR.C PLAU00PV.AUTO.POL.DTL2.MSTR.C PLAU00PV.AUTO.POL.DTL3.MSTR.C PLAU00PV.AUTO.POL.DTL4.MSTR.C PLPP00PV.HOME.CONTROL.MSTR.C PLPP00PV.HOME.POL.DTL.MSTR.C PLPP00PV.HOME.HO61.MSTR.C PLPP00PV.DWEL.POL.DTL.MSTR.C PLPP00PV.SHIP.POL.DTL.MSTR.C PLPP00PV.BLEX.POL.DTL.MSTR.C | HV-Personal Lines Legacy | Yes | POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Daily | TBD | Archive | TBD | TBD | Changeman | 30 days - App Specific | CLS release management Team | 1 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA | NA | MF Doc |  | 11/6: VSAM files are needed for HV Claims 10/30- Colleen do more research on it, may be needed for claims Set up meeting with Kristi on aligning on next steps and status. | Data Lakehouse | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 49 | 3 | 21 | 2 | 93.33% |  | Frank provided signed off on 02-18-2026
Application #27 | 5307 | HV-Commercial Lines Legacy | App will be decom with MF. | CL | HV | Esposito, Colleen | Angie Pike; Michael Martin | Dennis Schell | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF | Medium | 2 | DB2, VSAM | CL Policy Center | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | High | Single | Yes | No | No | HV-Informatica, HV-Claims, HV-Legacy Billing Systems | 3 | Files | HV-Informatica, HV-STAT, HV-Documerge | 3 | Files | Mainframe Retirement Holistically | HV-Commerial Lines Legacy | 0 | 30-70GB | 5/17/22 from Terry; There is VSAM data associated with this application which should still be in existence for inquiry purposes. Colleen and I discussed this app last night and this data should be made available in Alcides as it may be required for future Claims reporting. There should be inquiry functionality supporting this application with no transactional capability. Cindy Budka is knowledgeable on this app and would be able to speak to file layouts/content. COMM00PV.CAUT.CA.CONTROL.MASTER.C COMM00PV.CAUT.CA.DETAIL.MASTER.C COMM00PV.CAUT.PU.DETAIL.MASTER.C COMM00PV.WCOM.WC.CONTROL.MASTER.C COMM00PV.WCOM.WC.DETAIL.MASTER.C COMM00PV.WCOM.PU.DETAIL.MASTER.C COMM00PV.BEXC.BE.CONTROL.MASTER.C COMM00PV.BEXC.BE.DETAIL.MASTER.C COMM00PV.BEXC.PU.DETAIL.MASTER.C COMM00PV.MONO.CP.CONTROL.MASTER.C COMM00PV.MONO.CP.DETAIL.MASTER.C COMM00PV.MONO.GL.CONTROL.MASTER.C COMM00PV.MONO.GL.DETAIL.MASTER.C COMM00PV.MONO.BO.CB.CONTROL.MASTER.C COMM00PV.MONO.BO.CB.DETAIL.MASTER.C COMM00PV.MONO.PU.DETAIL.MASTER.C COMM00PV.MULT.IM.CONTROL.MASTER.C COMM00PV.MULT.IM.DETAIL.MASTER.C COMM00PV.MULT.MP.CONTROL.MASTER.C COMM00PV.MULT.MP.DETAIL.MASTER.C COMM00PV.MULT.CR.CONTROL.MASTER.C COMM00PV.MULT.CR.DETAIL.MASTER.C COMM00PV.MULT.PU.DETAIL.MASTER.C | HV-Commercial Lines Legacy | Yes | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Daily | TBD | Archive | TBD | TBD | Changeman | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | NA | NA | NA | NA | MF Doc |  | 11/6: VSAM files are needed for HV Claims 10/30- Colleen do more research on it, may be needed for claims Set up meeting with Kristi on aligning on next steps and status. | Hybrid (data Lakehouse + Gacier) | P&C Data Lakehouse + AWS Glacier | Inquiry UI, API, Data Extract Process + RRC | 49 | 3 | 22 | 1 | 94.67% |  | Frank provided signed off on 02-18-2026
Application #28 | 5308 | HV-Commercial Lines DMV | Used for reporting vehicle information to various state DMV agencies | CL | HV | Esposito, Colleen | Linda Brockney | Joanne Nuzzi | In-house | Back end | Utility | Support | No | In Progress - Planning | 2026-07-30 | Modernization | MF | Low | 1 | Flat files | CL Policy Center | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Part of Group | Yes | Yes | Yes | HV-Commercial Lines Legacy, HV-AQS, HV-Informatica | 3 | Files | Verisk (vendor for DMV reporting) | 1 | FTP | 5479 HV AQS | HV-AQS, HV-Commercial Lines Legacy | 5( Approx) | less than 10GB | Feeds to/from Verisk - CL | 5307 - HVCommercial Lines | No | N/A | Daily | No | Discard | TBD | TBD | Changeman | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | Verisk | NA | NA |  | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | N/A | Decom and Discard | Decom and Discard | 50 | 2 | 21 | 2 | 94.67% |  | Frank provided signed off on 02-18-2026
Application #29 | 5309 | HV-Midstream Stat Creation | This application refers to Creation of Accouting/Stat records related to insurance ploicy premium for reporting and downstream processing. | CL | HV | Esposito, Colleen | Angie Pike; Michael Martin | Venkata Ranga Mahesh, Padarthi | In-house | Back end | Application | Support | No | Not Started | 2027-04-30 | Modernization | MF, Win2019, SQL2019, Informatica, SFTP | Medium | 1 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Part of Group | Yes | No | No | HV-AQS | 1 | DB calls | HV-STAT | 1 | File | 5479 HV AQS | HV-AQS, HV-STAT | 0 | 30-70GB | AQS / DCT are the source | HV-AQS | No | N/A | Daily | No | N/A | NA | NA | Changeman, Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | 1 | 1 | 1 | NA | NA | NA |  | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #30 | 5385 | HV-AccessWeb - UWRulesEngineWeb App | User interface for accepting and responding to binding authority questions an rules. | CL | HV | Esposito, Colleen | George Schirripa | Tony Brnic | In-house | Back end | IT Service | UW | No | Not Started | 2026-12-31 | Modernization | WIN2019, IIS,SQL Server,C# .Net,Github, Jenkins, UCD | Medium | 1 | SQL Server | NA | NA | Active, Not isolated | >20 Years | 3-6 Months | No | No | Medium | Part of Group | No | No | No | HV-AQS | 1 | I-frame | NA | NA | NA | 5479 HV AQS | HV-AQS | 0 | less than 10GB | Uses xml Binding Authority blobs for Questions and Answers. | HV-URE, HV-Quote, IADB | No | UND120 – Commercial Lines, Property, Casualty -Indefinite | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 5 | 1 | 20 | Blaze,Github, Jenkins, UCD | NA | NA |  | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business 10/30- Colleen do more research on it Set up meeting with Kristi on aligning on next steps and status. | Glacier | AWS Glacier | RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #31 | 5390 | HV-Audit Upload Manager | Audits discrepancies in policy premium caused by quote and billing date issues. | CL | HV | Esposito, Colleen | Krystal Smith | Dan Croll | In-house | Both | Application | Support | Yes | Not Started | 2026-10-15 | Modernization | WIN2019, SQL2019 | Medium | 1 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 6-12 Months | Yes | No | Medium | Part of Group | No | No | No | ACE, AQS | 2 | DB calls | N/A | 0 | N/A | 5479 HV AQS | ACE Audit Upload, HV-AQS, Batch Cycle | 0 | less than 10GB | Database is the audit control file | AQS | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Shared | 1 | Shared | 7 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV-ACE - Premium Audit | Mike Kelly |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #32 | 5408 | HV-Renewal Automation | Renewal automation is a batch process (.net/sq.) that runs in the background on a nightly basis. The job gathers data from both legacy and AQS and flags 90 day expiration candidates for renewal. Some can issue automatically, others are flagged for manual intervention. Web Methods is the intermediary link between all the function. | CL | HV | Esposito, Colleen | Linda Brockney Amy Underwood | Dennis Schell | In-house | Both | Component | Support | N/A | In Progress - Planning | 2026-06-30 | Modernization | Win2019, SQL2019 ( asp.net, c#.net, SQL, Webservices, IIS ) | Low | 1 | Yes(SQL Server) | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | NA | No | No | NA | NA | NA | HV-AQS | 1 | DB calls | 5479 HV AQS | HV-AQS, Batch Cycle | 3 daily | 70-100GB | Renewal control db | AQS | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 1 | 0 | Already using go forward app | Yes | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 7 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV-Renewal Automation | Dan Croll | 1/20- Frank is doing more research | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #33 | 5413 | HV-Underwriting Rules Engine (URE) | The tool used to assign rules around potential customer's provided information. This rules engine will determine if the policy can be bindable, determining account-level renewal authority, determing applicable product, system and line of business.. | CL | HV | Esposito, Colleen | George Schirripa | Tony Brnic | In-house | Back end | Application | UW | Yes | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019,IIS,C# .Net,Github, Jenkins, UCD | Low | 1 | SQL Server | NA | NA | Active, Not isolated | >20 Years | 3-6 Months | No | No | Medium | Part of Group | No | No | No | HV-Webmethods, HV-Rules Maintenance Application (RMA) | 2 | API, DB calls | NA | NA | NA | 5479 HV AQS | HV-AQS, HV-Agent Portal | 0 | more than 100GB | Stores Protocol data and uses xml blob saved for prior referrals generated.Quote and IADB db's used to populate Blaze and .net objects. | HV-URE, HV-Quote, IADB | No | UND120 – Commercial Lines, Property, Casualty -Indefinite | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 5 | 1 | 20 | Blaze,Github, Jenkins, UCD | NA | NA |  | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business 10/30- Colleen to do more research | Glacier | AWS Glacier | RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #34 | 5415 | HV-ACE - Premium Audit | Premium audit. Commercial policy so much for the year. Premium is estimated. Your premium should be or less or more. Feeds from policy systems | CL | HV | Esposito, Colleen | Smith, Krystal A Shewey, Dora A | Mike Kelly | 3rd party | Back end | Third Party Application | Policy | Yes | In Progress - Planning | 2026-10-15 | Modernization | Win2019, SQL2019, IIS | High | 1 | MS-SQL | AuSum | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-Mainframe, Claim Center | 2 | ftp | HV-Billing/HV-AQS | 2 | flat file | 5479 HV AQS | HV-AQS, HV-AuditWin Plus - Premium Audit Folder in ImageRight | 0 | more than 100GB | Audit Data | HV AQS | No | UND120 – Commercial Lines, Property, Casualty - indefinite Und 100 - | Daily | No | Archive | RRC - 3 to 5 hrs SLA for retrieval | RRC - 3 to 5 hrs SLA for retrieval | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 20 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 2 | Dedicated | 4 | 2 | 0 | N/A | N/A | Yearly Support contract - 9/30 exp | TBD | HV-ACE - Premium Audit | Mike Kelly | 11/6: CL Premium audits falls under UND120 – Commercial Lines, Property, Casualty - indefinite 10/30- Colleen to do further research on this | Glacier | AWS Glacier | RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #35 | 5426 | HV-Clarify | CRM Tool for Contact Center and Service Center | CL,PL | HV | Esposito, Colleen | R. Hunter T. Webber | Mike Kelly | Clarify is a 3rd party application used for CRM | Back end | Utility | Support | No | In Progress - Planning | 2027-04-30 | Modernization | Win2016, SQL Server 2016, Proprietary IIS, C# .NET VSAM, Flat Files, COBOL | Medium | 1 | Yes - DB2, MS SQL Server | Genisys | already ready | Active, Not isolated | 15-20 years | 3-6 Months | No | No | Low | Part of Group | Yes | No | No | HV-Mainframe | 4 |  | HV-Voip Services | 3 | DB calls | 5296 Legacy Billing System | AQS, DCT, Billing, | 0 | more than 100GB | CRM data - data is sent to HV Direct Bill Mainframe - URA (User Remarks Area) - we stopped send sending this when Zoom replaced Clarify. Clarify still collects this data but no longer sends it to ZOOM | HV - Billing | No | N/A | Daily | No | Discard | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 0 | 0 | Already using go forward app | No | Minimal Documentation | Has only basic information | Dedicated | 1 | Shared | 1 | 2 | 47 | AmDocs/DoveTail GitHub | N/A | N/A | TBD | HV Billing | Mike Kelly | 10/30- Colleen to update retention column details Set up meeting with Kristi on aligning on next steps and status. | N/A | Decom and Discard | Decom and Discard | 51 | 1 | 22 | 1 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #36 | 5427 | HV-COGNOS | Query report and analysis capabilities for all type of data. A component of COGNOS is Analyst Studio, which also needs to be tested whenever any type of upgrade occurs. | CL | HV | Esposito, Colleen | Michael Martin Lori McCoy | alex gamarnik, dan croll | 3rd party | Both | Application | 3rd Party IBM Cognos | Yes | In Progress - Planning | 2026-09-01 | Modernization | Win2019, SQL2019 | Medium | 1 | Yes | SSRS | already ready | Active, Not isolated | 15-20 years | 3-6 Months | No | No | Medium | Single | Yes - feeds to Cognos | No | No | HV-Claims, HV-AQS | 10 | DB calls | NA | NA | NA | 5297 HV Legacy Claims | HV - Legacy Claims, Policy ODS | 14 some scheduled, some on demand | 30-70GB | Policy Holder, Conformed Demisions and Claims master BI Reporting, Audit Store and Content Store | HV-Legacy Claims (5297) | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 20 | 0 | 3-6 months | Yes | Well Documented | Has operational & business knowledge | Shared | 2 | Dedicated app, Shared db | 2 | 2 | 20 | IBM Cognos | Expires 12/2026 | NA | Monthly SQL = 6 @ $120.44 = $722.64 DPS (Backup) = 351 @ $.24 = $84.24 Web Server = 4 @ $14.51 = $58.04 Total Infras. = $864.92 LICENSE COSTS = $1,436.25 Labor = $1,500.00 TOTAL = $3,801.17 ANNUAL TOTAL = $45,804.00 | Cognos | Alex Gamarnik Dan Croll | 12/09/25 - 60% Complete on reWrite Rewrite & Decommission Planning Update Rewrite Progress: Approximately 60% complete. Two reports have been fully rewritten. A consolidated policyholder base report has been created, containing all required data. This consolidated report enables faster extraction for sub-reports without returning to Cognos, accelerating progress. Platform Decommissioning: Tracking separately; rewrite completion is a prerequisite for decommissioning. Colleen clarified that while overall rewrite progress is 60%. Key Achievements Successfully extracted all necessary data into a single consolidated report. Reduced dependency on Cognos for future report generation, enabling quicker migration. Risks Remaining rewrite tasks must be completed before platform decommission can proceed. Any delays in sub-report extraction could impact overall timeline. Next Steps Complete remaining rewrite tasks and sub-report extractions. Validate consolidated report accuracy and confirm business sign-off. Begin planning for Cognos platform decommission once rewrite reaches 100%. Provide updated completion percentage and timeline in next leadership review. Current Status Rewrite: 60% overall progress; 50% on core rewrite component. Decommission: Pending rewrite completion; timeline to be finalized post-rewrite. | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 23 | 0 | 100% |  | Frank provided signed off on 02-18-2026
Application #37 | 5442 | HV-ImageRight | Imaging and workflow management system from Vertafore. This system is used to capture policy, underwriting and claims workflow and documentation. Images can be introduced into this system in various ways such as scanning, printing, and email. | CL, PL, Claims, Life, Financial Accounting | HV | Esposito, Colleen | Lindsey Moyer Amy Olstedd Linda Brockney Kim Wysong Billing ? | Mike Kelly | 3rd party | Both | Third Party Application | Print, Rules | Yes | In Progress - Planning | 2027-07-15 | Modernization | MF, VSAM, CICS | Very High | 1 | MS-SQL | AWD and Filenet | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | High | Single | Yes | No | No | HV-Documerge, HV-Documaker, HV-Mainframe, HV-Agent Portal, HV-AQS, HV-Informatica, Doc Solutions, Exchange | 135 | ftp,webmethods, file copy, email | HV-AgentPortal, HV-UW Workbench,HV-Policy Browser | 1 | HV-webMethods, IR Webservices | 5479 HV AQS, DCT, Billing, Claims, ACE Premium Audit | HV-AQS, HV-DCT, HV-Billing, HV-Claims, HV-ACE Premium Audit, HV-Life, HV-UW Workbench, HV-webMethods, | 0 | more than 100GB | Stores Output from DCT, AQS, Claims, Billing, Accounting Reports (retire after all HV apps retired or docs moved) 6/30/21 Also used as an input to ClaimCenter, see notes for more info | ImageRight | Yes | See rules for the differenct lines - PL, CL, Life, Claims, Financial | Daily | No | Discard | RRC - 3 to 5 hrs SLA for retrieval | RRC - 3 to 5 hrs SLA for retrieval | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 2588 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 2 | Dedicated | 16 | 4 | 0 | N/A | N/A | N/A | TBD | ImageRight Doc | Mike Kelly | 11/7 - Images will be archived with their corresponding applications. Tracking will be at the individual application level 10/30- Needed for claims but that can be solved by getting stuff outside from ImageRight Big Rocks | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #38 | 5444 | HV-Informatica | ETL Tool | CL, PL, Claims, Agency | HV | Esposito, Colleen | Jay Mills - Actuarial | Frank Unger, Korni, AnilReddy , Dennis Schell | 3rd party | Back end | Third Party Application | N/A | Yes - Admin Interface | In Progress - Planning | 2027-07-01 | Modernization | Win2019, SQL2019, Informatica, SFTP | High | 2 | SQL Server | NW Informatica instance | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | High | Part of Group | Yes | Yes | No | CL Policy Center, HV-AQS, HV-Predictive Modeling, HV-Legacy Claims, HV-Agency Licensing, HV-Agency Systems | 100 | DB calls, files, sftp | CL Policy Center, HV-AQS, HV-Claims, HV-Legacy Billing Systems, HV-Commercial Lines Legacy, HV-STAT, ADS, Salesforce, DPIM, AMF | 100 | SFTP, Files, DB calls | 5479 HV AQS, DCT, Billing, Claims, Stat. Actuarial | Processes all HV Data | 0 | less than 10GB | ETL software that stores repository data and meta data (no policy data is stored) | HV - Informatica | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 3 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Shared | 2 | Shared | 3 | 1 | 1 | Informatica | Handled by Enterprise Informatica Team | Handled by Enterprise Informatica Team |  | Informatica |  | 10/30- Need to rewrite informatica workflows into Enterprise Informatica Set up meeting with Kristi on aligning on next steps and status. | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #39 | 5454 | HV-Rules Maintenance Application (RMA) | Development platform to write business rules. These rules are then used by the URE application. | CL | HV | Esposito, Colleen | George Schirripa | Tony Brnic | In-house | Both | Desktop Application | UW | Yes | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019,C# .Net,IIS | Low | 1 | SQL Server | NA | NA | Active, Not isolated | >20 Years | 3-6 Months | No | No | Medium | Part of Group | No | No | No | NA | NA | NA | HV-Underwriting Rules Engine (URE) | 1 | DB calls | 5479 HV AQS | HV-URE | 0 | less than 10GB | Uses database rules repository to store rule updates, templates and rule's information | HV-URE | No | UND120 – Commercial Lines, Property, Casualty - indefinite | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 1 | 1 | 20 | Blaze,Github, Jenkins, UCD | NA | NA |  | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business | Glacier | AWS Glacier | RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #40 | 5463 | HV-UWWB - Underwriter WorkBench | This is a Workbench for task completion. documentation, and making underwriting decisions for Underwriters. Processing uses this workbench for task completion and documentation as well. | CL | HV | Esposito, Colleen | Cece Moore? | Mike Kelly, Joanne Nuzzi | In-house | Both | Application | UW | Yes | In Progress - Planning | 2026-07-30 | Modernization | Win2019,SQL Server ,IIS,C# .NET ,GitHub, Jenkins, UCD | Very High | 1 | SQL server | N/A | already ready | Active, Not isolated | 15-20 years | 3-6 Months | No | No | High | Part of Group | No | Yes | No | HV-Webmethods, HV-ImageRight, HV-CoreLogic Service,HV-Account Proposal,HV-Hazard Grade Matrix (HGM),HV-AIS,HV-MVR Services,HV-Billing Svc, Claim Center, HV-Cognos, HV-Underwriting Rules Engine (URE), SSRS Reports, | 12 | webMethods | HV-U279, HV-ImageRight | 2 | webMethods, file copy | 5479 HV AQS | HV-Cognos, HV-Underwriting Rules Engine (URE), SSRS Reports, HV-Core Integration Svcs, HV-Image Right, HV-AIS | 0 | less than 10GB | Underwriter_Workbench database is used as its own db by the application. SQL | 5463-HV-UWWB - Underwriter WorkBench | No | //Mentioned duration is in Days or Years? UND115 - Commercial Lines: ACT+10 UND120: Commercial Lines: IND ISY100 Application Documentation and Source Code *1 ISY110 Disaster Recovery Plans *3 ISY120 Back-up Tapes, Files and Data MAX30 Days ISY130 Systems Technical Administration MAX3 Years ISY140 Technical Support Requests 3 ISY150 Website Activity Logs 6M ISY160 Website Data Security Records 3 ISY170 Information Security Testing 5 LEG190 Contracts and Agreements / Software Licenses and Escrow Agreements *7 LEG200 Contracts and Agreements / Vendors *7 | Daily | No | N/A | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 700 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Shared | 2 | Shared | 5 | 4 | 47 | GitHub, Jenkins | N/a | N/A | 5000 Annual Run Support | HV-UWWB - Underwriter WorkBench | Joanne Nuzzi | 1/21 - Joanne still working on the plan guide | N/A | N/A | N/A | 52 | 0 | 23 | 0 | 100% |  | Frank provided signed off on 02-18-2026
Application #41 | 5464 | HV-VOIP Services | Web service to provide insured and agent data back to the agent or call center representative. | CL | HV | Esposito, Colleen | R. Hunter T. Webber | Mike Kelly | in-house | Back end | IT Service | Support | No | In Progress - Planning | 2027-04-30 | Modernization | SFTP, VSAM, Windows, IIS, C# .Net Flat Files, COBOL | Medium | 1 | DB2 MS SQL Server | N/A | already ready | Active, Not isolated | 10-15 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-Clarify | 1 | DB | IVR | 1 | API | 5296 Legacy Billing System | Clarify | 0 | less than 10GB | reads HV Clarify database, decom with clarify | HV -Clarify | No | N/A | Daily | No | N/A | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 0 |  | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 1 | Shared | 5 | 2 | 47 | Github, Jenkins, UCD, Apigee, Harness | N/A | N/A | TBD | HV Billing | Mike Kelly | Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #42 | 5465 | HV-webMethods | webMethods is the backbone of Harleysville SOA- and EDA-enablement and provides support for HTTP/s, FTP/s and SMTP transport protocols, messaging, SOAP web service, synch/asynch, service orchestration, logging, standardized error handling, etc. The webMethods Integration Platform enables realime and batch service integration between Harleysville's core insurance applications on both the Windows and IBM mainframe environments. SOA application. | CL, PL, Claims, Life | HV | Esposito, Colleen | N/A | Mike Kelly | 3rd party | Back end | 3rd Party | 3rd Party | Yes - Developer IDE | Not Started | 2027-04-30 | Modernization | Java, Windows Server, SQL Server | Very High | 1 | MS-SQL | Apigee | already ready | Active, Not isolated | 15-20 years | 12-18 Months | No | No | Very High | Part of Group | No | Yes | No | HV-ALL | 123 | API | HV-All, Claim Center, | TBD | API, DB Calls | HV-Duck Creek, HV-AQS, HV-Agency Portal, HV-ImageRight | HV-Duck Creek, HV-AQS, HV-Agency Portal, HV-ImageRight | 0 | less than 10GB | database is self supporting, creates its own db to store configuration. | HV - All | No | N/A | Daily | No | Discard | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 0 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 2 | Dedicated | 19 | 2 | 0 | N/A | N/A | Support Contract | TBD | WebMethods Doc | Mike Kelly | 11/10- Date changed to 04/30/27 | N/A | Decom and Discard | Decom and Discard | 51 | 1 | 22 | 1 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #43 | 5478 | HV-Agent Portal | Portal for agents to view his book of business, begin new business transaction and launch into applicable policy systems, gather agency reports, etc. | CL | HV | Esposito, Colleen | Jamey Fauque | Tony Brnic | in-house | Both | Application | Support | Yes | Not Started | 2026-12-31 | Modernization | .net | High | 2 | Yes(MS SQL Server) | Agent Center | 2026-06-30 | Active, Not isolated | >20 Years | 3-6 Months | No | No | High | Single | Yes | Yes | No | NA | NA | NA | HV-AQS, SSRS, HV-Webmethods | 3 | API, DB calls | 5479 HV AQS | HV-Agent Portal, HV-IADB, HV-ImageRight, HV-AIS, HV-U279, HV-Underwriting Rules Engine (URE), HV - Harleysville Underwriting Guide, Claims Service, SSRS Reports, Account Propsal Services, Policy Holder Reports DB, HV Duck Creek, HV AQS, HV-Mainframe CL, HV-WebMethods, HV-Melissa, HV Informatica, HV Legacy Billing, | 7 on-demand | more than 100GB | IADB - account-level data | HV AQS | No | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 20 | >100 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 3 | 1 | 2 | Github, Jenkins, UCD | NA | NA |  | Agent Portal | Tony Brnic | 10/30- Colleen to do more research on it | Glacier | P&C Data Lakehouse + AWS Glacier | Inquiry UI, API, Data Extract Process + RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #44 | 5479 | HV-AQS | Policy administration for commercial lines. | CL | HV | Esposito, Colleen | Linda Brockney | dan croll | 3rd party / in-house | Both | Application | Policy | Yes | In Progress - Planning | 2026-12-31 | Modernization | Win2019, SQL2019 | Very High | 2 | Yes | CL Policy Center | already ready | Active, Not isolated | >20 Years | 6-12 Months | No | No | High | Part of Group | Yes | No | No | HV-Informatica, HV-Webmethods, SSRS | 10 | DB calls, API | HV-Webmethods | 20 | API | 5479 HV AQS | Policy Migration Services, HV Access Express, webMethods, agent portal | 19 daily | more than 100GB | HR_AQS_Policy, HR_AQS_Resource, HR_AQS_ResourceEdit,HR_AQS_ResourceTest, HR_AQS_Document, HR_AQS_DocumentEdit, HR_AQS_Repository, HR_AQS_System, IADB, Global_IADB | HV AQS | Yes | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 20 | >100 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Both | 9 | 5 | 1 | Github, Jenkins, UCD | NA | NA |  | HV-AQS | Dan Croll |  | Hybrid (data Lakehouse + Gacier) | P&C Data Lakehouse + AWS Glacier | Inquiry UI, API, Data Extract Process + RRC | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #45 | 5567 | HV-Starteam | Source management product that we have licensed for AQS. Need to save the source code. | CL | HV | Esposito, Colleen | IT | Mike Kelly, Joanne Nuzzi | 3rd party | Back end | 3rd Party | Source Code | Yes | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019 | Medium | 1 | SQL Server | NA | NA | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Part of Group | No | No | No | HV-AQS | 1 | db calls, source code | HV-AQS | 1 | db, sourc code | 5479 HV AQS | AQS | 0 | less than 10GB | Source Code for AQS, data, forms and rates | Starteam | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 1 | 1 | 1 | NA | NA | NA |  | HV-Starteam |  |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 20 | 3 | 96% |  | Frank provided signed off on 02-18-2026
Application #46 | 5570 | HV-Predictive Modeling | Provides underwriting scoring on accounts based on policy information | CL | HV | Esposito, Colleen | Scott Woomer | Dan Croll, Dennis Schell | In-house | Back end | Application | UW | No | Not Started | 2026-12-31 | Modernization | CICS, win2019, SQL2019, IIS,Duckcreek Author, asp.net, c#.net, SQL, Webservices,Melissa, Vintelligence, Proxix, ISOPPC, Documaker, MA RMA, Verisk reporting (MVR), Lexus Nexus, | Low | 1 | SQL | NA | NA | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | Yes | No | No | HV-Informatica, HV-Webmethods | 2 | db calls, api | HV-Informatica | 1 | DB calls | 5479 HV AQS | HV-AQS, HV-Quote Services, HV-Agent Portal | 0 | more than 100GB | Multilple Databases - collect non PII information that is used during rating/scoring | HV-Predictive Modeling | No | UND120 – Commercial Lines, Property, Casualty - indefinite | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 5 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV-Shared Web Doc |  |  | Glacier | AWS Glacier | RRC | 52 | 0 | 20 | 3 | 96% |  | Frank provided signed off on 02-18-2026
Application #47 | 5666 | HV-AIS | Agency SQL database and services used throughout organization for agency validation. | CL, PL | HV | Esposito, Colleen | Christina Ledbedder | Frank Unger | In-house | Back end | Component | Discard | No | Not Started | 2026-12-31 | Modernization | win2019, SQL2019, asp.net, c#.net, SQL, Webservices, IIS | Medium | 1 | Yes-SQL Server | AMF | already ready | Active, Not isolated | >20 Years | 6-12 Months | No | No | Medium | Part of Group | Yes | No | No | HV-Informatica, HV-Webmethods | 2 | db calls, api | HV-Agency Licensings | 1 | db call | 5479 HV AQS | AQS, DCT, Agent Portal. | 1 daily | 10-30GB | copy of mainframe master | HV- Agency Systems | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 0 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 1 | Shared | 5 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV-Shared Web Doc |  |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 20 | 3 | 96% |  | Frank provided signed off on 02-18-2026
Application #48 | 5668 | HV-Harleysville Enterprise Web Services (HEWS) | Grouping of services, an application service function provided using network address over the web enabling communication between two systems. | CL | HV | Esposito, Colleen | N/A | Joanne Nuzzi | In-house | Back end | IT Service | Support | No | In Progress - Planning | 2026-12-31 | Modernization | win2019, SQL2019, C# .NET, IIS | Medium | 2 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Part of Group | No | No | No | HV-Webmethods, HV-AQS | 1 | API | n/a | 0 | None | 5479 HV AQS | HV-IADB, | 0 |  | Uses various databases used by other apps. Does not have it's own database |  | No | N/A | Daily | No | N/A |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | CVALIR Reporting | N/A | N/A | TBD | HV-Shared Web Doc | Joanne Nuzzi |  | N/A | N/A | N/A | 49 | 3 | 21 | 2 | 93.33% |  | Frank provided signed off on 02-18-2026
Application #49 | 5670 | HV-Question Answer Service | Main service component for the URE application to determine questions to ask and then save responses Dependent on adding products. | CL | HV | Esposito, Colleen | Linda Brockney | Tony Brnic | In-house | Back end | Component | UW | Yes | Not Started | 2026-12-31 | Modernization | win2019, SQL2019,IIS,C# .Net,Github, Jenkins, UCD | Low | 1 | SQL Server | NA | NA | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-Webmethods | 1 | API | NA | NA | NA | 5479 HV AQS | HV-AQS, Agent Portal, HV URE | 0 | less than 10GB | Question, Service_Log | HV-Question Answer Service | No | UND120 – Commercial Lines, Property, Casualty - indefinite | Daily | No | Archive | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 5 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 5 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business 10/30- Colleen to do more research on it | Glacier | AWS Glacier | RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #50 | 5713 | HV-Melissa (address check) | Vendor supplied information used to validate and scrub addresses for Duck Creek quotes and policies. | CL, PL | HV | Esposito, Colleen | PL and CL | Dennis Schell | 3rd party / in-house | Back end | 3rd Party | 3rd Party | No | Not Started | 2026-12-31 | Modernization | Windows ,C# .NET , IIS, SQL Server, Github | Low | 1 | Files | NA | NA | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Single | No | No | No | HV-Webmethods | 1 | api | NA | NA | NA | 5479 HV AQS | HV-Duck Creek, HV-AQS | 0 | less than 10GB | Monthly datasets provided by vendor. ,DAT files | HV-Melissa | No | N/A | N/A | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 0 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Shared | 1 | Shared | 3 | 1 | 20 | Github, Jenkins, UCD, Melissa | NA | NA |  | HV-Shared Web Doc | Mike Kelly |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #51 | 5717 | HV-Active PDF | HV-Active PDF | CL | HV | Esposito, Colleen | Linda Brockney | dan croll, laurie fernes | 3rd party | Back end | Component | Support | No | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019 | Medium | 1 | Yes | NA | NA | Active, Not isolated | >20 Years | 6-12 Months | No | No | Medium | Part of Group | Yes | No | No | HV-AQS, HV-WCReporting, HV-Documaker | 3 | api | NA | NA | NA | 5479 HV AQS | Active PDF will not have it's own document and will be inserted in each Planning Guide as needed HV-Question Answer Service, HV Bill Matrix, HV EFT Services, HV BL registration DB, HV ISOMatrixHGM DB, HV ASPSessionState DB, Account Register(Global IADB), Clear quote, Agent Center, Policy Center, Experian, Recaptcha | 0 | less than 10GB | pdf images, batch print info | HV-AQS | No | N/A | N/A | No | Discard | N/A | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 1 | NA | 3 | Active PDF | NA | NA |  | HV-AQS | Dan Croll, Laurie Fernes |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #52 | 5720 | HV-UW Assignment | Web application for updating workflow routing within Image Right for Commercial Lines | CL | HV | Esposito, Colleen | Lindsey Moyer UW / Processing | Mike Kelly | In-house | Front end | Component | UW | Yes | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019 | Medium | 1 | MS-SQL | N/A | already ready | Active, Not isolated | 15-20 years | 3-6 Months | No | No | Low | Single | No | No | No | HV-Agency Master | 1 | DB | HV-ImageRight, HV-Agent Portal | 2 | DB, webMethods | 5479 HV AQS | HV-ImageRight, HV-Agent Portal | 0 | 10-30GB | HV U/W names and ID's/ SQL | HV-Imageright | No | N/A | Daily | No | Discard | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 20 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 2 | Shared | 4 | 4 | 47 | Github, Jenkins, UCD | n/A | N/A | TBD | ImageRight Doc | Mike Kelly |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #53 | 6010 | HV-Expiration | The HV Expiration System is a mainframe-based application responsible for managing policy expiration data. It operates as part of a larger batch processing flow and is typically the last system to run before the CICS files are brought back online each day. | CL | HV | Esposito, Colleen | IT | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | In-house | Both | Application | Support | Yes | In Progress - Planning | 2027-04-30 | Modernization | MF, VSAM, CICS | Low | 1 | VSAM | None | NA | Active, Not isolated | >20 Years | 12-18 Months | No | No | Low | Part of Group | Yes | No | No | HV-Commercial Lines Legacy, HV-Personal Lines Legacy | 2 | files | NA | NA | NA | 5479 HV AQS | most HV systems ( Agency, Direct bill) | 3 (Daily) | less than 10GB | Harleysville legacy system (policy summary index) for renewal processing of all personal and commercial policies both automated and manual and CICS, policy info, renewal info, dates, indicators, term info, premium, bill acct, status, etc (VSAM) CORP00PV.AGCY.EXP.REN.MASTER.C CORP00PV.AGCY.EXP.REN.IDX.C | 6010-HV-Expiration | No | N/A | Daily | No | Discard | N/A | NA | ChangeMan | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | NA | na | 20 | na | na | na |  | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #54 | 6096 | HV-AQS Batch Print | This is a custom .net application to package HVAQS Policy Output utilizing Active PDF. This component provides the bar coding on documents for Finishing. It also generates a transactional cover letter per Billing Account,applies the NY ID Card PDF417 bar code and packages new business and renewal output with the Agency Bill Schedule | CL | HV | Esposito, Colleen | Linda Brockney | dan croll, laurie fernes | In-house | Back end | Component | Support | No | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019 | Medium | 1 | Yes | NA | NA | Active, Not isolated | >20 Years | 3-6 Months | No | No | Medium | Part of Group | Yes | No | No | HV-AQS | 1 | db calls | NA | NA | NA | 5479 HV AQS | HV-AQS , HV-QDIRECT | 0 | less than 10GB | Input xml received from HV policy systems and images are created using this app and sent to HV-Q Direct for printing, images are fed to Imageright from HV-AQS not HV-BatchPrint. Input PDFs are received from from HV-AQS and HV-Peer Sync (to transfer pdfs to server) | HV-AQS | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 1 | 1 | 3 | NA | NA | NA |  | HV-AQS | Dan Croll |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #55 | 6393 | HV-Agency Licensing | Capturing of agency and producer information from CMS G2 onto a SQL database, which is enriched with demographic and banking info from the Harleysville Agency Master file, providing agency licensing validation to Harleysville systems and a regular ETL feed to Nationwide DPIM and AMF systems | CL, PL | HV | Esposito, Colleen | Christina Ledbedder | Venkata Ranga Mahesh, Padarthi , Frank Unger | In-house / data sourced from 3rd party | Back end | Component | 3rd Party | No | In Progress - Planning | 2026-12-31 | Modernization | Win2019, SQL2019, asp.net, c#.net, SQL, Webservices, IIS | Low | 1 | SQL Server | AMF, EPOM | already ready | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Part of Group | Yes | No | No | EPOM (Vertafore files) | 1 | Files | HV-Webmethods, HV-Informatica | 3 | API, DB calls, SFTP | 5479 HV AQS | AQS, DCT, Agent Portal. | 0 | 10-30GB | Producer Data from Vertfore - | ThirdParty Vertofore | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 0 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 1 | Shared | 5 | 1 | 20 | NA | NA | NA |  | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #56 | 6397 | HV-ISO PPC | 3rd Party data source that integrates with Duck Creek and CL AQS to supply Property Protection Class base on geographic information | CL, PL | HV | Esposito, Colleen | Angelia Pike | Mike Kelly | 3rd party | Back end | Third Party | 3rd Party | No | Not Started | 2026-12-31 | Modernization | DB2 | High | 1 | MS-SQL | N/A | already ready | Active, Not isolated | 10-15 Years | 3-6 Months | No | No | High | Single | Yes | Yes | No | HV-AQS, HV-Duckcreek | 2 | webMethods | N/A | 0 | None | 5479 HV AQS | HV-AQS HV-Duck Creek | 0 | more than 100GB | ISOLocation API product updates stored on the SQL database. Monthly updates received from 3rd party | HV-ISO PPC | No | N/A | Daily | No | Discard | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 0 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Dedicated | 1 | Shared | Kubernetes | 2 | 47 | Github, Harness, Kubernetes | N/A | N/A | TBD | HV-Shared Web Doc | Mike Kelly |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #57 | 6408 | HV-Bill Matrix | 3rd Party Vendor for on line payments -- an online payment system operated by BillMatrix Corporation that is designed to accept payments | CL, PL | HV | Esposito, Colleen | Andrea Shatto | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | 3rd party | Back end | Third Party | 3rd Party | No | In Progress - Planning | 2027-04-30 | Modernization | Vendor | High | 1 | NA | NA | NA | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Part of Group | Yes | Yes | Yes | HV-Legacy Billing Systems | 1 | SFTP | NA | NA | NA | 5479 HV AQS | HV-Direct Bill 5478 HV-Agent Portal | 0 | NA | Credit card processing and one time EFT for Harleysville |  | No | N/A | N/A | No | N/A | NA | NA | Changeman | 30 days - App Specific | CLS release management Team | 0 | 0 | Already using go forward app | No | Well Documented | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | TBD | NA | Handled by business |  | HV Billing |  | Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 50 | 2 | 21 | 2 | 94.67% |  | Frank provided signed off on 02-18-2026
Application #58 | 6422 | HV-Account Proposal | Application that generates Account Proposal for CL agents | CL | HV | Esposito, Colleen | Linda Brockney | Tony Brnic, Laurie Fernes | In-house | Front end | Component | Print | No | Not Started | 2026-12-31 | Modernization | Windows ,C# .NET , IIS, SQL Server, Github | Low | 1 | Yes | CL Policy Center | already ready | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Single | No | No | No | HV-Webmethods | 1 | api | NA | NA | NA | 5479 HV AQS | HV-DOCUMAKER, AQS, HIEDMS | 0 | less than 10GB | Requests entered via HV CL Agent Portal and Underwriter Workbench to generate real time Account Proposal generated using HV-Documaker. A PDF is returned to requesting user. HV-Documaker does not store the pdf or send it to ImageRight. | HV-AQS | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 5 | >100 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 5 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV-AQS | Dan Croll |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #59 | 6424 | HV-AuditWin Plus | Utility software used by field auditors to manage audit assignments, inventory and scheduling. Audit assignments are downloaded to the AuditWin Plus (formerly known as Field Manager) from Audit Control Environment (ACE). | CL, PL, Claims, Life, Financial Accounting | HV | Esposito, Colleen | Smith, Krystal A Shewey, Dora A | Mike Kelly | 3rd party | Back end | Component | Discard | Yes | Not Started | 2026-10-15 | Modernization | Windows, IIS, Third party | Medium | 1 | MS-SQL | AuSum | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | Yes | No | No | HV-ACE | 1 | web service | HV-ACE | 1 | web service | 5479 HV AQS | HV- ACE - Premium Audit | 0 |  | Service that retrieves data, no data is stored | HV - ACE Premium Audit | No | N/A |  | No | Discard | N/A | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 12 | 0 | Already using go forward app | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 2 | Desktop application | 0 | 0 | 0 | N/A | N/A | N/A | TBD | HV-ACE - Premium Audit | Mike kelly | 10/30- Collen to accelerate timeline | N/A | Decom and Discard | Decom and Discard | 50 | 2 | 22 | 1 | 96% |  | Frank provided signed off on 02-18-2026
Application #60 | 6452 | HV-ACCESS Collections | 3rd Party Vendor for collections agency -- With Access Collections, LLC you'll have the skill and expertise needed to collect your consumer debt, delivering improved cash flow and reduced days outstanding. | CL | HV | Esposito, Colleen | Melissa Wood Nick Ginther | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | 3rd party | Back end | Third Party | 3rd Party | No | In Progress - Planning | 2027-04-30 | Modernization | Vendor | High | 1 | NA | NA | NA | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Part of Group | Yes | Yes | Yes | NA | NA | NA | HV-Legacy Billing Systems | 1 | SFTP | 5296 HV Legacy Billing Systems | HV- Accounts Receivable | 0 | NA | File exchanges with 3rd party on receivables |  | No | N/A | N/A | No | N/A | NA | NA | Changeman | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | TBD | NA | Handled by business |  | HV Billing | Joanne Nuzzi | Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 50 | 2 | 22 | 1 | 96% |  | Frank provided signed off on 02-18-2026
Application #61 | 6453 | HV-PNC Bank Feed | 3rd Party Vendor for agent sweep screens - PNC/Wells Fargo Bank | CL | HV | Esposito, Colleen | Andrea Shatto | Venkata Ranga Mahesh, Padarthi , Colleen Esposito | 3rd party | Back end | Third Party | 3rd Party | No | In Progress - Planning | 2027-04-30 | Modernization | Vendor No code is available, because 3rd party vendor | High | 1 | NA | NA | NA | Active, Not isolated | >20 Years | 12-18 Months | No | No | Medium | Part of Group | Yes | Yes | Yes | HV-Legacy Billing Systems | 1 | Lock box - FTP | NA | NA | NA | 5296 HV Legacy Billing Systems | HV-Direct Bill, HV-Life | 0 | NA | Lockbox for Harleysville for Payments and stubs |  | No | N/A | N/A | No | N/A | NA | NA | Changeman | 30 days - App Specific | CLS release management Team | 0 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | NA | NA | 20 | TBD | NA | Handled by business |  | HV Billing | Joanne Nuzzi | Set up meeting with Kristi on aligning on next steps and status. | N/A | N/A | N/A | 50 | 2 | 22 | 1 | 96% |  | Frank provided signed off on 02-18-2026
Application #62 | 6500 | HV-AQS User SecurityLoad | Utility to load new NW/Harleysville agents as Users to AQS. | CL | HV | Esposito, Colleen | Linda Brockney | dan croll | in-house | Front end | Component | Security Audit | Yes | In Progress - Planning | 2026-12-31 | Modernization | Windows ,C# .NET , IIS, SQL Server, Github | Medium | 1 | Yes | NA | NA | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Part of Group | Yes | No | No | NA | NA | NA | HV-AQS | 1 | db call | 5479 HV AQS | HV-AQS | 0 | less than 10GB | UserSecurityLoad SQL db | AQS | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 5 | 1 | 20 | Github, Jenkins, UCD | NA | NA |  | HV-AQS | Dan Croll |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #63 | 6512 | HV-AQS - Doc Utility | Doc Utility is used by AQS Configuration Analysts and Developers for adding and updating document data. | CL | HV | Esposito, Colleen | Linda Brockney | dan croll | 3rd party | Front end | Component | Support | Yes | Not Started | 2026-12-31 | Modernization | Win2019, SQL2019 | Medium | 1 | Yes | NA | NA | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Part of Group | No | No | No | HV-AQS | 1 | api | NA | NA | NA | 5479 HV AQS | HV-AQS | 0 | less than 10GB | AQS_Docs | AQS | No | N/A | Daily | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Well Documented | Has operational & business knowledge | Shared | 2 | Shared | 1 | 1 | 3 | NA | NA | NA |  | HV-AQS | Dan Croll |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #64 | 6859 | HV - eForms Generation App | Generates ACORD COI (Certificate of Insurance) and EOP (Evidence of Property) forms currently used by the Service Center group. Minimal user entry required for form completion | CL | HV | Esposito, Colleen | Linda Brockney | Joanne Nuzzi | in-house | Both | Application | Print | Yes | In Progress - Planning | 2026-06-30 | Modernization | Win2019,SQL Server ,IIS,C# .NET ,Github | Medium | 1 | SQL server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-UWWB | 1 | API | n/a | 0 | None | 5479 HV AQS | N/A | 0 | less than 10GB | EFORM - Acord form data | HV-eForms Generation App | No | <Data treatment is mentioned as Discard> ISY100 Application Documentation and Source Code *1 ISY110 Disaster Recovery Plans *3 ISY120 Back-up Tapes, Files and Data MAX30 Days ISY130 Systems Technical Administration MAX3 Years ISY140 Technical Support Requests 3 ISY150 Website Activity Logs 6M ISY160 Website Data Security Records 3 ISY170 Information Security Testing 5 LEG190 Contracts and Agreements / Software Licenses and Escrow Agreements *7 LEG200 Contracts and Agreements / Vendors *7 | Daily | No | Discard |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | Github | N/A | N/A | 5000 Annual Run cost | HV-Shared Web Doc | Joanne Nuzzi | 1/20- Frank mentioned Joanne is looking into this | N/A | Decom and Discard | Decom and Discard | 51 | 1 | 23 | 0 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #65 | 7558 | HV-Hazard Grade Matrix (HGM) | Application used by underwriters to get the Matrix Grade; also used by Product staff to update information for use in Underwriting decisions via an admin page. | CL | HV | Esposito, Colleen | Linda Brockney | Tony Brnic, Joanne Nuzzi | in-house | Both | Component | UW | Yes | In Progress - Planning | 2026-12-31 | Modernization | Windows, C# .NET, IIS | Medium | 1 | Yes(SQL Server) | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-Webmethods, HV-AQS, HV-Agent Portal,HV - UWWW | 1 | DB | n/a | 0 | none | 5479 HV AQS | N/A | 0 | less than 10GB | ISOMATRIXHGM - List of all hazard information. | HV-HGM | No | Indefinite | Daily | No | Archive | 3-4 hours | N/A | Source code to be retained in GitHub for atleast a year planning guide : Sharepoint, GitHub | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | Yes | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | GitHub | N/A | N/A | TBD | HV-Hazard Grade Matrix (HGM) | Joanne Nuzzi | 1/20- Frank mentioned Joanne is looking into this | Glacier | AWS Glacier | RRC | 52 | 0 | 22 | 1 | 98.67% |  | Frank provided signed off on 02-18-2026
Application #66 | 7814 | HV-CL Insured Account search tool | CL Insured Account name search tool used by processing groups for a lookup of account and billing account \# info. A Link to Image Right is included | CL | HV | Esposito, Colleen | Jennifer Zaugg | Joanne Nuzzi | in-house | Both | Utility | Support | Yes | In Progress - Planning | 2026-06-30 | Modernization | ADO .Net, ASP .Net, C#.net, AJAX .Net, SQL, T-SQL, SQL CLR, CSS, XML, XSLT, SOAP, JavaScript, Jquery | Medium | 1 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Single | No | No | No | n/a | 0 |  | n/a | 0 | none | 5479 HV AQS | AQS, Agent Portal, Workbench, | 0 |  | N/A | CL Insured Account DB (IADB) | No | N/A | Daily | No | N/A |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 102 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | Melissa, Experian, MSB, Sage, Mueller, Hagerty, Bill Matrix, Refcon, BingMaps, SmartWorks, TrustArc, Recaptcha, MS Enterprise Library, AjaxControlToolkit, HTMLAgilityPack, NewtonSoft, YUI library Github, Jenkins, UCD | N/A | N/A | TBD | HV-Agent Portal |  |  | N/A | N/A | N/A | 49 | 3 | 20 | 3 | 92% |  | Frank provided signed off on 02-18-2026
Application #67 | 7866 | HV-U279 Processing Form | New business and renewal communication tool between Underwriting and Processing. Supports instructions for setting up billing and policies. Tool to generate a form for completion and save to Image Right for future updates. | CL | HV | Esposito, Colleen | Linda Brockney | Joanne Nuzzi | in-house | Both | Utility | Underwriting | Yes | In Progress - Planning | 2026-12-31 | Modernization | Windows,IIS,C# .NET | Medium | 1 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-UWWB | 1 | API | HV-ImageRight | 1 | API | 5479 HV AQS | HV-Underwriter Workbench | 0 |  | N/A | N/A | No | Indefinite | Daily | No | Archive | 3-4 hours | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | GitHub | N/A | N/A | TBD | HV-U279 Processing Form | Joanne Nuzzi | 1/20- Frank mentioned Joanne is looking into this | RRC |  |  | 51 | 1 | 22 | 1 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #68 | 7944 | HV-PowerShell-BuildDeployment-Scripts | Jenkins is the tool we use for developers to initiate the PowerShell scripts to do the build/deployment - This will be used to deploy AQS and WebMethods code (confirm if this is already gone, switch to urban code deploy) | CL | HV | Esposito, Colleen | IT | Dennis Schell, Dan Croll | in-house | Back end | Component | Support | No | Not Started | 2026-12-31 | Modernization | PowerShell | Low | 1 | NA | NA | NA | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Single | No | No | No | Jenkins | 1 | execution | HV-AQS | 1 | files, deploy | 5479 HV AQS | AQS, Starteam | 0 | NA | deployment tool for AQS | N/A | No | N/A | N/A | No | Discard | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 2 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | 1 | NA | NA | NA | NA | NA |  | HV-Starteam |  |  | N/A | Decom and Discard | Decom and Discard | 52 | 0 | 20 | 3 | 96% |  | Frank provided signed off on 02-18-2026
Application #69 | 7954 | HV-Core Integration Svc | Collection of web services utilized by numerous applications. A large number are used by UWWB and AQS NB and Renewal process | CL | HV | Esposito, Colleen | IT | Joanne Nuzzi | in-house | Back end | IT Service | Support | No | In Progress - Planning | 2026-12-31 | Modernization | Windows,IIS,C# .NET , SQL Server, | Medium | 1 | SQL server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-Webmethods, HV-AQS, HV-Agent Portal | 1 | API | n/a | 0 | none | 5479 HV AQS | AQS, HV-IADB, Quote Service | 0 |  | N/A | N/A | No | N/A | Daily | No | N/A |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | Github | N/A | N/A | TBD | HV-Shared Web Doc | Joanne Nuzzi |  | N/A | N/A | N/A | 50 | 2 | 21 | 2 | 94.67% |  | Frank provided signed off on 02-18-2026
Application #70 | 7955 | HV-MVR Services | Used by AQS and UWWB to request/access driver MVR records. MVR records are then stored in ImageRight. Also contains a batch component, that calls an external service, that scans public records for additional driver data that is then stored in a local database | CL | HV | Esposito, Colleen | Linda Brockney Brenda Crossin | Joanne Nuzzi | in-house | Back end | IT Service | Support | No | In Progress - Planning | 2026-06-30 | Modernization | Windows, IIS, C# .NET, SQL, GitHub | Medium | 1 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | Yes | Yes | No | HV-UWWB | 1 | API | HV-UWWB | 1 | API | 5479 HV AQS | HV-UWWB; webMethods; HV-AQS, Stat | 0 | 30-70GB | CL_Driver, Application_Log; MVR database on OHNALDB0199.nwie.net, 1021 can be deleted | AQS | No | N/A | Daily | No | Discard |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 3 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | N/A | N/A | N/A | 5000 Annual Run support | MVR DOC | Frank Unger |  | N/A | Decom and Discard | Decom and Discard | 51 | 1 | 22 | 1 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #71 | 7956 | HV-Core Logic Svc | Services that handle Hazard data for Property policies. Used by NB and Renewal processes | CL | HV | Esposito, Colleen | Linda Brockney | Joanne Nuzzi | in-house | Back end | IT Service | 3rd Party | No | In Progress - Planning | 2026-12-31 | Modernization | Windows,IIS,C# .NET , SQL Server, | Medium | 1 | SQL server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Part of Group | No | No | No | HV-Webmethods, HV-AQS, HV-Agent Portal | 1 | API | n/a | 0 | none | 5479 HV AQS | AQS | 0 | less than 10GB | External_Property_Data | N/A | No | N/A | Daily | No | N/A |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only basic information | Shared | 2 | Shared | 5 Server directory/folder | 2 (Prod/E2E) | 47 | Github | N/A | N/A | TBD | HV-Shared Web Doc | Joanne Nuzzi |  | N/A | N/A | N/A | 51 | 1 | 21 | 2 | 96% |  | Frank provided signed off on 02-18-2026
Application #72 | 7957 | HV-Billing Svc | Services that support Billing | CL | HV | Esposito, Colleen | Linda Brockney | Venkata Ranga Mahesh, Padarthi , Frank Unger | in-house | Back end | IT Service | Support | yes | Not Started | 2027-04-30 | Modernization | Windows ,C# .NET , IIS, SQL Server, Github | Low | 1 | SQL Server | Flex Bill | already ready | Active, Not isolated | >20 Years | 6-12 Months | No | No | Low | Single | No | No | No | NA | 0 | NA | HV-Webmethods | 1 | API | 5479 HV AQS | HV-Core Integration Svcs, HV-IADB, CL Legacy Service, Agent Portal | 0 | NA | N/A | N/A | No | N/A | N/A | No | N/A | NA | NA | Source code to be retained in GitHub for atleast a year | 30 days - App Specific | CLS release management Team | 0 | 0 | Already using go forward app | No | Minimal Documentation | Has only operational knowledge | Shared | 1 | Shared | 5 | 1 | 20 | NA | NA | NA |  | HV-Billing | Joanne Nuzzi |  | N/A | N/A | N/A | 52 | 0 | 21 | 2 | 97.33% |  | Frank provided signed off on 02-18-2026
Application #73 | 8039 | HV-CLManuscripts | HV-CLManuscripts CL Manuscripts (or CL Corporate Form) templates publish from CL Forms Sharepoint library to AgentPortal, UWWB, and AQS.Agent Portal –Supplemental applications and Questionaires, versions, and link to retrieve those forms once selected UWWB – Manuscript Templates – Forms/endorsements, versions, and a link to retrieve forms (same forms used for AQS) AQS – Manuscript endorsement titles and wording is used for AQS forms | CL | HV | Esposito, Colleen | Linda Brockney | Joanne Nuzzi | in-house | Back end | IT Service | Support | No | In Progress - Planning | 2026-06-30 | Modernization | Windows ,C# .NET , IIS, SQL Server, Github | Medium | 1 | SQL Server | CL Policy Center | already ready | Active, Not isolated | >20 Years | 3-6 Months | No | No | Low | Single | No | No | No | n/a | 0 |  | HV-UWWB, HV-AgentPortal, HV-AQS | 3 | NAS Shares | 5479 HV AQS | same as HV-AQS | 0 |  | This application/component doesn’t have its own database. It uses other databases ‘Renewal Automation’ and ‘APADB’ | N/A | No | N/A | Daily | No | N/A |  | N/A | Source code to be retained in GitHub for atleast a year | 30 days | CLS release management Team | 1 | 0 | Users already using Policy Center | No | Minimal Documentation | Has only operational knowledge | Shared | 2 | Shared | 3 Server directory/folder | 2 (Prod/E2E) | 47 | Github | N/A | N/A | TBD | HV-CLManuscripts | Joanne Nuzzi |  | N/A | N/A | N/A | 49 | 3 | 21 | 2 | 93.33% |  | Frank provided signed off on 02-18-2026
Application #74 | 9999 | Commercial Auto | All policy and quote data in BA, this is a supporting app with rates. | Commercial Auto | PCIO | Esposito, Colleen | Andrea Amick | Mike Hansen | In-house | Both | Application | Policy | Yes | In Progress - Planning | 2026-12-31 | The app is no longer needed with the migration to the go forward CL PolicyCenter platform | zOS,CICS, DB2 on zOS, COBOL,JCL,SQL, Changeman | High | Low | DB2 on zOS, SQL, VSAM, Tape | CL Policy Center | N/A | Active, Not isolated | >20 Years | 3-6 Months | Yes | Yes | High | Part of Group | Yes | No | No | Mainframe Business Auto (909) | 10 | FTP, Flat Files | Mainframe Business Auto (909) | 10 | FTP, Flat Files | 909 Mainframe Business Auto | Specified in AH and AK | None | less than 10GB | VSAM files for storing commercial auto rates and coverage codes | Commercial Auto | No | Indefinite | Daily | N/A | TBD | TBD | TBD | Source code is stored in Changeman. Documentation is stored in Sharepoint. Source code should be kept for 1 year. | 30 days - App Specific | NA | > 30 Users | > 30 Users | N/A | No | Minimal Documentation | Has operational & business knowledge | Dedicated | 3 | Shared | NA | NA | NA | Tablebase | Yes | Yes | Combined | Commercial Auto | Prasad/ Sunset-PCIO |  | Hybrid (data Lakehouse + Gacier) | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | 49 | 3 | 22 | 1 | 94.67% |  | Signed off by Prasad on 02-18-2026
[77 empty] | 3724 | 124 | 1564 | 138 | 95.28%
Note on Z9: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z10: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z12: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z13: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z15: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z23: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z26: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z27: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z28: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z29: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z30: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z31: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z32: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z33: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z34: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z43: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z59: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z63: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z66: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z67: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.
Note on Z80: Karthikeyan, Sumithra: The system will not allow NB and Renewal to process with an expiration of 7/2/2026 or greater.

## Master 2024 - Refer this (hidden)
App Id | Application Name | Decommissioning Planning Status | Decom Target Complete | Planning Guide Document | Planning Guide Doc Lead | Next Steps | Application Description | SEPM | SME | Big Rock | Business Facing | App Life Cycle Phase | Application Category | Retirement Date - Date when Business No Longer Used | Count | 2017 Decommissioning Category | 2017 Decommissioning Event | 2017 Forecasted ARC (Directional) | 2018 Forecasted ARC (Directional) | 2018 Decommissioning Category | 2018 Decommissioning Timeline | 2019 Decommissioning Category | 2019 Decommissioning Timeline | 2019 Decommissioning Timeline (Updates in red) | 2019 Forecasted ARC TCO | 2019 Disb Code | 2020 Decommissioning Category | 2020 Decommissioning Timeline | 2020 Decommissioning Timeline (Updates in red) | Database or Data Store | Database/Data Store description; Type of data | System of Record | Data Owner (System) | Database Disposition | Retention Requirement | Application Type | Access - API/Service (also in Planning Guide) | Access - UI | Access - Batch/Bulk | Immediate access needed for some period of time? | Archive Pattern | Application Suite Dependency | Dependencies (App Level) | Tech Contact | Architect | Business Contact | SEPM Review Comments | Comments - Actions NEEDED (2020) | Suite | Data Type | Archive Storage | Data Access to Archive Data | Archive Target Start | Planview | Application Run Cost (2024) | Application Run Cost (2019) from APM (also in Planning Guide) | Contracts | Infrastructure | Agile Line | Questions | Location | Planning Completion Date | Planner Board Link | Plan Guide Link | Assess Business Stakeholders | Business Next Steps | Business Stakeholders Engaged | Business Status
451 | Pathway (DSM) | Not Started | 2026-12-31 | Pathway (DSM) |  | 10/30-Not sure it is being used for householding ,Lisa and team to do more research on tables and ecosystem | Maintains customer information at the name and address level 1/6/2020 go forward as long as Agent Center continues to use 03/14/25: APRM indicates retirement 12/31/26; follow up with John to align on needing to add this to our decom list. 03/14/25: John approved this to be added to decom list. | Schillaci-Beane, Lisa |  | No |  | Production | Application | N/A | 1 | [11 empty] | Go Forward | Go Forward | Go Forward | DB2 Tables | DB2 Tables- Around 20 Tables | No |  | Discard | N/A | Support |  |  |  |  | N/A | [11 empty] | N/A | [7 empty] | DM
909 | Mainframe Business Auto | In Progress - Planning | 2026-12-31 | Mainframe Business Auto | Prasad/ Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Policy processing system for Business Auto Policies. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM rate files, class files, edit files and tablebase VSAM files for entry, master and quotes. Also automatic renewal VSAM files VSAMC.PPV.DATA.ENTRY.INDEX VSAMC.PPV.DATA.ENTRY.MASTER VSAMC.PPV.INDEX VSAMC.PPV.MASTER VSAMC.PPV.LIVE.RATE VSAMC.PPV.QUOTE.PRINT.INDEX VSAMC.PPV.QUOTE.PRINT.MASTER VSAM1.PPV.ACCTDIST.MASTER VSAM1.PPV.CLASS VSAM1.PPV.QUOTE.INDEX VSAM1.PPV.QUOTE.INDEX.PRIOR VSAM1.PPV.QUOTE.MASTER.PRIOR VSAM1.PPV.QUOTE.MASTER VSAM1.PPV.QUOTE.INDEX.CURRENT VSAM1.PPV.QUOTE.MASTER.CURRENT VSAM1.PPV.RECYCLE.INDEX VSAM1.PPV.RECYCLE.MASTER VSAM1.PPV.RENEW.INDEX VSAM1.PPV.RENEW.MASTER VSAM1.PPV.VEHICLE.MAKE VSAM files used for inquiry during the nightly batch cycle VSAMN.PPV.DATA.ENTRY.INDEX VSAMN.PPV.DATA.ENTRY.MASTER VSAMN.PPV.INDEX VSAMN.PPV.INDEX.AFMR VSAMN.PPV.LIVE.RATE VSAMN.PPV.MASTER VSAMN.PPV.MASTER.AFMR VSAMN.PPV.QUOTE.PRINT.INDEX VSAMN.PPV.QUOTE.PRINT.MASTER | Yes | Mainframe Business Auto | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | Mike Hansen | Scott Grau | Michael Martin / Angie Pike | 1/27/23 From Jen Reed; BOP and BA ISO feeds. When those policies finally roll off legacy the current ISO feeds need to be adjusted to follow the ETL process defined for all other LOB's coming thru Policy Center. Mike Hanson (Sunset team) currently managed these processes today. |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
910 | Mainframe General Liability (GLS) | In Progress - Planning | 2026-12-31 | Mainframe General Liability (GLS) | Prasad/ Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Policy Processing system for General Liability policy types. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | VSAM policy and quote data in the index, master, data entry and quoue hold files. Also VSAM rates, rate date and class code files VSAM Files – Index - VSAMC.GLS.INDEX Master - SAMC.GLS.MASTER history index - VSAMC.GLS.HISTORY.INDEX history master - VSAMC.GLS.HISTORY.MASTER data entry - VSAMC.GLS.DATA.ENTRY quote - VSAMC.GLS.QUOTE.HOLD Quote print - VSAMC.GLS.QUOTE.PRT Rate date - VSAMC.GLS.POL.RATE.DATE rate file - VSAMC.GLS.LIVE.RATE,VSAM1.GLS.PSEUDO.RATE class code file - VSAMC.GLS.LIVE.CLASS quote file - VSAMC.GLS.QUOTE.HOLD Renewal data entry - VSAMC.GLS.DATA.ENTRY.RENEW, VSAMC.GLS.DATA.ENTRY.WORK Renewal rate date - VSAMC.GLS.RATE.DATE.RENEW,VSAMC.GLS.RATE.DATE.WORK Tape Files - Policy data is in the below tape files AID01.GLS.FINAL.YTD.INDEX.PURGE AID01.GLS.FINAL.YTD.MASTER.PURGE AID01.GLS.YTD.INDEX.PURGE AID01.GLS.YTD.MASTER.PURGE DB2 Tables – General Liability does not own any DB2 tables. Hercules - Data in Index and Master file is ingested to Hercules | Yes | Mainframe General Liability (GLS) | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | Rhonda Giedd | Scott Grau | Michael Martin / Angie Pike |  |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
911 | Mainframe Commercial Property | In Progress - Planning | 2026-12-31 | Mainframe Commercial Property | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Policy processing system for the Commercial Property Line of Business | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM rate files and tablebase VSAM files – Index - VSAMC.CPS.INDEX Master - VSAMC.CPS.MASTER Data entry - VSAMC.CPS.DATA.ENTRY Rates - VSAMC.CPS.RATE.FILE Renewal Data Entry - VSAMC.CPS.DATA.ENTRY.RENEW Quotes - VSAMC.CPS.QUOTE.ENTRY Quote print - VSAMC.CPS.QUOTE.PRINT Account Dist - VSAMC.CPS.ACCTDIST DB2 Tables – Commercial Property does not own any DB2 table Tape Files - AID01.CPS.FINAL.YTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules" | Yes | Mainframe Commercial Property | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | Patty Stump | Scott Grau | Michael Martin / Angie Pike |  |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
912 | Mainframe Package Control | In Progress - Planning | 2026-12-31 | Mainframe Package Control | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Policy processing system for the commercial package control system. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | VSAM policy and quote data on our index, master, and data entry files. VSAM Renewal index, master and data entry . Also VSAM edit files and tablebase VSAM files for entry, master and quotes. Also automatic renewal VSAM files VSAMC.PPZ.DATA.ENTRY.INDEX VSAMC.PPZ.DATA.ENTRY.MASTER VSAMC.PPZ.INDEX VSAMC.PPZ.MASTER VSAMC.PPZ.QUOTE.INDEX VSAMC.PPZ.QUOTE.MASTER VSAMC.PPZ.QUOTE.PRINT.INDEX VSAMC.PPZ.QUOTE.PRINT.MASTER VSAM1.PPZ.RENEW.INDEX VSAM1.PPZ.RENEW.MASTER VSAM1.PPZ.DAILY.EDIT.ERRORS VSAM1.PPZ.DATA.ENTRY.INDEX.CURRENT VSAM1.PPZ.DATA.ENTRY.MASTER.CURRENT VSAM1.PPZ.DATA.ENTRY.INDEX.PRIOR VSAM1.PPZ.DATA.ENTRY.MASTER.PRIOR VSAM1.PPZ.QUOTE.INDEX.CURRENT VSAM1.PPZ.QUOTE.MASTER.CURRENT VSAM1.PPZ.QUOTE.INDEX.PRIOR VSAM1.PPZ.QUOTE.MASTER.PRIOR VSAM1.PPZ.RECYCLE.INDEX VSAM1.PPZ.RECYCLE.MASTER VSAM files used in the Pak money FMR process VSAMC.PPZ.RECYCLE.ERROR VSAM1.PPZ.BATCH.SUSPENSE.NUMBER VSAM files used for inquiry during the nightly batch cycle VSAMN.PPZ.DATA.ENTRY.INDEX VSAMN.PPZ.DATA.ENTRY.MASTER VSAMN.PPZ.INDEX VSAMN.PPZ.INDEX.AFMR VSAMN.PPZ.INDEX.AMFMR VSAMN.PPZ.MASTER VSAMN.PPZ.MASTER.AFMR VSAMN.PPZ.MASTER.AMFMR VSAMN.PPZ.QUOTE.INDEX VSAMN.PPZ.QUOTE.MASTER VSAMN.PPZ.QUOTE.PRINT.INDEX VSAMN.PPZ.QUOTE.PRINT.MASTER VSAMN.PPZ.RECYCLE.ERROR | Yes | Mainframe Package Control | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | Mike Hansen | Scott Grau | Michael Martin / Angie Pike |  |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
921 | Mainframe Farm | In Progress - Planning | 2026-12-31 | Mainframe Farm | Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Policy processing system for Farm policies | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | VSAM policy,quote and rate data; database inflation factor, farm credit, RCE VSAM Files – Index - VSAMC.FMP.INDEX Policy - VSAMC.FMP.POLICY Quote - VSAMC.FMP.QUOTE.HOLD data entry - VSAMC.FMP.DATA.ENTRY quote print - VSAMC.FMP.QUOTE.PRINT Worksheet - VSAMC.FMP.TEMP.WRKSHEET.FILE accounting/distribution - VSAM1.FMP.ACCTDIST rate data - VSAMC.FMP.RATES DB2 Tables – FB2T0070_RES_INFL_FCTR (Inflation Factors) FB2T0050_CRDT_INFO (Farm Credit) FB2T0030_CHS_DIVD (Farm Dividend) FB2T0300_RCE_GENERAL(RCE) FB2T0310_RCE_STRUCTURE(RCE) FB2T0320_RCE_COMPONENT(RCE) Tape Files - AID01.FMP.FINAL.YTD.PURGE AID01.FMP.YTD.PURGE AID01.FMP.MTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules | Yes | Mainframe Farm (WINS) | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | Mark VanWyk | Scott Grau | Michael Martin / Angie Pike | Weekly farm bureau validation and annual farm dividends are processing CLT data. |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
923 | Mainframe Business Owners (SBO) | In Progress - Planning | 2026-12-31 | Mainframe Business Owners (SBO) | Prasad Penchala | Set up meeting with Kristi on aligning on next steps and status. | Policy Processing System for Commercial Business Owners policies. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | VSAM policy and quote data in the index, master, data entry and quoue hold files. Also VSAM rates, class code and the accounting/distribution files VSAM files – Index - VSAMC.SBO.INDEX Master - VSAMC.SBO.MASTER Data entry - VSAMC.SBO.DATA.ENTRY class codes -VSAMC.SBO.LIVE.CLASS rates - VSAMC.SBO.LIVE.RATE Renewal index - VSAMC.SBO.DATA.ENTRY.RENEW Prior Index - VSAMC.SBO.PRIOR.INDEX Quotes - VSAMC.SBO.QUOTE.HOLD Quote print - VSAMC.SBO.QUOTE.PRINT Account Dist - VSAM1.SBO.ACCTDIST BOP Index after FMR - VSAM1.SBO.INDEX.AFMR BOP Master after FMR - VSAM1.SBO.MASTER.AFMR DB2 Tables – Businessowners does not own any DB2 table PPH_STATE_ZIP_INFLT_FCTR – State Zip Code Tape Files - AID01.SBO.FINAL.YTD.* AID01.SBO.YTD.* | Yes | Mainframe Business Owners (SBO) | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Marshall & Swift, Property rates, Blackbox | Patty Stump | Scott Grau | Michael Martin / Angie Pike | 1/27/23 From Jen Reed; BOP and BA ISO feeds. When those policies finally roll off legacy the current ISO feeds need to be adjusted to follow the ETL process defined for all other LOB's coming thru Policy Center. Mike Hanson (Sunset team) currently managed these processes today. |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
924 | Mainframe Policy Entry | In Progress - Planning | 2026-12-31 | Mainframe Policy Entry | Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Policy Processing System for Inland Marine, Crime, Commercial Umbrella, and Personal Umbrella policies | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT & PLT | Transformation: CLT & PLT | Yes | VSAM policy and quote data on our index, master, MOT and data entry files. VSAM Renewal index, master, MOT and data entry. VSAM files – Index (Policies and Quotes) - VSAM1.PCS.INDEX Master (Policies and Quotes) - VSAM1.PCS.POLICY Data entry (trigger record only for NB/REN)- VSAM1.PCS.DATA.ENTRY MOT (trigger record only for changes) - VSAM1.PCS.MOT class codes , forms-VSAM1.PCS.TABLE rates - no rate file for Policy Entry Renewal index - VSAM1.PCS.RENEW.INDEX Renewal Master - VSAMC.PCS.RENEW.POLICY Renewal Data Entry - VSAM1.PCS.RENEW.DATA.ENTRY DB2 Tables – Policy Entry does not own any DB2 table Tape Files - AID01.PCS.FINAL.YTD.PURGE Hercules - Data in Index and Master file is ingested to Hercules" | Yes | Mainframe Policy Entry | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | PAK, Claims, FLEX billing, BAM billing, Agent Master file, Forms System | Rhonda Giedd | Scott Grau | Michael Martin / Angie Pike |  |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
926 | Mainframe Workers Comp | In Progress - Planning | 2026-12-31 | Mainframe Workers Comp | Sunset-PCIO | Set up meeting with Kristi on aligning on next steps and status. | Policy processing systems for Workers Compensation policies. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | VSAM files - index, master, data entry, MOT, class code descriptions, rates, unit stat, dividends, renewal index/master/data entry VSAM files – Index - VSAMC.WCS.INDEX Master - VSAMC.WCS.MASTER Data entry - VSAMC.WCS.DATA.ENTRY MOT - VSAMC.WCS.MOT class code descriptions - VSAMC.WCS.DESC rates - VSAMC.WCS.RATE.ENTRY, VSAMC.WCS.RATES unit stat - VSAMC.WCS.US.MASTER dividends - VSAMC.WCS.PARPLAN.MASTER Renewal index - VSAMC.WCS.RENEW.INDEX, VSAMC.WCS.INDEX.WORK Renewal master - VSAMC.WCS.RENEW.MASTER, VSAMC.WCS.INDEX.MASTER Renewal data entry - VSAMC.WCS.RENEW.DATA.ENTRY, VSAMC.WCS.DATA.ENTRY.WORK Endorsements - VSAM1.WCS.END.EDITS DB2 Tables – Work comp does not own any DB2 tables Tape Files - AID01.WCS.FINAL.YTD.PURGE AID01.WCS.YTD.PURGE.HISTORY Hercules - Data in Index and Master file is ingested to Hercules | Yes | Mainframe Workers Comp | Archive | Indefinite | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Glacier) | 912 Mainframe Package Control | CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | Rhonda Giedd | Scott Grau | Michael Martin / Angie Pike | Unit Stat and Dividends are processing CLT data as well |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | After 7/31/26 | [5 empty] | Sunset |  | DM | TBD
940 | Allied Endorsements | Not Started | 2027-02-28 | Allied Endorsements |  | 10/30-Potential needed to keep, Lisa and team going to do more research on it | Repository of policy endorsements available to Service Advantage policy systems, billing and TCS 1/11/25: John indicated decom 1/16/25: any MF DM would be using this to print. Need to find out if it is used in Billing. If it is tied to Billing it would be a go-forward. | Schillaci-Beane, Lisa |  | Yes |  | Production | Application | TBD | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes - VSAM | Endorsements by prefix/state with the start/end date of use. | Yes |  | Archive | Indefinite | Support, Endorsement | No | Yes | No | Yes | S3 | 912 Mainframe Package Control | SA/PCIO, TADA jobs, DR jobs, UWSW0082 - Rerate running every week. | K Hatch | D Mardis |  | 04/26/2021 - ED51 I've heard Agent Center has a tab (Reference Connect) that lets the agent see what forms "could have been" on the policy. This consists of a list from the Endorsement system. I see a disclaimor now on AC to look somewhere else. Is that good enough to allow us to retire as long as Bonds stops running on the MF? Didn't find files in JCL for Bonds 5/5 Confirm with K Newhall, concern that we wouldn't know what should have been on the policy, or could reference connect tell us that. |  | PCIO | Document Images | AWS S3 | Inquiry UI, API, Data Extract Process | TBD | [7 empty] | DM | TBD
1208 | Alpha Search | In Progress - Planning | 2026-12-31 | Alpha Search | Sravanthi Vanam | 10/30- Lisa and team doing further research John O’Neal confirmed that while there was no activity last week, the team’s new Sprint begins on September 11, and Alpha Search will be prioritized for Planning Guide development. • Planning cards have been created for all three applications, and work is expected to begin with Alpha Search first. 9/19/2025 - Will create the Planning Guide, but no lobor tied to it. Will shut off with PCIO | Maintains customer information by policy at the customer name and address level 01/11/25: John indcated decom 01/16/25: it could happen now, just a few users left 04/02/25: all remaining updates on status can be found on the Planner board. LInk is in the 2nd to last column in this spreadsheet. 07/16/25: need to verify if Claims is using this to search for policies. | Schillaci-Beane, Lisa |  | No |  | Production | Application |  | 1 | [11 empty] | Early Opportunity | Transformation:CLT | Tranformation: CLT | No | Customer data | No |  | Discard | N/A | Support | No | Yes | No | No | N/A | 912 Mainframe Package Control | Claims, PCIO, SA, Bonds | K Hatch | D Mardis |  | AS51; similar to Pathway, only shows PCIO, continued usage until policy system retired, need to understand user groups that may still want to see historical info Archival length can be decided | Maintains customer information by policy at the customer name and address level. | PCIO | Misc. Data and Rules | N/A | N/A | TBD | [7 empty] | DM |  | https://planner.cloud.microsoft/webui/v1/plan/1k8FS6ivX0-5Af2zg0vx_2QAHmhP/view/board/task/BAIf77HArUCO_77BpT6TBGQAClD7?tid=22140e4c-d390-45c2-b297-a26c516dc461 |  | 7/16 - Received list of users from J O'Neal | Review feedback from "frequent" recent users. Pending Plan Guide from John O'Neal. Confirm dependencies and archive information is incorporated in Plan Guide | Asked John O'Neal who is verifying claims use. Limited use. Sent to request for feedback to: Valenta, Jamie; Retzlaff, Duke J; Borton, Jeff; Gdowski, Mark L; Schilling, Mindy M; Smith, Paul A; Flor, Tim D | Sent request to users 8/11. Due 8/20. T Flor indicates high need to retain
1214 | Error Message | Not Started | 2026-12-31 | Error Message |  | 11/092025 - LSB - reviewing Decom for on-line and need final review of 10/30- Lisa and Team doing more research on it | Maintains a VSAM based common message file for the Service Avantage policy systems. The policy system requests a type of message and gets back a specific error correctly worded. 03/14/25: APRM indicates retirement 12/31/26; follow up with John to align on needing to add this to our decom list. 03/14/25: John approved this to be added to decom list. | Schillaci-Beane, Lisa |  | No |  | Production | Application | N/A | 1 | [11 empty] | Go Forward | Go Forward | Go Forward | No |  | No |  | N/A | N/A | Support |  |  |  |  | N/A | [11 empty] | N/A | [7 empty] | DM
1220 | Policy Reload | Not Started | 2026-12-31 | Policy Reload |  | 11/14/2025 - used by Flex (go forward app) to retrieve purged billing accounts (look to move into Flex) 11/13/25 - AP - Moved back to Decomm & Discard. Added back to WBS? Needs additional dev before discard. 11/09/2025 - LSB - will evaluate for other options for data loads in Flex. Not a big rock. **PCIO & P&C - uses this. Needed for litigation and need capability to print. 10/30- Lisa and Team do more research Policy Reload – Decommission Planning Update Progress Summary • Policy Reload has been identified as part of the early decommissioning track, currently targeted for March 31, 2026. • John O’Neal confirmed ownership of the application and acknowledged it is included in the decommission planning sheet. • As of the latest update, no active work has started on Policy Reload, but it is expected to be addressed in upcoming planning cycles. • The application will be considered alongside other early decommission candidates such as Alpha Search, Policy Expiration, and Microfilm Indexing, with prioritization based on team capacity and dependency analysis. Next Steps • John to initiate Planning Guide development for Policy Reload in alignment with the early decommission timeline. • Evaluate system dependencies and business impact during planning to confirm feasibility of the March 2026 target. • Coordinate with relevant stakeholders to validate assumptions and identify any retention or integration requirements. | Central point for customers to request a policy to be reloaded from back up files onto online policy systems. 1/6/2020 This would no longer be used after CLT, the archiving strategy will still be needed but not using MF 1/11/25: John indcated decom 1/16/25: we would decom and replace with records retention tool. 9/19/2025 - This will need to go with PCIO | Schillaci-Beane, Lisa |  | Yes |  | Production | Application | TBD | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | No | Used to notify policy admin systems to reload a policy from backup tapes | No |  | Archive | Transfer to Flex | Support | N/A | N/A | N/A | N/A | N/A | 912 Mainframe Package Control | PCIO, SA | K Hatch | D Mardis |  | Solution to retire is in flight, different/new application would be created to perform the reload for PCIO, HV, CLT |  | PCIO | Decom and Discard | N/A |  | 2026-07-15 | [7 empty] | DM
1418 | Policy Expirations | Not Started | 2026-12-31 | Policy Expirations |  | 10/30- Lisa and team going to research-Is Bonds still tied to this? Should this come off Decom list? Policy Expiration – Decommission Planning Update Policy Expiration is a legacy application tied to the PCIO platform. While no activity was reported as of mid-September, the application is part of the planning card set and is expected to follow the PCIO decommissioning timeline. Recent discussions confirm that the application is still in use and cannot be decommissioned until PCIO-related renewals are complete. Progress Summary Lisa Schillaci-Beane and John O’Neal confirmed the application is still active and required. Decommissioning cannot proceed until PCIO renewals are complete. Next Steps Confirm PCIO Shutdown Timeline Validate renewal completion dates and final shutdown schedule. Ensure Policy Expiration decommissioning aligns with PCIO dependencies. Update Planning Guide Reflect dependency on PCIO and revised decommissioning timeline. Include milestone tracking for renewals and shutdown readiness. | Process expiring policies. EXP on a monthly basis(end of month processing(EOM)) selects policies that are 105 days or less from expiring and generates reports such as NON-RENEWLs list, EXPIRATION list, etc. EXP also creates a monthly file of expiring policies that gets processed daily and any policy that is 73 days or less from expiring is written to EFILE and EFILE is sent to Columbus for further processing. 1/6/2020 Dawn was going to check impacts to Bonds 1/11/25: John indicates Go Forward until BONDS move off MF 1/16/25: Need to follow up with E&S on whether they are using the output of this. 03/14/25: APRM indicates retirement 12/31/26; follow up with John to align on needing to add this to our decom list. 03/14/25: John approved this to be added to decom list. 9/19-2025 - Is Bonds still tied to this? Should this come off Decom list? | Schillaci-Beane, Lisa |  | No |  | Production | Application |  | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | No | Policies coming up for renewal 11/09/2025 - will review opportunity to decommission earlier, but need time to review. Not a big rock | Yes |  | Discard | N/A | Discard | N/A | N/A | N/A | N/A | N/A | 912 Mainframe Package Control | PCIO, eFile | K Hatch | D Mardis |  | 4/26/2021 - Need to verify that Bonds does not use Expirations, need to verify. Nothing new once PCIO is moved. KA has steps with process to review/work these policies |  | PCIO | Decom and Discard | Decom and Discard | Decom and Discard | 2023-11-01 | [7 empty] | DM
1660 | Commercial Umbrella | In Progress - Planning | 2026-05-31 | Commercial Umbrella | Bill Mardis, Chaos Monkeys | 1/20-Planning guide started. Bill reached out to data warehouse. Sounds like they do have the data in data warehouse | online calculator for Commercial Umbrella policies. This application is being used by Commercial Underwriters in PCIO Exclusive and Independent.(APRM says plan to retire 2024) | Esposito, Colleen | Bill Mardis | Yes |  | Production | Application | TBD | 1 | [11 empty] | Review | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Cloud SQL Server database COMUDB has 30 tables that are a combination of Umbrella quote data entered in the tool along with tables that contain app rules/class codes/rates 1/14-Preliminary discussion started,its calculator | Yes |  | Archive | MAX 5 years for quotes, need to determine | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Gacier) | N/A | N/A | Bill Mardis | Mike Waytenick | Cece Moore? Or other MM rep | Need to determine length and business need for retention |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | TBD |  |  |  | No | SQL Server | Chaos Monkeys |  | DM | TBD |  |  | 8/18 - Received users from B Mardis(18 users) | Reach out to users: - Is this required until all policies are migrated/expired on legacy?
2887 | Commercial Rate Step Maintenance | In Progress - Planning | 2026-03-31 | Commercial Rate Step Maintenance | Bill Mardis, Sunset-PCIO/Chaos Monkeys | 1/20- Bill met with, Angie and Colleen this week. Angie went back to the business, had some conversations. Right now target turning off the web app in February. | 9/15/2025 - This is currently focused on the Web app only. The DB2 databases are still needed. The tables will be included with PCIO mainfram application. This is the Rate Step Maintenance Application used by Commercial to maintain rate Steps for BOP, BA, & Farm. Also, this project may go with a Minor Release sometime after the PC4.0-08 Release. (APRM says plan to retire 2024) 04/02/25: all remaining updates on status can be found on the Planner board. LInk is in the 2nd to last column in this spreadsheet. | Esposito, Colleen | Bill Mardis | No |  | Production | IT Service | TBD | 1 | [11 empty] | Review | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Updates/reads mainframe DB2 tables that are ultimately used by PCIO mainframe policy systems PPHDP001 PPH_COBOL_STEP PPH_COBOL_STEP_CRITR PPH_CVRG_DM PPH_ITEM_GRP_DM PPH_ITEM_MAPPING_DM PPH_ORG_DM PPH_PRODUCT_DM PPH_RT_STEP PPH_RT_STEP_CRITR PPH_STATE_DM PPH_SUBPRODUCT_DM PPH_UNIT_DM PPH_VALID_CVRG_DM PPH_VALID_PREFX_DM PPH_WKSHT_DSC_DM 1/14-Turn of Web App in second week of Feb | Yes | MF PCIO - PAK | N/A | Data Retention will be done as per PCIO Mainframe , getting rid of UI | Support | No | No | No | Yes | Glacier | 912 Mainframe Package Control | N/A | Bill Mardis | Mike Waytenick | Cece Moore? Or other MM rep | Do PCIO policy systems actually own database? Not needed once policies off the system. Archive rate steps, need to determine how long after last legacy policy we keep this before decommission the utility 11/10/21 This would be considered configuration/source code and we would folllow the source code retention requirement |  | PCIO | Misc. Data and Rules | Decom and Discard | None/Manual, Data Extract Process | TBD | [5 empty] | Chaos Monkeys |  | DM |  | https://planner.cloud.microsoft/webui/v1/plan/1k8FS6ivX0-5Af2zg0vx_2QAHmhP/view/board/task/FvrNUqXWwUOZde0IjrVmVmQAMZHp?tid=22140e4c-d390-45c2-b297-a26c516dc461 |  |  | Pending plan guide and user list from B Mardis.
2918 | CCRF Agent Center | Not Started | 2026-06-30 | CCRF Agent Center |  | 1/20- Bill is going to do more research | Allows agents to submit Commercial Change Requests via the Agent Center. 01/11/25: Jamie indicates decom. 01/13/25: Per Bill Mardis… CCRF Agent Center (2918) is one that will eventually get turned off. CCRF is used for submitting amendment details for PCIO accounts. Assume it will last a little longer than CIQ, but go away at some point as PCIO accounts continue to dwindle. Volume does continue to decrease every month in CCRF. Probably a case later in 2025 to look at the usage and determine with the business if enough is coming through it to warrant continuing to support. - Amendments submitted through CCRF o December 2024 - 49 o November 2024 - 86 o October 2024 - 81 o September 2024 - 109 o August 2024 - 174 o July 2024 - 192 o June 2024 - 244 o May 2024 - 321 o April 2024 - 365 o March 2024 - 361 o February 2024 – 395 o January 2024 – 543 04/02/25: all remaining updates on status can be found on the Planner board. LInk is in the 2nd to last column in this spreadsheet. | Esposito, Colleen |  |  |  | Production | Application | TBD | 1 | [11 empty] | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Cloud SQL Server Database PH4DD001 - 29 tables starting with PH4* that contain amendment details keyed into the app. When user submits an amendment, the details are put in a PDF and sent to processing via eFile. There is no direct connection between the data entered/stored in CCRF with the PCIO mainframe policy systems. All data is manually keyed in CCRF and then manually keyed in PCIO mainframe. | No | CCRF Agent Center | Discard | N/A | Policy | N/A | N/A | N/A | N/A | N/A | 912 Mainframe Package Control | N/A | Bill Mardis | Mike Waytenick | Katherine H?? | Receives amendments for commercial policies. Input data for amendments and then sent back to policy systems when applies (make sure we communicate to agents plenty of time when shut down, stay up as long as policy apps are running) |  | PCIO | Decom and Discard | Decom and Discard | Decom and Discard | TBD | [7 empty] | DM | TBD | https://planner.cloud.microsoft/webui/v1/plan/1k8FS6ivX0-5Af2zg0vx_2QAHmhP/view/board/task/QtEKJWXvskSOPIXcSprlqWQAIYzT?tid=22140e4c-d390-45c2-b297-a26c516dc461
4245 | Commercial Mainframe COI | In Progress - Planning | 2026-12-31 | Commercial Mainframe COI | Bill Mardis | Set up meeting with Kristi on aligning on next steps and status. | Commercial Mainframe COI processing/printing. 12/19: Per Bill...The description in ServiceNow is wrong, it isn't connected to CIQ. It is a mainframe interface used by COI web app (3065, owned by Jamie). From the web app, users can say they want to start a certificate of insurance based on existing policies. When this happens, the web app sends a request containing an account number to this mainframe COI piece. The mainframe piece then sees if the PAK exists on PCIO mainframe, consolidates policy data from the various PCIO mainframe systems, and sends back an XML response of data used to prefill information for creating certificates of insurance. Guessing the mainframe interface has to continue to run until all of the policies are off of PCIO mainframe or a business decision was made that the COI web app no longer needs to support creating COIs based on PCIO policy data. I don't believe there is any unique data stores on the mainframe side for COI, think 4245 is just an interface that pulls together data from the PCIO policy systems and sends an XML response of relevant information. (Seeing comments in the spreadsheet asking about PC COI. The web app (3065) does support prefilling data for a certificate for both PCIO and PolicyCenter. If the account exists on PolicyCenter, that data is obtained from a different service on the PC side. So web app (3065) is go forward app because it pulls in PolicyCenter data, but mainframe interface (4245) is a candidate for being decommissioned whenever the need goes away for certificates prefilled with PCIO policy data.) | Esposito, Colleen |  |  |  | Production | Infrastructure Service | TBD | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | No | Cert of Insurance from Agent Center, still utilized. Is this used for PC COI? Should not be on the decom list, need to verify it's the same tool used for PC because it needs to remain. Request comes from Agent Center COI | No | MF PCIO - PAK | N/A | N/A | Support | Yes | No | Yes | No | N/A | 912 Mainframe Package Control | N/A | Mike Hansen | Scott Grau | Cece Moore? | Moved from June to Matt's list…Matt has expertise, but still in June's name |  | PCIO | TBD Pending Research | N/A | N/A | TBD | [5 empty] | Sunset |  | DM
4260 | Commercial Renewal Reporting DB | Not Started | 2026-12-31 | Commercial Renewal Reporting DB |  | 10/30- Lisa and team will do more research, this may come off DECOM list Commercial Renewal Reporting DB – Progress The application is tied to renewal-related data, and its relationship to Commercial Underwriting rules is being clarified. Initial target for decommissioning is Q1 2026, pending validation of dependencies and business impact. Next Steps: Planning Guide Development: Begin Planning Guide work to clarify system dependencies and validate assumptions. Business Impact Assessment: Evaluate feasibility of early decommissioning based on business needs and system interdependencies. Documentation Alignment: Ensure Planning Guide reflects the distinction between Commercial Underwriting rules and renewal info database. Stakeholder Engagement: Engage business and compliance teams to validate retention requirements and confirm decommissioning readiness. | PCIO - Stores the U/W renewal rules and statistics to report against it. The database we own is for business driven Brio Reports measuring policies that Renew without being touched by underwriters. It also measures renewal errors that are triggering Underwriter activities to determine if the renewal rules need to be adjusted to meet the business needs. There are also reports that measure regional office renewal volume and premium. 1/11/25: John indcated decom 1/16/25: only being used for PCIO data. Once we are done migration, we could potentially shut down. We need to review the reports first if we want to do earlier, otherwise we shut down with PCIO. 11/09/25 - LSB - needed for PCIO | Schillaci-Beane, Lisa |  | No |  | Production | Component |  | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes | Renewal data from PCIO Automatic Renewal process | No |  | N/A | N/A | Policy | N/A | N/A | N/A | N/A | N/A | 912 Mainframe Package Control |  | K Hatch | D Mardis |  | Dawn Thompson ? |  | PCIO | Decom and Discard | Decom and Discard | Decom and Discard | 2023-11-01 | [7 empty] | DM
4261 | Commercial Underwriting DB | Not Started | 2026-12-31 | Commercial Underwriting DB |  | 10/30- Lisa and team doing more research Commercial Underwriting DB – Progress Summary The application stores renewal rules, which differ from the renewal info database used elsewhere. This distinction will be clarified during Planning Guide development. Initial decommissioning target is Q1 2026, pending validation of dependencies and business impact. Next Steps: Planning Guide Development: Begin Planning Guide work to clarify system dependencies and validate assumptions. Business Impact Assessment: Evaluate feasibility of early decommissioning based on business needs and system interdependencies. Retention Review: Confirm whether any data retention requirements apply to renewal rules stored in the database. Stakeholder Engagement: Use Planning Guide to engage stakeholders and validate readiness for decommissioning. | Marketing/Pricing/Underwriting Database - Monitors IA Agents productivity and IA Agents Quote to Issue Premium Variations. Owned by Underwriting. Web front-end that is owned by CIQ. Also produces and stores reports for Marketing, Pricing and Underwriting. Includes several BRIO queries. Underwriting owns BRIO queries, and Vicky Duke's area executes the BRIO queries. 1/11/25: John indcated decom 1/16/26: not sure there is anything CIQ related. We would shut down with PCIO. | Schillaci-Beane, Lisa |  | No |  | Production | Component |  | 1 | [11 empty] | Transformation | Transformation: CLT | Transformation: CLT | Yes |  | No |  | Discard | N/A | UW |  |  |  |  | N/A | 912 Mainframe Package Control |  | K Hatch | D Mardis |  | Business Insights or Underwriting? Alicia Colins, Rob Chenowith |  | PCIO | TBD Pending Research | N/A | N/A | 2023-11-01 | [7 empty] | DM
5281 | HV-Accounts Receivable | In Progress - Planning | 2027-04-01 | HV Billing | Colleen Esposito | 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | Accounts Receivable Also known as Agent Balance and Reconciliation Recieves feeds from Billing System and PNC lockbox | Esposito, Colleen |  | Yes |  | Production | Application |  | 1 | Orphan | Policy Platform | 26959 | 29402.4956 | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 43600.5816 | 73KA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | DB2 tables - contain accounts receivable data. prod.ARCV_STMNT_ELMNT prod.ARCV_ACCT_STMNT | Yes | 5281 HV-Accounts Receivable | Archive | FMA170 – Accounting Records -7 years | Financial | No | Yes | No | No | Glacier | 5296 HV Legacy Billing Systems | 5296 HV-Legacy Billing Systems | Mark Holsopple | Scott Grau | Day Flanagan, Ricki | Accounting team inputs data into the system, then data is sent to NW GL accounting system. Need better understanding of screens, who uses and how |  | HV CL |  | AWS Glacier | RRC | TBD |  |  | 43600.5816 | No |  | Sunset |  | HV
5282 | HV-Agency Bill Account Current | In Progress - Planning | 2027-04-01 | HV Billing | Colleen Esposito | 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | This application is used to bill agents (monthly) and track their balances due the company. | Esposito, Colleen |  |  |  | Production | Application |  | 1 | Orphan | Policy Platform | 0 | 29402.4956 | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 43600.5816 | 73KA21001 | Transformation | Transformation: CLT | Transformation: CLT | No | N/A | N/A | 5296 HV-Legacy Billing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5296 HV Legacy Billing Systems | 5281 HV- Accounts Receivable | Mark Holsopple | Scott Grau | Ricki Day | Guidewire will not replace HV Legacy, all old policies and billing will need to fall off as move to CLT |  | HV CL |  | N/A | N/A | TBD |  |  | 43600.5816 |  |  | Sunset |  | HV
5283 | HV-Agency Systems | In Progress - Planning | 2027-04-01 |  | Frank Unger | 10/30- Joy and Colleen are working on the requirements 11/4- Frank to provide some samples to Joy 11/10 - INS1020 – Agency Administration - Active + 7 years Set up meeting with Kristi on aligning on next steps and status. | Includes Agency Performance, Agency Commissions, Agency Master, Expiration, and Mainframe Portion of Agency Download | Esposito, Colleen |  | Yes |  | Production | Application |  | 1 | Transformation | Agency | 242631 | 147012.4779 | Transformation | Transformation: PLT & CLT | Unplanned | Unplanned | Unplanned | 174402.3265 | 73KA21001 | Unplanned | Unplanned | Unplanned | Yes | Harleysville legacy system including Agency Master, Agency Performance, and Agency Download batch processing and CICS. VSAM files Agency Master file: CORP00PV.AGCY.NEW.ADSK..C Master file contains all agency info including appointments Agency Performance: CORP00PV.AGCY.PERFORM.C HV agency data is fed over to AMF and DPIM | Yes | 5283 HV Agency Systems | Archive | INS1020 – Agency Administration - Active + 7 years | Producer/Agency |  |  |  |  | Glacier | 5479 HV AQS | all HV systems | Rachael Wilford | Scott Grau | Christina Ledbedder | Is all the same info fed to other systems so that this data is no longer needed? This has a lot of info related to agent activity. Need to confirm with business stakeholders what access and for what reason it would be needed in the future |  | HV CL | TBD Pending Research | AWS Glacier | RRC |  |  |  | 174402.3265 |  |  | Sunset |  | HV
5285 | HV-CCMS & Score | In Progress - Planning | 2027-04-01 | MF Doc |  | 10/30- Colleen to review and see accelerated timelines Set up meeting with Kristi on aligning on next steps and status. | Used for assignment of policy numbers for manual policies and to link them in the Insured Account Database. In addition, if any of these policies are brought into automation at renewal, CCMS would be used to set up the renewal conversion. | Esposito, Colleen |  |  |  | Production | Application |  | 1 | Transformation | CLT | 26959 | 29402.4956 | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 43600.5816 | 73KA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Vsam - Policy number assignment for manual policies COMM00PV.CCMS.MASTER.C | N/A | 5285-HV-CCMS & Score | Discard | NA | Support | No | No | No | N/A | N/A | 5303 HV Stat | HV-Midstream Stat | Cindy Budka | Scott Grau |  | Has a UI component, suggestion we check and see if anyone is using it. |  | HV Leg Bill STAT | Decom and Discard | Decom and Discard | Decom and Discard | 2024-10-01 |  |  | 43600.5816 |  |  | Sunset |  | HV
5290 | HV-Direct Bill Commission | In Progress - Planning | 2027-04-01 | HV Billing | Colleen Esposito | 11/6: 7 year retention requirement - FMA170 – Accounting Records 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | Monthly application that creates agent's commission payments for Direct Bill policies. | Esposito, Colleen |  | Yes |  | Production | Application |  | 1 | Transformation | Agency | 26959 | 117609.9823 | Early Opportunity | 2019 Review | Early Opportunity | 2019 Review | 2019 Review | 174402.3265 | 73KA21001 | Early Opportunity | 2019 Review | 2019 Review | No | agent commissions, pull data from stat and accounting records and feed to SAP, data returned and do check print, processing, commissions payments, check statements FMA170 – Accounting Records | N/A | N/A | Archive | FMA170 – Accounting Records -7 years | Financial | N/A | N/A | N/A | N/A | Glacier | 5303 HV Stat | HV-Stat | Mark Holsopple | Scott Grau | Ricki Day | pass through only | Monthly application that creates agent's commission payments for Direct Bill policies. | HV Leg Bill STAT | Decom and Discard | AWS Glacier | RRC | 2024-10-01 |  |  | 174402.3265 |  |  | Sunset |  | HV
5296 | HV-Legacy Billing Systems | In Progress - Planning | 2027-04-01 | HV Billing | Colleen Esposito | 11/6: 7 year retention requirement - FMA170 – Accounting Records 10/30- Joy and Colleen are working on the requirements Set up meeting with Kristi on aligning on next steps and status. | The Agency bill system supports the monthly billing and collection from each agent on a net premium basis (premium less commission). The agency bill premiums are for accounts of $50,000 or more. The system provides a history of collection activity and provides detailed Information on all outstanding unpaid premium by agent.The Direct Bill system supports the billing and collection directly from the customer, of P&C insurance premium written by Harleysville Insurance operations. | Esposito, Colleen |  | Yes |  | Production | Application |  | 1 | Orphan | Policy Platform | 188713 | 176414.9735 | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 348804.653 | 73KA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Accounts/Policies/Cash transactions/Audit trail, VSAM BILL00PV.DRCT.B1.MASTER.C BILL00PV.DRCT.B2.MASTER.C BILL00PV.DRCT.B3.MASTER.C BILL00PV.DRCT.B4.MASTER.C BILL00PV.DRCT.ACCT.AUDIT.TRAIL.C BILL00PV.DRCT.AUDIT.TRAIL.C FMA170 – Accounting Records Images stored in IR and will go to RRC with ImageRight decom | Yes | 5296 HV-Legacy Billing | Archive | FMA170 – Accounting Records -7 years | Financial | No | Yes | No | Yes | Glacier | 5296 HV Legacy Billing Systems | Policy Systems Agent Portal | Harry Hermann | Scott Grau | Boyer, Tricia <BOYERT3@nationwide.com>; Mc Clain, Tracy L <tracy.mcclain@nationwide.com>; Mixdorf, Matthew C <MIXDORM@nationwide.com>Kristen Troxel | Not sure billing info is indefinite, need to confirm. |  | HV Leg Bill STAT | Billing, Check Data | AWS Glacier | RRC | TBD |  |  | 348804.653 |  |  | Sunset |  | HV
5306 | HV-Personal Lines Legacy | In Progress - Planning | 2027-04-01 | MF Doc |  | 11/6: VSAM files are needed for HV Claims 10/30- Colleen do more research on it, may be needed for claims Set up meeting with Kristi on aligning on next steps and status. | Policy adminstration for Personal lines Homeowners, Automobile, Blanket Excess, Inland Marine, and Shipmate on the mainframe | Esposito, Colleen |  | Yes |  | Production | Application | 2027-04-01 | 1 | Transformation | PLT | 107836 | 117609.9823 | Transformation | Transformation: PLT | Transformation | Transformation: PLT | Transformation: PLT | 174402.3265 | 73EF21001 | Transformation | Transformation: PLT | Transformation: PLT | Yes | Personal lines policy information for Harleysville including Auto, Home, Dwelling and Unbrella lines of businesss on the mainframe. There is a database for Auto, Home, and Umbrella PLAU00PV.AUTO.POL.CTRL.PROD.MSTR.C PLAU00PV.AUTO.POL.DTL1.MSTR.C PLAU00PV.AUTO.POL.DTL2.MSTR.C PLAU00PV.AUTO.POL.DTL3.MSTR.C PLAU00PV.AUTO.POL.DTL4.MSTR.C PLPP00PV.HOME.CONTROL.MSTR.C PLPP00PV.HOME.POL.DTL.MSTR.C PLPP00PV.HOME.HO61.MSTR.C PLPP00PV.DWEL.POL.DTL.MSTR.C PLPP00PV.SHIP.POL.DTL.MSTR.C PLPP00PV.BLEX.POL.DTL.MSTR.C | Yes | HV-Personal Lines Legacy | Archive | POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Policy | Yes | Yes | Yes | Yes | Data Lakehouse | Mainframe Retirement Holistically |  | Boris Shif | Scott Grau | Amy Olmstead | There are about 1100 policies left in this system. All Auto have been migrated. Only a few Homeowners left. Dwelling will begin non renewal process in June. Umbrella migration is in progress. Shipmate will be non-renewed starting later in 2021. |  | HV PL | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | TBD | 1012681 |  | 174402.3265 | Yes - HV-Oden (terminate 4/25) | MF | Accenture |  | HV | TBD
5307 | HV-Commercial Lines Legacy | In Progress - Planning | 2027-04-01 | MF Doc |  | 11/6: VSAM files are needed for HV Claims 10/30- Colleen do more research on it, may be needed for claims Set up meeting with Kristi on aligning on next steps and status. | 10/31: no active policies since 2015. App will be decom with MF. | Esposito, Colleen |  | Yes |  | Production | Application | 2027-04-01 | 1 | Retired | Retired | 0 | 0 | Retired | Retired | Retired | Retired | Retired | 0 | 73KD21001 | Retired | Retired | Retired | Yes | 5/17/22 from Terry; There is VSAM data associated with this application which should still be in existence for inquiry purposes. Colleen and I discussed this app last night and this data should be made available in Alcides as it may be required for future Claims reporting. There should be inquiry functionality supporting this application with no transactional capability. Cindy Budka is knowledgeable on this app and would be able to speak to file layouts/content. COMM00PV.CAUT.CA.CONTROL.MASTER.C COMM00PV.CAUT.CA.DETAIL.MASTER.C COMM00PV.CAUT.PU.DETAIL.MASTER.C COMM00PV.WCOM.WC.CONTROL.MASTER.C COMM00PV.WCOM.WC.DETAIL.MASTER.C COMM00PV.WCOM.PU.DETAIL.MASTER.C COMM00PV.BEXC.BE.CONTROL.MASTER.C COMM00PV.BEXC.BE.DETAIL.MASTER.C COMM00PV.BEXC.PU.DETAIL.MASTER.C COMM00PV.MONO.CP.CONTROL.MASTER.C COMM00PV.MONO.CP.DETAIL.MASTER.C COMM00PV.MONO.GL.CONTROL.MASTER.C COMM00PV.MONO.GL.DETAIL.MASTER.C COMM00PV.MONO.BO.CB.CONTROL.MASTER.C COMM00PV.MONO.BO.CB.DETAIL.MASTER.C COMM00PV.MONO.PU.DETAIL.MASTER.C COMM00PV.MULT.IM.CONTROL.MASTER.C COMM00PV.MULT.IM.DETAIL.MASTER.C COMM00PV.MULT.MP.CONTROL.MASTER.C COMM00PV.MULT.MP.DETAIL.MASTER.C COMM00PV.MULT.CR.CONTROL.MASTER.C COMM00PV.MULT.CR.DETAIL.MASTER.C COMM00PV.MULT.PU.DETAIL.MASTER.C | Yes | HV-Commercial Lines Legacy | Archive | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Policy | Yes | Yes | Yes | Yes | Hybrid (data Lakehouse + Gacier) | Mainframe Retirement Holistically | HV-Commerial Lines Legacy | Boris Shif | Scott Grau | Angie Pike; Michael Martin |  |  | HV CL | Policy Data | P&C Data Lakehouse + AWS Glacier | Inquiry UI, API, Data Extract Process + RRC | TBD |  |  |  | No | MF | Sunset |  | HV | TBD
5308 | HV-Commercial Lines DMV | In Progress - Planning | 2027-04-01 | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | Used for reporting vehicle information to various state DMV agencies 4/19/21 Moved to Terry at Carolyn's request | Esposito, Colleen |  |  |  | Production | Utility | TBD | 1 | Transformation | CLT | 26959 | 29402.4956 | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 43600.5816 | 73KA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Feeds to/from Verisk - CL | No | 5307 - HV-Commercial Lines Legacy | Discard | N/A | Support | N/A | N/A | N/A | N/A | N/A | 5479 HV AQS |  | Tony Brnic, Sundar Elangovan Elangovan |  | Linda Brockney | reporting vehicle info via LexisNexis. Retain as needed with an active policy to report the vehicle info. Since for auto, could decom with last policy (no tail for WC data and reporting) |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | 2023-11-01 |  |  | 43600 |  |  | Chariots of Fire |  | HV | 2023-03-31
5309 | HV-Midstream Stat Creation | Not Started | 2027-04-01 | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | Creation of Accouting/Stat to be processed downstream systems | Esposito, Colleen |  |  |  | Production | Application |  | 1 | Transformation | CLT | 188713 | 176414.9735 | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 348804.653 | 73KA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | No | AQS / DCT are the source | No | N/A | N/A | N/A | Support | N/A | N/A | N/A | N/A | N/A | 5479 HV AQS | HV-AQS, HV-Claims, HV-Duckcreek, HV PL Legacy | B. Shif |  |  | Batch process, no database, as long as HV are processing transactions, this process will need to continue. Will stop after all HV transaction processing has stopped |  | HV CL | Decom and Discard | N/A | N/A | 2023-11-01 |  |  | 348804 |  |  |  |  | HV
5385 | HV-AccessWeb - UWRulesEngineWebApp | Not Started | 2026-12-31 | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business 10/30- Colleen do more research on it Set up meeting with Kristi on aligning on next steps and status. | User interface for accepting and responding to binding authority questions an rules. | Esposito, Colleen |  | Yes |  | Production | IT Service | 2026-05-15 | 1 | Transformation | CLT | 0 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 28921.5914 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Uses xml Binding Authority blobs for Questions and Answers. | Yes | HV-URE, HV-Quote, IADB | Archive | UND120 – Commercial Lines, Property, Casualty -Indefinite | UW | No | No | No | No | Glacier | 5479 HV AQS | HV-AQS | Greg Schreffler | Scott Grau | George Schirripa | Data is used for Binding Authority to analyze agents answering questions and determine if policy needs to be referrred or can be binding.UI to answer questions for rules service. 11/10 Archive the data and the source code together, but would not need an archive/retrieve UI to view this data (keep more than the 1 year) |  | HV CL | Misc. Data and Rules | AWS Glacier | RRC | 2023-11-01 |  |  | 28921.5914 | No |  |  |  | HV
5390 | HV-Audit Upload Manager | Not Started | 2026-12-31 | HV-ACE - Premium Audit | Mike Kelly |  | Audits discrepancies in policy premium caused by quote and billing date issues. | Esposito, Colleen |  |  |  | Production | Application | 2026-07-31 | 1 | Transformation | CLT | 183958 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 151087.957 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Database is the audit control file | No | AQS | Discard | N/A | Support | N/A | N/A | N/A | N/A | N/A | 5479 HV AQS | ACE Audit Upload, HV-AQS, Batch Cycle | Dan Croll | Bosheng Lin | Krystal Smith |  | De-comm w/ HV-AQS or earlier if business makes concessions to no longer process automateed audits for AQS policies | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | 151087 | No | win2012, SQL 2012 | Chariots of Fire |  | HV | TBD
5408 | HV-Renewal Automation | In Progress - Planning | 2026-06-30 | HV-Renewal Automation | Dan Croll | 1/20- Frank is doing more research | Renewal automation is a batch process (.net/sq.) that runs in the background on a nightly basis. The job gathers data from both legacy and AQS and flags 90 day expiration candidates for renewal. Some can issue automatically, others are flagged for manual intervention. Web Methods is the intermediary link between all the function. 03/05/26: 120 before July 2026 date, decom end of first quarter 2026 04/02/25: all remaining updates on status can be found on the Planner board. LInk is in the 2nd to last column in this spreadsheet. | Esposito, Colleen |  |  |  | Production | Component | 2026-03-31 | 1 | Transformation | CLT | 551875 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 285792.7313 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Renewal control db | No | AQS | Discard | N/A | Support | N/A | N/A | N/A | N/A | N/A | 5479 HV AQS | HV-AQS, Batch Cycle | Dan Croll | Bosheng Lin | Linda Brockney Amy Underwood |  | De-comm when last AQS policy has migrated to PC. | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 285792 | No | win 2019 SQL and Windows, batch | Chariots of Fire |  | HV | TBD | https://planner.cloud.microsoft/webui/v1/plan/1k8FS6ivX0-5Af2zg0vx_2QAHmhP/view/board/task/h6E2B58ckkqafBK2VR3N22QACD-u?tid=22140e4c-d390-45c2-b297-a26c516dc461 |  | 8/13/25 - There is no business user base for this. Scott G described it as a IT tool. | N/A? | N/A | 8/20 - Colleen assessing viability of early decomm. Lack of SME resource and minimal value to early decommsion may result in delay.
5413 | HV-Underwriting Rules Engine (URE) | Not Started | 2026-12-31 | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business 10/30- Colleen to do more research | The tool used to assign rules around potential customer's provided information. This rules engine will determine if the policy can be bindable, determining account-level renewal authority, determing applicable product, system and line of business.. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-05-15 | 1 | Transformation | CLT | 551875 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 531282.2625 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Stores Protocol data and uses xml blob saved for prior referrals generated.Quote and IADB db's used to populate Blaze and .net objects. | No | HV-URE, HV-Quote, IADB | Archive | UND120 – Commercial Lines, Property, Casualty -Indefinite | UW | No | Yes | No | No | Glacier | 5479 HV AQS | HV-AQS, HV-Agent Portal | Ron Posatko | Scott Grau | George Schirripa | Assortment of both rules and .net services to process Underwriting rules analyzation. Services consist of Market Segment, Account Authority - Renewals, System Determination, Underwriter type, Binding Authority - NewBusiness. Commercial only |  | HV CL | Misc. Data and Rules | AWS Glacier | RRC | N/A |  |  | 531282.2625 | FICO Contract (terminated 12/28/24) | Win2019, SQL 2019 |  |  | HV | TBD
5415 | HV-ACE - Premium Audit | Not Started | 2026-12-31 | HV-ACE - Premium Audit | Mike Kelly | 11/6: CL Premium audits falls under UND120 – Commercial Lines, Property, Casualty - indefinite 10/30- Colleen to do further research on this | Premium audit. Commercial policy so much for the year. Premium is estimated. Your premium should be or less or more. Feeds from policy systems | Esposito, Colleen |  | Yes |  | Production | Third Party Application | 2026-07-31 | 1 | Orphan | Standalone | 153403 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 126129.2996 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Audit Data | Yes | HV AQS | Archive | UND120 – Commercial Lines, Property, Casualty - indefinite Und 100 - | Policy | No | No | No | Yes | Glacier | 5479 HV AQS | HV-AQS, HV-AuditWin Plus - Premium Audit Folder in ImageRight | M. Kelly | Scott Grau | Smith, Krystal A Shewey, Dora A | Audit app process audit and audit data is uploaded to AQS and Billing, will pivot to PAM after CLT 6/22 need to follow up with colleen on retention requirements |  | HV CL | TBD Pending Research | AWS Glacier | RRC | TBD |  |  | 126129 | Yes - Business Owned | Win2019, SQL 2019 | Dangerous Forest |  | HV | TBD
5426 | HV-Clarify | In Progress - Planning | 2027-04-01 | HV Billing |  | 10/30- Colleen to update retention column details Set up meeting with Kristi on aligning on next steps and status. | CRM Tool for Contact Center and Service Center 11/20: Add to MF Planning Guide. | Esposito, Colleen |  |  |  | Production | Utility | 2027-04-01 | 1 | Orphan | Standalone | 361643 |  | Unplanned | Unplanned | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 66626.2853 | 300841001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | CRM data - data is sent to HV Direct Bill Mainframe - URA (User Remarks Area) - we stopped send sending this when Zoom replaced Clarify. Clarify still collects this data but no longer sends it to ZOOM | No | HV - Billing | Discard | N/A | Support | Yes | No | Yes | No | N/A | 5296 Legacy Billing System | AQS, DCT, Billing, | J. Whitman | Scott Grau | R. Hunter T. Webber |  |  | HV CL | TBD Pending Research | Decom and Discard | Decom and Discard | TBD | 1012036 |  | 66626 | No | WIN 2016, SQL 2019 |  |  | HV | TBD
5427 | HV-COGNOS | In Progress - Planning | 2026-09-30 | Cognos | Alex Gamarnik Dan Croll | 12/09/25 - 60% Complete on reWrite Rewrite & Decommission Planning Update Rewrite Progress: Approximately 60% complete. Two reports have been fully rewritten. A consolidated policyholder base report has been created, containing all required data. This consolidated report enables faster extraction for sub-reports without returning to Cognos, accelerating progress. Platform Decommissioning: Tracking separately; rewrite completion is a prerequisite for decommissioning. Colleen clarified that while overall rewrite progress is 60%. Key Achievements Successfully extracted all necessary data into a single consolidated report. Reduced dependency on Cognos for future report generation, enabling quicker migration. Risks Remaining rewrite tasks must be completed before platform decommission can proceed. Any delays in sub-report extraction could impact overall timeline. Next Steps Complete remaining rewrite tasks and sub-report extractions. Validate consolidated report accuracy and confirm business sign-off. Begin planning for Cognos platform decommission once rewrite reaches 100%. Provide updated completion percentage and timeline in next leadership review. Current Status Rewrite: 60% overall progress; 50% on core rewrite component. Decommission: Pending rewrite completion; timeline to be finalized post-rewrite. | Query report and analysis capabilities for all type of data. A component of COGNOS is Analyst Studio, which also needs to be tested whenever any type of upgrade occurs. 4/14/21 Lisa Berke having discussions to move forward on decom for this 1/24/22 Decom with HV BSA per Colleen. (CL Claims, Life, actuarial etc reporting) Update master dependency 10/23/24 Terry mentioned cost is $24,500, discussed some of the earlier cost numbers likely included contractors, more usage/consumption, etc. 04/02/25: all remaining updates on status can be found on the Planner board. LInk is in the 2nd to last column in this spreadsheet. | Esposito, Colleen | Alex Gamarnik |  | Yes | Production | Application | 2027-04-01 | 1 | Orphan | Harleysville Platform | 183958 |  | Transformation | Transformation: PLT & CLT | Unplanned | Unplanned | Unplanned | 231255.0417 | 73KD21001 | Unplanned | Unplanned | Unplanned | Yes | Policy Holder, Conformed Demisions and Claims master BI Reporting, Audit Store and Content Store | No | HV-Legacy Claims (5297),HV- AQS (5479) | Discard | N/A | 3rd Party IBM Cognos | N/A | N/A | Yes - feeds to Cognos | N/A | N/A | 5297 HV Legacy Claims | HV - Legacy Claims, Policy ODS | Alex Gamarnik | Scott Grau | Michael Martin Lori McCoy | Effort with Lisa Berke to begin the decom process. All HV run budget was assumed as going away and claimed as a CLT benefit. | Query report and analysis capabilities for all type of data. A component of COGNOS is Analyst Studio, which also needs to be tested whenever any type of upgrade occurs. 4/14/21 Lisa Berke having discussions to move forward on decom for this 6/6/24 - Need to be decommissioned in 2024 to save expenses. This came out of Guru's consumption reduction effort | Other Early Adopt | Decom and Discard | Decom and Discard | Decom and Discard | N/A | 1012025 | Monthly SQL = 6 @ $120.44 = $722.64 DPS (Backup) = 351 @ $.24 = $84.24 Web Server = 4 @ $14.51 = $58.04 Total Infras. = $864.92 LICENSE COSTS = $1,436.25 Labor = $1,500.00 TOTAL = $3,801.17 ANNUAL TOTAL = $45,804.00 | 231255 | Yes - $17,325/year Cognos license expires in 12/21/26 Lori McCoy | WIN 2016, SQL 2016 | Chariots of Fire |  | HV | TBD | https://planner.cloud.microsoft/webui/v1/plan/1k8FS6ivX0-5Af2zg0vx_2QAHmhP/view/board/task/mckD7PV3AUGVepe7VB8VpGQAI58x?tid=22140e4c-d390-45c2-b297-a26c516dc461 | HV_COGNOS_Plan_Guide.docx | Link to tracking workbook: Cognos Report List July 2024.xlsx | Pending estimates and recommendation from IT. | See tracking workbook. | · 35 reports hidden from view – not needed/used · 30 reports needed until migration is complete 13 reports need a new solution 8/7 - Recommend rewriting the 13 reports to SQL Reporting Svsc. IT working on estimates/run costs.
5442 | HV-ImageRight | Not Started | 2027-07-01 | ImageRight Doc |  | 11/7 - Images will be archived with their corresponding applications. Tracking will be at the individual application level 10/30- Needed for claims but that can be solved by getting stuff outside from ImageRight Big Rocks | Imaging and workflow management system from Vertafore. This system is used to capture policy, underwriting and claims workflow and documentation. Images can be introduced into this system in various ways such as scanning, printing, and email. Archive tool is a dependency. 12/19: right now using ImageRight for some archival including PL, once IR is archived, they will need to go to the archival tool once it is ready. | Esposito, Colleen |  | No |  | Production | Third Party Application | 2027-07-01 | 1 | Orphan | Harleysville Platform | 437222 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 970111.7965 | 73KB21001 | Review | Review | Review | Yes | Stores Output from DCT, AQS, Claims, Billing, Accounting Reports (retire after all HV apps retired or docs moved) 6/30/21 Also used as an input to ClaimCenter, see notes for more info | No | ImageRight | Discard | N/A | Print, Rules | Yes | Yes | Yes | Yes | N/A | 5479 HV AQS, DCT, Billing, Claims, ACE Premium Audit | AQS, DCT, Billing, Claims, ACE Premium Audit | M. Kelly | Scott Grau | Lindsey Moyer Amy Olstedd Linda Brockney Kim Wysong Billing ? | Maintains legacy u/w file (all incoming correspondence and output), u/w docs for PL and CL, maintains docs for legacy claims (receive feed from Documerge 6/30/21 per L. Moyer; folks are using ImageRight for their ClaimCenter claims as a document passthrough. ImageRight monitors mailboxes and pulls docs in automatically, creates tasks and routes to right person. When it recognizes a CC claim number, the doc is ftp'd to FileNet and then appears in ClaimCenter, with a notice to the associate that it's there. There is no direct way to do this into CLaimcenter - so they use this creative workaround. |  | HV CL | Document Images | Decom and Discard | Decom and Discard | TBD |  |  | 970111 | Yes - Contract Terminated Feb 2024 | Win2019, SQL2019 |  |  | HV | TBD
5444 | HV-Informatica | In Progress - Planning | 2027-07-01 | Informatica |  | 10/30- Need to rewrite informatica workflows into Enterprise Informatica Set up meeting with Kristi on aligning on next steps and status. | ETL Tool 11/6: No data retention. Source code will be saved 12/19: part of the decom will be done with the 4/1/27 date. Jobs and workflow will need to be in place until state reporting is defined (could this be manual). Phase 1 with MF, Phase 2 jobs/workflows needed for reporting. Include Actuarial | Esposito, Colleen |  | No |  | Production | Third Party Application | 2027-07-01 | 1 | Orphan | Harleysville Platform | 735834 |  | Unplanned | Unplanned | Unplanned | Unplanned | 2019 Review | 800474.7253 | 73EA21001 | Early Opportunity | 2019 Review | 2019 Review | Yes | ETL software that stores repository data and meta data (no policy data is stored) | No | HV - Informatica | Discard | N/A | N/A | Yes | Yes - Admin Interface | Yes | No | N/A | 5479 HV AQS, DCT, Billing, Claims, Stat. Actuarial | Processes all HV Data | B. Shif F. Unger | Scott Grau | Jay Mills - Actuarial | all, as long as HV transactions, it's needed…same as other | ETL Tool | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | 800474 | Yes - Enterprise Contract | Win2019, SQL2019 |  |  | HV | TBD
5454 | HV-Rules Maintenance Application (RMA) | Not Started | 2026-12-31 | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business | Development platform to write business rules. These rules are then used by the URE application. | Esposito, Colleen |  | Yes |  | Production | Desktop Application | 2026-05-15 | 1 | Transformation | CLT | 0 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 28921.5914 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Uses database rules repository to store rule updates, templates and rule's information | Yes | HV-URE | Archive | UND120 – Commercial Lines, Property, Casualty - indefinite | UW | No | Yes | No | No | Glacier | 5479 HV AQS | HV-URE | Ron Posatko | Scott Grau | George Schirripa | Application is user interface and allows Underwriting rules team to enter rules for processing. Only available in DEV, Pre-Prod regions. IT takes rules from repo and builds Blaze adb file for system use. 5/19 Retain source code to access the rules |  | HV CL | Misc. Data and Rules | AWS Glacier | RRC | TBD |  |  | 28921.5914 | FICO Contract (terminated 12/28/24) | Desktop |  |  | HV | TBD
5463 | HV-UWWB - Underwriter WorkBench | In Progress - Planning | 2026-07-30 | HV-UWWB - Underwriter WorkBench | Joanne Nuzzi | 1/21 - Joanne still working on the plan guide | This is a Workbench for task completion. documentation, and making underwriting decisions for Underwriters. Processing uses this workbench for task completion and documentation as well. | Esposito, Colleen |  | No | Yes | Production | Application | 2026-12-31 | 1 | Transformation | CLT | 586430 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 447472.7071 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Underwriter_Workbench database is used as its own db by the application. SQL | No | 5463-HV-UWWB - Underwriter WorkBench | N/A | N/A | UW | No | Yes | No | Yes | N/A | 5479 HV AQS | HV-Cognos, HV-Underwriting Rules Engine (URE), SSRS Reports, HV-Core Integration Svcs, HV-Image Right, HV-AIS | Joanne Nuzzi | Scott Grau | Cece Moore? | 5/12 need to archive u/w notes This application depends on various services/systems for displaying of data to the user. Also, uses multiple other databases as source of data are listed below: Conformed_Dimensions Application_Log IADB Policyholder Enterprise_Tables Agency_Portal_Billing U_517_Report ISOMatrix Renewal_Automation External_Property_Data Operational_Tables APADB | Need business decision as to when this application can be de-commed | HV CL | Underwriting Assessment Notes | N/A | N/A | TBD |  |  | 447472.7071 | No |  |  |  | HV | TBD
5464 | HV-VOIP Services | In Progress - Planning | 2027-04-01 | HV Billing |  | Set up meeting with Kristi on aligning on next steps and status. | Web service to provide insured and agent data back to the agent or call center representative. | Esposito, Colleen |  |  |  | Production | IT Service | 2027-04-01 | 1 | Orphan | Standalone | 0 |  | Unplanned | Unplanned | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 1868.0494 | 300841001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | No | reads HV Clarify database, decom with clarify | No | HV -Clarify | N/A | N/A | Support | Yes | No | No | No | N/A | 5296 Legacy Billing System | Clarify | M.Kelly | Scott Grau | R. Hunter T. Webber | decom with clarify | Web service to provide insured and agent data back to the agent or call center representative. | HV CL | Decom and Discard | N/A | N/A | N/A | 1012019 |  | 0 | No | WIN2019 |  |  | HV | TBD
5465 | HV-webMethods | Not Started | 2027-04-30 | WebMethods Doc |  | 11/10- Date changed to 04/30/27 | 11/6: No data retention. Source code will be saved webMethods is the backbone of Harleysville SOA- and EDA-enablement and provides support for HTTP/s, FTP/s and SMTP transport protocols, messaging, SOAP web service, synch/asynch, service orchestration, logging, standardized error handling, etc. The webMethods Integration Platform enables real-ime and batch service integration between Harleysville's core insurance applications on both the Windows and IBM mainframe environments. SOA application. | Esposito, Colleen |  | No |  | Production | 3rd Party | 2027-07-01 | 1 | Orphan | Harleysville Platform | 551875 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 673565.1825 | 73EA21001 | Unplanned | Unplanned | Unplanned | Yes | database is self supporting, creates its own db to store configuration. | No | HV - All | Discard | N/A | 3rd Party | Yes | Yes - Developer IDE | No | No | N/A | HV-Duck Creek, HV-AQS, HV-Agency Portal, HV-ImageRight | HV-Duck Creek, HV-AQS, HV-Agency Portal, HV-ImageRight | Subba Suda, Mike Kelly | Scott Grau | N/A | The ESB middleware application used by all applications for web services calls |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | N/A |  |  | 673565.1825 | Yes - IBM | WIN2022, SQL2019 |  |  | HV | TBD
5478 | HV-Agent Portal | Not Started | 2026-12-31 | Agent Portal | Tony Brnic | 10/30- Colleen to do more research on it | Portal for agents to view his book of business, begin new business transaction and launch into applicable policy systems, gather agency reports, etc. 6/16/22 Met with Lori Laird and ADS team, wanting dates of PL and CL policy retirements, wanting to kick off research of the application 03/31/25: concerns from Lindsey Moyer on the timing due to Claims impact. Colleen set up meeting on 4/2 to discuss. 04/02/25: targeted July of this year to turn off as part of a seperate project to turn off agent access due to non-renewal of a contract. Talking to Lindsey Moyer. Could agent center be used to gather information? Need follow up with Frank K's area (Marano). Loss/Run download and number of policies remaining; need to know that need claims. They will not be able to access driver loss data. I&O: Jason Draper. Removing access to Agent Portal. Legacy Claims was overlooked. This is going to impact user experience and cause an increase with needed resources from Claims. Set pre-meeting with Colleen, Terry, Tony Brnic, Mike Kelly, Angie Pike and Sharon Bealer for 4/3. Larger meeting with ADS Frank K and Mark Marrano on 4/9. | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | Orphan | Harleysville Platform | 893607 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 808337.3956 | 73KB21001 | Unplanned | Unplanned | Unplanned | Yes | IADB - account-level data | Yes | HV AQS | Archive | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Support | Yes | Yes | Yes | Yes | Glacier | 5479 HV AQS | HV-Agent Portal, HV-IADB, HV-ImageRight, HV-AIS, HV-U279, HV-Underwriting Rules Engine (URE), HV - Harleysville Underwriting Guide, Claims Service, SSRS Reports, Account Propsal Services, Policy Holder Reports DB, HV Duck Creek, HV AQS, HV-Mainframe CL, HV-WebMethods, HV-Melissa, HV Informatica, HV Legacy Billing, | Tony Brnic | Scott Grau | Jamey Fauque | system stay online until last policy, retention defined by quote vs policy data. There is a quote DB that is populated from AQS. | 1. Shutdown for external users by August 2025 to avert PingOne. 2. Meet w/ Business partners on 6/12/2024 to discuss downsize/de-comm of HV-Agent Portal | HV CL | Misc. Data and Rules | P&C Data Lakehouse + AWS Glacier | Inquiry UI, API, Data Extract Process + RRC | TBD |  |  | 808337 | No | Win2019, SQL2019 | Chariots of Fire |  | HV | TBD
5479 | HV-AQS | In Progress - Planning | 2026-12-31 | HV-AQS | Dan Croll |  | Policy administration for commercial lines. | Esposito, Colleen |  | Yes | Yes | Production | Application | 2026-12-31 | 1 | Transformation | CLT | 7082225 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 6508026.1346 | 73KD21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | HR_AQS_Policy, HR_AQS_Resource, HR_AQS_ResourceEdit,HR_AQS_ResourceTest, HR_AQS_Document, HR_AQS_DocumentEdit, HR_AQS_Repository, HR_AQS_System, IADB, Global_IADB | Yes |  | Archive | POL140 – Commercial Lines, Property and Casualty Insurance Lifetimes - Indefinite Stand-alone commercial auto: POL100 – Policyholders Administration, Lifetime Policy Records - Active + 10 years | Policy | Yes | Yes | Yes | Yes - Hybrid (data Lakehouse + Gacier) | Hybrid (data Lakehouse + Gacier) | 5479 HV AQS | Policy Migration Services, HV Access Express, webMethods, agent portal | Dan Croll | Scott Grau | Linda Brockney | packaged app which we now own. Contracts exist for Infragistics | 1. Need business concessions to stop procesing prior term transactions and amendments. 2. Need policy archival in place | HV CL | Policy and Claims Data | P&C Data Lakehouse + AWS Glacier | Inquiry UI, API, Data Extract Process + RRC | TBD |  |  | 6508026 | No | Win2019, SQL2019 | Chariots of Fire |  | HV | TBD
5567 | HV-Starteam | Not Started | 2026-12-31 | HV-Starteam |  |  | 11/6: No data retention. Source code will be saved Source management product that we have licensed for AQS. Need to save the source code. | Esposito, Colleen |  | No |  | Production | 3rd Party | 2026-12-31 | 1 | Transformation | CLT | 127371 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 1868.0494 | 300841001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Source Code for AQS, data, forms and rates | n/a | Starteam | Discard | N/A | Source Code | Yes | Yes | No | Yes | N/A | 5479 HV AQS | AQS | D. Schell Dan Croll | Scott Grau | N/A |  |  | HV CL | Misc. Data and Rules | Decom and Discard | Decom and Discard | N/A |  |  | 1868 | Yes - Opentext (Borland) | Win2019, SQL2019 |  |  | HV | TBD
5570 | HV-Predictive Modeling | Not Started | 2026-12-31 | HV-Shared Web Doc |  |  | Provides underwriting scoring on accounts based on policy information | Esposito, Colleen |  | Yes |  | Production | Application | 2026-12-31 | 1 | Transformation | CLT | 515083 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 508823.8711 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Multilple Databases - collect non PII information that is used during rating/scoring | No | HV-Predictive Modeling | Archive | UND120 – Commercial Lines, Property, Casualty - indefinite | UW | Yes | No | Yes | No | Glacier | 5479 HV AQS | HV-AQS, HV-Quote Services, HV-Agent Portal | Ron Posatko | Scott Grau | Scott Woomer | Data stored by PM is non-PII information used to determine Company/Model/Scoring Information along with temporary numbers needed for calculations. Data used by business for reporting 5/19 Includes info on HOW the rate was calculated, storing input and some output, but no calculations. Need to store the rules in the DB, not the input or output data |  | HV CL | Misc. Data and Rules | AWS Glacier | RRC | TBD |  |  | 508823.8711 | No | Win2019, SQL2019 |  |  | HV | TBD
5666 | HV-AIS | Not Started | 2026-12-31 | HV-Shared Web Doc |  |  | Agency SQL database and services used throughout organization for agency validation.* This is incorrectly categorized as an application and is being retired * | Esposito, Colleen |  |  |  | Production | Component | 2026-12-31 | 1 | Orphan | Harleysville Platform | 36792 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 85503.1828 | 73EA21001 | Unplanned | Unplanned | Unplanned | Yes | copy of mainframe master | No | HV- Agency Systems | Discard | N/A | Discard | Yes | No | Yes | N/A | N/A | 5479 HV AQS | AQS, DCT, Agent Portal. | F. Unger | Scott Grau | Christina Ledbedder | Service used for agency validation - Agency Master from Mainframe is populated into SQL tables for HV-AIS - this is daily and over writes each day |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | 85503 | No | Win2019, SQL2019 | Dangerous Forest |  | HV | TBD
5668 | HV-Harleysville Enterprise Web Services (HEWS) | Not Started | 2026-12-31 | HV-Shared Web Doc | Joanne Nuzzi |  | Grouping of services, an application service function provided using network address over the web enabling communication between two systems. | Esposito, Colleen |  |  |  | Production | IT Service | 2026-12-31 | 1 | Orphan | Harleysville Platform | 0 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 33128.6698 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | No | Uses various databases used by other apps. Does not have it's own database | No | N/A | N/A | N/A | Support | Yes | No | No | No | N/A | 5479 HV AQS | HV-IADB, | Joanne Nuzzi | Scott Grau | N/A |  |  | HV CL | Decom and Discard | N/A | N/A | TBD |  |  | 33128.6698 | No | Win2019, SQL2019 |  |  | HV | TBD
5670 | HV-Question Answer Service | Not Started | 2026-12-31 | HV Underwriting Rules | Tony Brnic | 11/7/2025- Obatined the retention requiremets, updated Master, Udated WBS, sent info to the business for OCM, schedueld meeting with the business 10/30- Colleen to do more research on it | Main service component for the URE application to determine questions to ask and then save responses Dependent on adding products. 12/19: this is highly integrated with other apps, need to weigh risk of trying to remove early due to integration. | Esposito, Colleen |  | Yes |  | Production | Component | 2026-05-15 | 1 | Transformation | CLT | 0 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 16564.3349 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Question, Service_Log | Yes | HV-Question Answer Service | Archive | UND120 – Commercial Lines, Property, Casualty - indefinite | UW | Yes | Yes | No | Yes | Glacier | 5479 HV AQS | HV-AQS, Agent Portal, HV URE | Ron Posatko, Dan Croll | Scott Grau | Linda Brockney | Not sure this is used by AQS |  | HV CL | Misc. Data and Rules | AWS Glacier | RRC | TBD |  |  | 16564.3349 | No | Win2019, SQL2019 |  |  | HV | TBD
5712 | HV-Proxix (Corelogic) | In Progress - Planning | 2026-03-31 | HV-Proxix (Corelogic) | Frank Unger | 1/20- Vendor accepted the non-renewal of the license. Their only stipulation is that everything has to be deleted within 30 days of the license expiration, which is the 19th. Everything is scheduled to get turned off for this on the 20th because the license expires. The license expires on the 19th, so nothing's gonna work anyway after that. So Frank gonna stop, stop everything on the 20th.We met with the business users and they agreed to the manual process that has to take place. Frank did update the OCM piece in the plan guide and sent that out to them for approval. For the plan guide approval, but regardless it gets.Frank went to Rachel Barone and we're waiting for the sign off. So this will probably be done prior to the 3/31 date. | Vendor supplied Geo coding and territory information used by Duck Creek (Core Logic) and Commercial Lines (AQS) | Esposito, Colleen |  |  | No | Production | Third Party Application | 2026-12-31 | 1 | Orphan | Policy Platform | 36792 |  | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 28921.5914 | 73EA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Monthly datasets provided by vendor. ,DAT files | No | HV-Proxix (Corelogic) | Discard | N/A | 3rd Party | N/A | N/A | N/A | N/A | N/A | HV - Commercial Lines Legacy | HV - AQS | Mike Kelly | N/A | Angie Pike; Mikchael Martin | The CoreLogic Interface converts address into geographic coordinates Latitude, Longitude and also Spatial analytics information like riskZone (fire,flood,earthquake..)and other information from spatial files 5/19 PL only, CL moved to GIS services, quarterly file based updates |  | HV PL | Decom and Discard | Decom and Discard | Decom and Discard | N/A | 1012685 | N/A | 28921.5914 | Yes - business owned (Zach Cozier contact for contract) | SQL 2019 |  |  | HV | TBD
5713 | HV-Melissa (address check) | Not Started | 2026-12-31 | HV-Shared Web Doc | Mike Kelly |  | Vendor supplied information used to validate and scrub addresses for Duck Creek quotes and policies. | Esposito, Colleen |  |  |  | Production | 3rd Party | 2026-12-31 | 1 | Orphan | Harleysville Platform | 36792 |  | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 28921.5914 | 73EA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | No | Monthly datasets provided by vendor. ,DAT files | n/a | HV-Melissa | Discard | N/A | 3rd Party | Yes | No | No | N/A | N/A | 5479 HV AQS | HV-Duck Creek, HV-AQS | Vlad Levin | Scott Grau | PL and CL | The Melissa Address Check Interface verifies and standardizes your Address data using the most current data from the U.S. Postal Service |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | 28921.5914 | Yes | Win2016 |  |  | HV | TBD
5717 | HV-Active PDF | Not Started | 2026-12-31 | HV-AQS | Dan Croll, Laurie Fernes |  | HV-Active PDF | Esposito, Colleen |  |  | No | Production | Component | 2026-12-31 | 1 | Transformation | CLT | 0 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 10938.0278 | 73KD21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | pdf images, batch print info | No | HV-AQS | Discard | N/A | Support | Yes | No | Yes | No | N/A | 5479 HV AQS | Active PDF will not have it's own document and will be inserted in each Planning Guide as needed HV-Question Answer Service, HV Bill Matrix, HV EFT Services, HV BL registration DB, HV ISOMatrixHGM DB, HV ASPSessionState DB, Account Register(Global IADB), Clear quote, Agent Center, Policy Center, Experian, Recaptcha | Dan Croll, Laurie Fernes | Scott Grau | Linda Brockney | 3rd party software - ActivePDF, stay online until we can stop doing print from AQS. | De-comm with HV-AQS if solution in place for policy re-prints | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | 10938 | No - we did not review | Win2019, SQL2019 | Chariots of Fire |  | HV
5720 | HV-UW Assignment | Not Started | 2026-12-31 | ImageRight Doc |  |  | Web application for updating workflow routing within Image Right for Commercial Lines 4/19/21 changed assignment from Colleen to Carolyn 12/19: could be done earlier than ImageRight. | Esposito, Colleen |  |  |  | Production | Component | 2026-12-31 | 1 | Orphan | Policy Platform | 134081 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 33128.6698 | 73KB21001 | Unplanned | Unplanned | Unplanned | Yes | HV U/W names and ID's/ SQL | No | HV-Imageright | Discard | N/A | UW | Yes | Yes | No | No | N/A | 5479 HV AQS |  | M. Kelly | Scott Grau | Lindsey Moyer UW / Processing | used to assign work, can delete after HV commercial lines workflow is no longer used 5/12 flow in imageright that sends to correct u/w |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | 33128 | No - Imageright contract terminated | Win2019, SQL2019 |  |  | HV | TBD
6010 | HV-Expiration | In Progress - Planning | 2027-04-01 | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | Policy / Renewal tracking application | Esposito, Colleen |  |  |  | Production | Application | 2027-04-01 | 1 | Orphan | Policy Platform | 0 |  | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 48100.5816 | 73KA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Harleysville legacy system (policy summary index) for renewal processing of all personal and commercial policies both automated and manual and CICS, policy info, renewal info, dates, indicators, term info, premium, bill acct, status, etc (VSAM) CORP00PV.AGCY.EXP.REN.MASTER.C CORP00PV.AGCY.EXP.REN.IDX.C | No | 6010-HV-Expiration | Discard | N/A | Support | Yes | Yes | Yes | No | N/A | 5479 HV AQS | most HV systems | Rachael Wilford | Scott Grau | IT | May be the system of record for manual policies? The manual policy only exists as keyed into the Expiration system. Only archive manual policy - if system of record for manual policy |  | HV CL | Policy and Claims Data | Decom and Discard | Decom and Discard |  |  |  | 48100.5816 | No | MF, VSAM, CICS | Sunset |  | HV | TBD
6096 | HV-AQS Batch Print | Not Started | 2026-12-31 | HV-AQS | Dan Croll |  | This is a custom .net application to package HV-AQS Policy Output utilizing Active PDF. This component provides the bar coding on documents for Finishing. It also generates a transactional cover letter per Billing Account,applies the NY ID Card PDF417 bar code and packages new business and renewal output with the Agency Bill Schedule | Esposito, Colleen |  |  | No | Production | Component | 2026-12-31 | 1 | Transformation | CLT | 0 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 0 | Not HV BSA | Transformation | Transformation: CLT | Transformation: CLT | Yes | Input xml received from HV policy systems and images are created using this app and sent to HV-Q Direct for printing, images are fed to Imageright from HV-AQS not HV-BatchPrint. Input PDFs are received from from HV-AQS and HV-Peer Sync (to transfer pdfs to server) | No | HV-AQS | Discard | N/A | Support | No | No | Yes | No | N/A | 5479 HV AQS | HV-AQS , HV-QDIRECT | Joanne Nuzzi, Tony Brnic, Laurie Fernes | Lin, Bo | Linda Brockney | it is used to generate packaged Policy Output for HV-AQS. HV-AQS BatchPrint creates and transfers zip files containing policy output to HV-Q Direct for print/finish/mail at Grove City. Dependent on HV-ActivePDF, HV-Peer Sync, HV-Q Direct and HV-AQS. |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | TBD |  |  | $7,800 labor | No | Win2019, SQL2019 | Chariots of Fire |  | HV | TBD
6393 | HV-Agency Licensing | In Progress - Planning | 2027-04-01 | MF Doc |  | Set up meeting with Kristi on aligning on next steps and status. | Capturing of agency and producer information from CMS G2 onto a SQL database, which is enriched with demographic and banking info from the Harleysville Agency Master file, providing agency licensing validation to Harleysville systems and a regular ETL feed to Nationwide DPIM and AMF systems | Esposito, Colleen |  |  |  | Production | Component |  | 1 | Transformation | Agency | 0 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 57843.1828 | 73EA21001 | Unplanned | Unplanned | Unplanned | No | Producer Data from Vertfore - | No | ThirdParty Vertofore | Discard | N/A | 3rd Party | N/A | N/A | N/A | N/A | N/A | 5479 HV AQS | AQS, DCT, Agent Portal. | F. Unger |  | Christina Ledbedder |  |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 57843 | No | Win2019, SQL2019 | Dangerous Forest |  | HV | TBD
6397 | HV-ISO PPC | Not Started | 2026-12-31 | HV-Shared Web Doc | Mike Kelly |  | 3rd Party data source that integrates with Duck Creek and CL AQS to supply Property Protection Class base on geographic information | Esposito, Colleen |  |  |  | Production | Third Party | 2026-12-31 | 1 | Orphan | Policy Platform | 0 |  | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 33121.5914 | 73EA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | ISOLocation API product updates stored on the SQL database. Monthly updates received from 3rd party | No | HV-ISO PPC | Discard | N/A | 3rd Party | Yes | No | Yes | No | N/A | 5479 HV AQS | HV-AQS HV-Duck Creek | Mike Kelly | Scott Grau | Angelia Pike | The LocationAPI product provides Protection class code, Auto Territory code for PL LOB and for CL LOB it provides GLTerri, ISOProp, BCEGS and other Territory information |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 33121.5914 | Yes - Business Owned | Win2019, SQL2019 |  |  | HV | TBD
6405 | HV-CoreLogix Quarterly Update | In Progress - Planning | 2026-03-31 | HV-Proxix (Corelogic) | Frank Unger | 1/20- Vendor accepted the non-renewal of the license. Their only stipulation is that everything has to be deleted within 30 days of the license expiration, which is the 19th. Everything is scheduled to get turned off for this on the 20th because the license expires. The license expires on the 19th, so nothing's gonna work anyway after that. So Frank gonna stop, stop everything on the 20th.We met with the business users and they agreed to the manual process that has to take place. Frank did update the OCM piece in the plan guide and sent that out to them for approval. For the plan guide approval, but regardless it gets.Frank went to Rachel Barone and we're waiting for the sign off. So this will probably be done prior to the 3/31 date. | Comparison Utility CoreLogix is a leading provider of consumer, financial and property information, analytics and services to business and government | Esposito, Colleen |  |  |  | Production | Third Party | 2026-12-31 | 1 | Transformation | CLT | 36792 |  | Transformation | Transformation: PLT & CLT | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | 37921.5914 | 73EA21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | No |  | No | HV-Proxix (Corelogic) | Discard | N/A | 3rd Party | No | No | Yes | No | N/A | 5397 HV Duck Creek | HV-AQS HV-Duck Creek | Mike Kelly | Scott Grau | Linda Brockney | Quarterly product updates from Vendor, related to 5712, same updates |  | HV PL | Decom and Discard | Decom and Discard | Decom and Discard |  | 1012689 |  | 37921.5914 | Yes - Business Owned | Win2019 |  |  | HV | TBD
6408 | HV-Bill Matrix | In Progress - Planning | 2027-04-01 | HV Billing |  | Set up meeting with Kristi on aligning on next steps and status. | 3rd Party Vendor for on line payments -- an online payment system operated by BillMatrix Corporation that is designed to accept payments 4/19/21 Carolyn mentioned this was her app, it was previously marked retired. Moving back to Not Started, CArolyn confirmed it still running. Need a decom date 1/24/22 - Previously assessed and documentation is available in our folder structure. Leave until migrated off of legacy platforms. NW Life and IVR has connection. PL uses to take payments. Tony to check on PL. CC payment through 5478 Agent Portal - attach on master. Collen will update APRM | Esposito, Colleen |  |  |  | Production | Third Party |  | 1 | Orphan | Policy Platform | 13480 |  | Unplanned | Unplanned | Unplanned | Unplanned | 2020 Review | 43600.5816 | 73KA21001 | Retired | Retired | Retired | No | Credit card processing and one time EFT for Harleysville | N/A | N/A | N/A | N/A | 3rd Party | No | No | Yes | No | N/A | 5479 HV AQS | HV-Direct Bill 5478 HV-Agent Portal | Harry Hermann | Scott Grau | Andrea Shatto | Per Carolyn this needs decommed, there is a proposal to stop using this and use NW preferred vendor, in process 8/31 Per Tony, this also used by HV life company. Connected into IVR also, not a small effort. | 3rd Party Vendor for on line payments -- an online payment system operated by BillMatrix Corporation that is designed to accept payments 4/19/21 Carolyn mentioned this was her app, it was previously marked retired. Moving back to Not Started, CArolyn confirmed it still running. Need a decom date I dont think this is retired. | HV CL | Decom and Discard | N/A | N/A |  | 1012015 |  | 43600 | Yes - Business Owned | SFTP, VSAM | Sunset | I don't think this is retired? | HV | TBD
6422 | HV-Account Proposal | Not Started | 2026-12-31 | HV-AQS | Dan Croll |  | Application that generates Account Proposal for CL agents 4/19/21 Moved to Terry per Carolyn 12/11: Separate service on the document end could come down, remaining would be dependent on shutting down transactions for AQS. 12/19: this is highly integrated with other apps, need to weigh risk of trying to remove early due to integration. | Esposito, Colleen |  |  | Yes | Production | Component | 2026-10-31 | 1 | Transformation | CLT | 0 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 57843.1828 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | Requests entered via HV CL Agent Portal and Underwriter Workbench to generate real time Account Proposal generated using HV-Documaker. A PDF is returned to requesting user. HV-Documaker does not store the pdf or send it to ImageRight. | No | HV-AQS | Discard | N/A | Print | Yes | No | No | No | N/A | 5479 HV AQS | HV-DOCUMAKER, AQS, HIEDMS | Vlad Levin | Scott Grau | Linda Brockney | system online until finished with new business in AQS |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard | N/A |  |  | 57843 |  |  | Chariots of Fire |  | HV
6424 | HV-AuditWin Plus | Not Started | 2026-12-31 | HV-ACE - Premium Audit | Mike kelly | 10/30- Collen to accelerate timeline | Utility software used by field auditors to manage audit assignments, inventory and scheduling. Audit assignments are downloaded to the AuditWin Plus (formerly known as Field Manager) from Audit Control Environment (ACE). | Esposito, Colleen |  |  |  | Production | Component | 2026-12-31 | 1 | Orphan | Standalone | 14574 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 16564.3349 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | No | Service that retrieves data, no data is stored | No | HV - ACE Premium Audit | Discard | N/A | Discard | No | No | Yes | N/A | N/A | 5479 HV AQS | HV- ACE - Premium Audit | Mike Kelly |  | Smith, Krystal A Shewey, Dora A | Service, user inputs in this app then it uploads to HV-ACE |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 16564 | Yes - Business Owned | Download | Dangerous Forest |  | HV
6452 | HV-ACCESS Collections | In Progress - Planning | 2027-04-01 | HV Billing |  | Set up meeting with Kristi on aligning on next steps and status. | 3rd Party Vendor for collections agency -- With Access Collections, LLC you'll have the skill and expertise needed to collect your consumer debt, delivering improved cash flow and reduced days outstanding. 12/11/24: will need a manual process for this going forward. | Esposito, Colleen |  |  |  | Production | Third Party |  | 1 | Orphan | Policy Platform | 0 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 43600.5816 | 73KA21001 | Unplanned | Unplanned | Unplanned | No | File exchanges with 3rd party on receivables | N/A | N/A | N/A | N/A | 3rd Party | No | No | Yes | N/A | N/A | 5296 HV Legacy Billing Systems | HV- Accounts Receivable | Harry Hermann |  | Melissa Wood Nick Ginther |  |  | HV CL |  | N/A | N/A |  |  |  | 43600.5816 | Yes - Business Owned | SFTP, Flat File | Sunset |  | HV | TBD
6453 | HV-PNC Bank Feed | In Progress - Planning | 2027-04-01 | HV Billing |  | Set up meeting with Kristi on aligning on next steps and status. | 3rd Party Vendor for agent sweep screens - PNC/Wells Fargo Bank 12/11: project in flight to decom the feed and then a new one will be created. | Esposito, Colleen |  |  |  | Production | Third Party |  | 1 | Orphan | Standalone | 0 |  | Unplanned | Unplanned | Unplanned | Unplanned | Unplanned | 43600.5816 | 73KA21001 | Unplanned | Unplanned | Unplanned | No | Lockbox for Harleysville for Payments and stubs | N/A | N/A | N/A | N/A | 3rd Party | N/A | N/A | N/A | N/A | N/A | 5296 HV Legacy Billing Systems | HV-Direct Bill, HV-Life | Harry Hermann |  | Andrea Shatto |  |  | HV CL |  | N/A | N/A | N/A |  |  | 43600.5816 | Yes - Business Owned | SFTP, Flat File | Sunset |  | HV | TBD
6500 | HV-AQS User SecurityLoad | In Progress - Planning | 2026-12-31 | HV-AQS | Dan Croll |  | Utility to load new NW/Harleysville agents as Users to AQS. | Esposito, Colleen |  | no | No | Production | Component | 2026-12-31 | 1 | Transformation | CLT | 36792 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 35401.5914 | 73EA21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | UserSecurityLoad SQL db | no | AQS | Discard | N/A | Security Audit | Yes | Yes | Yes | N/A | N/A | 5479 HV AQS | HV-AQS | Dan Croll | Bosheng Lin | Linda Brockney | remain for as long as AQS is running, used for access, role changes | De-comm with HV-AQS | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 35401 | No | CICS, win2019, SQL2019 | Chariots of Fire |  | HV | TBD
6512 | HV-AQS - Doc Utility | Not Started | 2026-12-31 | HV-AQS | Dan Croll |  | Doc Utility is used by AQS Configuration Analysts and Developers for adding and updating document data. 12/19: need follow up with Dan Croll if this is an early decom. This could cause manual reporting. Need to weigh this in also. Need to determine level of confidence of not being needed anymore --No longer needing regulatory changes. | Esposito, Colleen |  |  | No | Production | Component | 2025-12-31 | 1 | Transformation | CLT | 0 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 1818.0278 | 73KD21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | AQS_Docs | No | AQS | Discard | N/A | Support | Yes | Yes | No | N/A | N/A | 5479 HV AQS | HV-AQS | Dan Croll |  | Linda Brockney | Part of the AQS app and data, treat same as AQS, no data to archive | De-comm with HV-AQS | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 1818 | No | win2019, SQL2019 | Chariots of Fire |  | HV | TBD
6859 | HV - eForms Generation App | In Progress - Planning | 2026-06-30 | HV-Shared Web Doc | Joanne Nuzzi | 1/20- Frank mentioned Joanne is looking into this | Generates ACORD COI (Certificate of Insurance) and EOP (Evidence of Property) forms currently used by the Service Center group. Minimal user entry required for form completion | Esposito, Colleen |  |  |  | Production | Application |  | 1 | Orphan | Standalone | 27925 |  | Unplanned | Unplanned | Transformation | Transformation: CLT | Transformation: CLT | 33128.6698 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | EFORM - Acord form data | No | HV-eForms Generation App | Discard | N/A | Print | Yes | Yes | No | N/A | N/A | 5479 HV AQS | N/A | Joanne Nuzzi | Scott Grau | Linda Brockney | COI form generater stores data that is inpur for the form completion and generates the PDF, which is then moved to imageright | De-comm with HV-Service Center or at the discretion of the business | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 33128.6698 | No | win2019, SQL2019 |  |  | HV | TBD |  |  | Patel, Minal C <mpatel@nationwide.com>; Davis, Terri L <tdavis@nationwide.com> |  | Terri Davis
7558 | HV-Hazard Grade Matrix (HGM) | In Progress - Planning | 2026-06-30 | HV-Hazard Grade Matrix (HGM) | Joanne Nuzzi | 1/20- Frank mentioned Joanne is looking into this | Application used by underwriters to get the Matrix Grade; also used by Product staff to update information for use in Underwriting decisions via an admin page. 1/11/22 Per Marcy F The HGM application is currently still in use, but even once the application retires (no details on timeline), I believe the database (ISOMatrixHGM) will live on. The HUG application is no longer being used (replaced with HGM), but the database (ISOMatrix) is still linked to several legacy applications. I believe the data from ISOMatrix was already copied to ISOMatrixHGM, so once the work is done to disconnect the apps from ISOMatrix and move the connections to ISOMatrixHGM, the ISOMatrix database will no longer be needed. We will be picking the analysis back up to confirm the work that needs to be done, as it relates to the ISOMatrix database. It is my understanding that the HUG application codebase is somehow intermixed with HGM, so the code cannot be removed. However, it is no longer referenced in GitHub, Jenkins or UCD, so we can probably retire in SNOW. | Esposito, Colleen |  | Yes |  | Production | Component |  | 1 | N/A | N/A | 0 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 78197.3396 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | Yes | ISOMATRIXHGM - List of all hazard information. | Yes | HV-HGM | Archive | Indefinite | UW | Yes | Yes | No | No | Glacier | 5479 HV AQS | N/A | Joanne Nuzzi | Scott Grau | Linda Brockney | Information is taken from a spreadsheet and then put into the app. Follow up with Jess, can the spreadsheet be used for the historical record, used regularly by processing. | De-comm at the discretion of the business or with HV-AQS | HV CL | Misc. Data and Rules | AWS Glacier | RRC |  |  |  | 78197.3396 | No | win2019, SQL2019 |  |  | HV |  |  |  | Jessica Went
7814 | HV-CL Insured Account search tool | In Progress - Planning | 2026-12-31 | HV-Agent Portal |  |  | CL Insured Account name search tool used by processing groups for a lookup of account and billing account # info. A Link to Image Right is included | Esposito, Colleen |  |  |  | Production | Utility |  | 1 | N/A | N/A | 0 |  | Transformation | Transformation: CLT | Transformation | Transformation: CLT | Transformation: CLT | 16564.3349 | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | No | N/A | N/A | CL Insured Account DB (IADB) | N/A | N/A | Support | Yes | Yes | No | No | N/A | 5479 HV AQS | AQS, Agent Portal, Workbench, | Tony Brnic | Scott Grau | Jennifer Zaugg |  | De-comm at the discretion of the business or with HV-Agent Portal | HV CL |  | N/A | N/A |  |  |  | 16564.3349 | No | SQL2019, Win2019 |  |  | HV | [5 empty] | Trina Deihl, Nick Ginther Brenda Crossin Specialist, Statistical
7866 | HV-U279 Processing Form | In Progress - Planning | 2026-06-30 | HV-U279 Processing Form | Joanne Nuzzi | 1/20- Frank mentioned Joanne is looking into this | New business and renewal communication tool between Underwriting and Processing. Supports instructions for setting up billing and policies. Tool to generate a form for completion and save to Image Right for future updates. | Esposito, Colleen |  |  |  | Production | Utility |  | 1 | [6 empty] | Transformation | Transformation: CLT | Transformation: CLT |  | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | No | N/A | Yes | N/A | Archive | N/A | Underwriting | Yes | Yes | No | N/A | RRC | 5479 HV AQS | HV-Underwriter Workbench | Joanne Nuzzi | Scott Grau | Linda Brockney | This application depends on HV-UW Assignment and 5720-HV-ImageRight-IRWebServices for data. Pulls the data from the assignmet and puts the data on the form, then processing completes and put in imageright, only generates the word doc | De-comm with HV-AQS and/or HV-agent portal | HV CL | Decom and Discard | [6 empty] | No | SQL2019, Win2019 |  |  | HV | [5 empty] | Brenda Crossin
7944 | HV-PowerShell-Build-Deployment-Scripts | Not Started | 2026-12-31 | HV-Starteam |  |  | Jenkins is the tool we use for developers to initiate the PowerShell scripts to do the build/deployment - This will be used to deploy AQS and WebMethods code (confirm if this is already gone, switch to urban code deploy) | Esposito, Colleen |  |  |  | Production | Component |  | 1 | [6 empty] | Unplanned | Unplanned | Unplanned |  | 300841001 | Review | Unplanned | Unplanned | No | deployment tool for AQS | No | N/A | Discard | N/A | Support | Yes | No | No | N/A | N/A | 5479 HV AQS | AQS, Starteam | D. Schell |  | IT | contains the scripts to deploy code |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  | 0 | No | win2019 |  |  | HV
7954 | HV-Core Integration Svc | Not Started | 2026-12-31 | HV-Shared Web Doc | Joanne Nuzzi |  | Collection of web services utilized by numerous applications. A large number are used by UWWB and AQS NB and Renewal process | Esposito, Colleen |  |  |  | Production | IT Service |  | 1 | [6 empty] | Transformation | Transformation: CLT | Transformation: CLT |  | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | No | N/A | N/A | N/A | N/A | N/A | Support | Yes | No | No | N/A | N/A | 5479 HV AQS | AQS, HV-IADB, Quote Service | Mike Kelly | Scott Grau | IT | This service is used by many of the systems as integration point for data, main with IADB and Quote databases.Though this service doesn't have any direct database it uses other critical database systems for data updates. | Cannot de-comm until HV-UWWB Underwriter WorkBench is no longer used and AQS is ready for de-comm | HV CL | Decom and Discard | N/A | N/A |  |  |  |  | No | SQL2019, Win2019 |  |  | HV
7955 | HV-MVR Services | In Progress - Planning | 2026-06-30 | MVR DOC | Frank Unger |  | Used by AQS and UWWB to request/access driver MVR records. MVR records are then stored in ImageRight. Also contains a batch component, that calls an external service, that scans public records for additional driver data that is then stored in a local database | Esposito, Colleen |  |  |  | Production | IT Service |  | 1 | [6 empty] | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT |  | 73KB21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | CL_Driver, Application_Log; MVR database on OHNALDB0199.nwie.net, 1021 can be deleted | No | AQS | Discard | N/A | Support | Yes | No | Yes | N/A | N/A | 5479 HV AQS | HV-UWWB; webMethods; HV-AQS, Stat | Joanne Nuzzi Boris Shif |  | Linda Brockney Brenda Crossin | records stored in imageright | De-comm at the discretion of the business | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  |  | Yes - Business | SQL2019, Win2019 |  |  | HV
7956 | HV-Core Logic Svc | Not Started | 2026-06-30 | HV-Shared Web Doc | Joanne Nuzzi |  | Services that handle Hazard data for Property policies. Used by NB and Renewal processes | Esposito, Colleen |  |  |  | Production | IT Service |  | 1 | [6 empty] | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT |  | 73KB21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | No | External_Property_Data | No | N/A | N/A | N/A | 3rd Party | Yes | No | No | N/A | N/A | 5479 HV AQS | AQS | Joanne Nuzzi, Mike Kelly |  | Linda Brockney | web serivce for property and building data, used at NB and renewal, new locations, decom with AQS, data is stored in AQS with the policy | De-comm with HV-AQS | HV CL | Decom and Discard | N/A | N/A |  |  |  |  | Yes | SQL2019, Win2019 |  |  | HV
7957 | HV-Billing Svc | Not Started | 2026-12-31 | HV-Billing | Joanne Nuzzi |  | Services that support Billing | Esposito, Colleen |  |  |  | Production | IT Service |  | 1 | [6 empty] | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT |  | 73KB21001 | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | No | N/A | N/A | N/A | N/A | N/A | Support | Yes | yes | No | N/A | N/A | 5479 HV AQS | HV-Core Integration Svcs, HV-IADB, CL Legacy Service, Agent Portal | Mike Kelly, Tony Brnic | Scott Grau | Linda Brockney | It uses other database Agency_Portal_Billing. | De-comm with HV-Agent Portal | HV CL | Decom and Discard | N/A | N/A |  |  |  |  | No | SQL2019, Win2019 |  |  | HV
7959 | HV-Update AQS Stat Feed | In Progress - Planning | 2026-03-31 | HV-Proxix (Corelogic) | Frank Unger | 1/20- Vendor accepted the non-renewal of the license. Their only stipulation is that everything has to be deleted within 30 days of the license expiration, which is the 19th. Everything is scheduled to get turned off for this on the 20th because the license expires. The license expires on the 19th, so nothing's gonna work anyway after that. So Frank gonna stop, stop everything on the 20th.We met with the business users and they agreed to the manual process that has to take place. Frank did update the OCM piece in the plan guide and sent that out to them for approval. For the plan guide approval, but regardless it gets.Frank went to Rachel Barone and we're waiting for the sign off. So this will probably be done prior to the 3/31 date. | nightly batch job (EDR0090 | Esposito, Colleen |  |  |  | Production | Component |  | 1 | [6 empty] | Transformation | Transformation: CLT | Transformation: CLT |  | 73KB21001 | Transformation | Transformation: CLT | Transformation: CLT | No | Updates Stat_Feeds_AQS database. Accounting transactions that are passed down to the accounting and stat process. Done through ETL. | No | N/A | Discard | N/A | Stat | Yes | No | Yes | N/A | N/A | 5479 HV AQS | Proxix service, webMethods | Mike Kelly |  | Linda Brockney | Needed until no policy on AQS, need to retain the stat DB as part of the mainframe files. |  | HV CL | Decom and Discard | Decom and Discard | Decom and Discard |  |  |  |  | Yes | SQL2019, Win2019 |  |  | HV
8039 | HV-CLManuscripts | Not Started | 2026-06-30 | HV-CLManuscripts | Joanne Nuzzi |  | HV-CLManuscripts CL Manuscripts (or CL Corporate Form) templates publish from CL Forms Sharepoint library to AgentPortal, UWWB, and AQS.Agent Portal –Supplemental applications and Questionaires, versions, and link to retrieve those forms once selected UWWB – Manuscript Templates – Forms/endorsements, versions, and a link to retrieve forms (same forms used for AQS) AQS – Manuscript endorsement titles and wording is used for AQS forms | Esposito, Colleen |  |  |  | Production | IT Service |  | 1 | [14 empty] | No | This application/component doesn’t have its own database. It uses other databases ‘Renewal Automation’ and ‘APADB’ | No | N/A | N/A | N/A | Support | Yes | No | No | N/A | N/A | 5479 HV AQS | same as HV-AQS | Joanne Nuzzi, Tony Brnic |  | Linda Brockney | This application used to fetch the Manuscript documents stored in NAS share. Basically, Agent Portal and UWWB applications uses these manuscript files which are shown as links within the application and when user clicks on the link the document is downloaded to users local machine. There should be groups which would have access to the NAS share for the users to have permission to download the document. AQS also use these documents when they review policy documents section. They would see these as ‘Manuscript Exclusion’. | De-comm w/ HV-AQS and/or HV-Agent Portal | HV CL | Decom and Discard | N/A | N/A |  |  |  |  | No | SQL2019, Win2019 |  |  | HV
9999 | Commercial Auto | In Progress - Planning | 2026-12-31 | Commercial Auto |  |  | All policy and quote data in BA, this is a supporting app with rates. Would need to archive in scenarios we needed to see and determine rate steps, which would be difficult to do without a policy system. Archive rate steps and archive code that was used for the rate step? (Terry to follow up with Mike Hansen if this comment is correct) 12/18: Will not be making changes anymore. Question around the archive, can we get rid of items that determine rate. Need to follow up on what if anything needs to be captured as part of the rates. Needs a follow up discussion with Terry, Bill M and whoever Terry wants to add. 12/19: per Bill...Commercial Auto (9999) - I didn't think this was related to Commercial Rate Step Maintenance (2887). Not sure if we can find the meeting transcript, but thought Tim was able to pull an explanation from his memory maybe a month or two ago in one of these meetings. Could this be Commercial Auto information going back before the current PCIO mainframe app was rewritten in the late 1990's? All policy and quote data in BA, this is a supporting app with rates. Would need to archive in scenarios we needed to see and determine rate steps, which would be difficult to do without a policy system. Archive rate steps and archive code that was used for the rate step Is this related to CAS - Commercial Auto System? Possibly. There is some items left for this. This needs analysis. | Esposito, Colleen |  | Yes |  | Production | Application |  | 1 | [11 empty] | Transformation | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | VSAM files for storing commercial auto rates and coverage codes | Yes |  | Archive | 10 Years | Support | Yes | Yes | Yes | Hybrid (data Lakehouse + Gacier) | Hybrid (data Lakehouse + Gacier) | 912 Mainframe Package Control | Mainframe Business Auto | Mike Hansen | Scott Grau | Andrea Amick | All policy and quote data in BA, this is a supporting app with rates. Would need to archive in scenarios we needed to see and determine rate steps, which would be difficult to do without a policy system. Archive rate steps and archive code that was used for the rate step |  | PCIO | Policy Data | P&C Data Lakehouse | Inquiry UI, API, Data Extract Process | TBD |  |  |  | No | DB2, VSAM, COBOL |  |  | DM
0000 | Policy Management System (PMS) CalFarm | In Progress - Planning | 2026-03-31 | Policy Management System (PMS) CalFarm | Prasad | 1/20- Angie confirmed Retain data in current format unless business requires access.- We are going to Discard Await formal approval from FARM leadership/legal before moving status to Green.-Already got it as per Angie as per Angie- We are on track for Q1 since we got approval to discard so. | 1/29: Awaiting archival approach documentation. 12/17: Mark is working on getting access. He pulled together a word document on all the pieces and added to the folder. Changed number from 9999 to 0000. Need a follow up on if we need to archive then the question is how we would archive; follow up with Scott. 12/10: Mark Van Wyk to get access to db tables, shut off screen test and look for more documentation on Calfarm. 11/20: Scott feedback •The Calfarm policies are CL and would fall under the CL retention policies, generally indefinite. •If we are not able to interpret the data, then it is of no value and no need to incur costs to retain it •To delete, I think we need the agreement of legal, retention, and business that this can and should be deleted. 11/13: app has policies back to the 1990's, looking to see if there is the ability to decom. CalFarm is more than just Farm policies. Need to determine if this can be inquired into for retrieving data? 03/05/25: needs data archival approach identiified. 04/02/25: all remaining updates on status can be found on the Planner board. LInk is in the 2nd to last column in this spreadsheet. 7/16/25: do we need to keep it or not. Old CalFarm company acquired. Old history would be in this files. See email from 1/28/25 9/15/2025 - Looking to get more info about hwat was migrated. There is vey little for existing documentation. | Esposito, Colleen | Prasad | Yes |  | Production | Application | TBD | 1 | [11 empty] | Early Opportunity | Transformation: PLT & CLT | Transformation: PLT & CLT | Yes | Files and backup tapes from acquisition of CalFarm Insurance 4/1/1999. Migration was during 2000 - 2001 | Yes |  | Archive |  | Policy | No | No | No | No | Glacier | 912 Mainframe Package Control | Claims | Ronda Giedd |  | Lindsey Moyer, Chris Clawson | There were screens available for inquiry after the policies were converted from PMS/PMS2 to the Allied commercial systems. The conversion data is still in the AGISDB2 DB2 tables (CV2T0101_CONV_MAST THRU CV2T0121_P_COINS); since this was over 20 years ago, we do not believe the online transaction or vsam files are in use anymore. Any remaining pieces were just a shell for inquiry of policies prior to conversion. |  | PCIO | Misc. Data and Rules | AWS Glacier | None/Manual, Data Extract Process |  |  |  |  | No | DB2 |  |  | DM
Note on A1: Huckel, Karina: Originally APRM number and now in Servicenow 9999=not available in APRM or Servicenow
Note on B1: Huckel, Karina: Downloaded from SNOW to obtain official name.
Note on C1: Huckel, Karina: 8/1/24 This came out of APRM in 2020. However there were some marked Retired but were not Retired. This may not be the correct state of where it is today. Complete were ones done by working team in 2020ish. Decommission means they were done before 2020 by other teams (older than 2020) Go Forward will not retire. Retired marked before 2020. CURRENT STATUSES USED AFTER CLEANUP Not Started Definitions Not Started: needs decom and not started. Not Started-Early Decom: needs decom and could be started earlier than audits. Not Started-Potential Decom: needs decom but needs further analysis to determine ability to decom before audits. Completed - Year Will be used for decom and the year associated so we can produce graphical representations. Started using this approach in 2024. In Progress
Note on H1: Huckel, Karina: Came from SNOW plus updates from the team
Note on L1: Huckel, Karina: (Y-CL, Y-Farm, Y-Both, N)
Note on M1: Huckel, Karina: Came from APRM and was recorded from the system when pulled in approx 2020
Note on N1: Huckel, Karina: Came from APRM
Note on O1: Huckel, Karina: Field initially from APRM. No longer using the application.
Note on P1: Huckel, Karina: Used for pivot tables
Note on Q1: Huckel, Karina: Originally from HV decom before CL was involved
Note on R1: Huckel, Karina: Originally from HV decom before CL was involved
Note on S1: Huckel, Karina: Originally from HV decom before CL was involved
Note on T1: Huckel, Karina: Originally from HV decom before CL was involved
Note on U1: Huckel, Karina: Originally from HV decom before CL was involved
Note on V1: Huckel, Karina: Originally from HV decom before CL was involved
Note on W1: Huckel, Karina: Originally from HV decom before CL was involved
Note on X1: Huckel, Karina: Originally from HV decom before CL was involved
Note on Y1: Huckel, Karina: Originally from HV decom before CL was involved
Note on Z1: Huckel, Karina: Originally from HV decom before CL was involved
Note on AA1: Huckel, Karina: Originally from HV decom before CL was involved
Note on AB1: Huckel, Karina: Labeled when picked up in 2020
Note on AC1: Huckel, Karina: Labeled when picked up in 2020
Note on AD1: Huckel, Karina: Labeled when picked up in 2020
Note on AE1: Mulcahy, Timothy (Tim): Y = Yes, app has DB N = No, not a DB in app If it has a DB, then it would need to archive
Note on AF1: Mulcahy, Timothy (Tim): Identify type of data in the app, describe the database
Note on AG1: Mulcahy, Timothy (Tim): System that owns the data, true source of the data Y = This app is the system of record N= This app is not the system of record
Note on AH1: Mulcahy, Timothy (Tim): What system is the system of record? App name should be the same as ServiceNow/APRM N/A = no data in app
Note on AI1: Mulcahy, Timothy (Tim): Discard = delete data Archive = retain data N/A = no data in app
Note on AJ1: Mulcahy, Timothy (Tim): Per RIM guidelines N/A = no data in app Worked with Retention Leader to gather this (part of legal). If there is an active Legal Hold, you cannot delete the data.
Note on AL1: Huckel, Karina: Is the access to the app an API or Service?
Note on AM1: Huckel, Karina: Does it have a user iterface? Is it customer and/or associate facing?
Note on AN1: Huckel, Karina: Is it batch or bulk that data is updated?
Note on AO1: Huckel, Karina: How we use Glacier and how the data is accessed real time or multi-day? Need to determine if this field is needed.
Note on AP1: Mulcahy, Timothy (Tim): Per RIM guidelines N/A = no data in app Lakehouse = Hercules. S3 = Cloud Store
Note on AR1: Mulcahy, Timothy (Tim): Identify systems that rely/use data from this app. Name should match the ServiceNow/APRM name for traceability
Note on AV1: Huckel, Karina: From the big meeting, notes from the SEPM
Note on AX1: Huckel, Karina: High level category
Note on AZ1: Huckel, Karina: Is S3 and Glacier the same?
Note on BD1: Huckel, Karina: Labor, NonLabor and Consumption Cost
Note on D3: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O3: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D4: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O4: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D5: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O5: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D6: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O6: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D7: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O7: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D8: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O8: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D9: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O9: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on D10: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on O10: Huckel, Karina: Archival and retention dependencies need to be defined.
Note on C12: Huckel, Karina: 1/11/25: John indicates Decom
Note on C14: Huckel, Karina: 1/11/25: John indcated decom
Note on C15: Huckel, Karina: 1/11/25: John indicates Go Forward until BONDS move off MF
Note on AZ16: Huckel, Karina: Need further discussion
Note on BA16: Huckel, Karina: Need further discussion
Note on C17: Huckel, Karina: No new business and renewals, shut down by the end of 2025. Changing algorhytms to calculate the premium. We need to discuss the risk of taking this down vs just leaving it up. After WC Rate Reviews are complete, then this could be shut down.
Note on AI17: Huckel, Karina: Needs analysis
Note on AJ17: Huckel, Karina: Need to evaluate
Note on AO17: Huckel, Karina: Need to evaluate
Note on AP17: Huckel, Karina: Need to evaluate
Note on BA17: Huckel, Karina: Need to evaluate
Note on C18: Huckel, Karina: 1/11/25: Jamie indicates decom
Note on C20: Huckel, Karina: 1/11/25: John indcated decom
Note on C21: Huckel, Karina: 1/11/25: John indcated decom
Note on D28: Huckel, Karina: All MF will come down at the same.
Note on O28: Huckel, Karina: All MF will come down at the same.
Note on AP28: Huckel, Karina: Needs discussion with Hercules MF - open question on VSAM
Note on BD28: Huckel, Karina: Colleen to break down high level and provide a number.
Note on D29: Huckel, Karina: All MF will come down at the same.
Note on O34: Huckel, Karina: Need to validate correct date
Note on AP36: Huckel, Karina: Add as TBD
Note on AJ37: Huckel, Karina: No longer have Zoom
Note on D38: Huckel, Karina: Dependency on Claims archival approach and Loss Run reports. Moving from 7/1/25 to 4/1/27
Note on E42: Huckel, Karina: Need Terry to validate
Note on AI45: Huckel, Karina: Account level data
Note on AG46: Huckel, Karina: HV-AQS
Note on AI46: Huckel, Karina: Ok to archive to Imageright or archive to tool
Note on AJ47: Huckel, Karina: AQS Source Code
Note on BF48: Huckel, Karina: Dependency on Experen
Note on B57: Huckel, Karina: Terry to review with Laurie Berness
Note on AL66: Huckel, Karina: new user, batch runs to update accesses to grant security role in AQS
Note on BF67: Huckel, Karina: Infragistics related contract was not renewed.
Note on AI69: Huckel, Karina: Terry to follow up
Note on AL72: Huckel, Karina: within itself an API
Note on AG77: Huckel, Karina: HV-AQS
Note on AG78: Huckel, Karina: HV-AQS

## Master from RFP phase - Old (hidden)
App Id | Application Name | Decom Target Complete | Application Description | Application Category | Database or Data Store | System of Record | Data Owner (System) | Access - API/Service | Access - UI | Access - Batch/Bulk | Application Suite Dependency | Dependencies (App Level) | Infrastructure | Legacy Suite
451 | Pathway (DSM) | 12/31/26 | Maintains customer information at the name and address level | Application | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | PCIO
909 | Mainframe Business Auto | 12/31/26 | Policy processing system for Business Auto Policies. | Application | Yes | Yes | Mainframe Business Auto | Yes | Yes | Yes | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | TBD | PCIO
910 | Mainframe General Liability (GLS) | 12/31/26 | Policy Processing system for General Liability policy types. | Application | Yes | Yes | Mainframe General Liability (GLS) | Yes | Yes | Yes | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | TBD | PCIO
911 | Mainframe Commercial Property | 12/31/26 | Policy processing system for the Commercial Property Line of Business | Application | Yes | Yes | Mainframe Commercial Property | Yes | Yes | Yes | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | TBD | PCIO
912 | Mainframe Package Control | 12/31/26 | Policy processing system for the commercial package control system. | Application | Yes | Yes | Mainframe Package Control | Yes | Yes | Yes | 912 Mainframe Package Control | CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | TBD | PCIO
921 | Mainframe Farm | 12/31/26 | Policy processing system for Farm policies | Application | Yes | Yes | Mainframe Farm (WINS) | Yes | Yes | Yes | 912 Mainframe Package Control | CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | TBD | PCIO
923 | Mainframe Business Owners (SBO) | 12/31/26 | Policy Processing System for Commercial Business Owners policies. | Application | Yes | Yes | Mainframe Business Owners (SBO) | Yes | Yes | Yes | 912 Mainframe Package Control | PAK, CLaims, FLEX billing, Agent Master file, Forms System, Marshall & Swift, Property rates, Blackbox | TBD | PCIO
924 | Mainframe Policy Entry | 12/31/26 | Policy Processing System for Inland Marine, Crime, Commercial Umbrella, and Personal Umbrella policies | Application | Yes | Yes | Mainframe Policy Entry | Yes | Yes | Yes | 912 Mainframe Package Control | PAK, Claims, FLEX billing, BAM billing, Agent Master file, Forms System | TBD | PCIO
926 | Mainframe Workers Comp | 12/31/26 | Policy processing systems for Workers Compensation policies. | Application | Yes | Yes | Mainframe Workers Comp | Yes | Yes | Yes | 912 Mainframe Package Control | CLaims, FLEX billing, Agent Master file, Forms System, Blackbox | TBD | PCIO
940 | Allied Endorsements | 12/31/26 | Repository of policy endorsements available to Service Advantage policy systems, billing and TCS | Application | Yes - VSAM | Yes | TBD | No | Yes | No | 912 Mainframe Package Control | SA/PCIO, TADA jobs, DR jobs, UWSW0082 - Rerate running every week. | TBD | PCIO
1025 | CIQ Agent Center | 12/31/25 | Commercial Internet Quoting(CIQ) is the agent facing commercial quoting web site. Supported LOBs are PAK, BOP, BA, Property, GL, WC and farm. CIQ is the data gathering function and makes use of mainframe rating engines for developing premium. Other components of CIQ are proposal, App and submit for issue. CL Processing Center Users and Underwriters receive CIQ New Business into E-File. | Application | Yes | Yes | CIQ Agent Center | No | Yes | No | 912 Mainframe Package Control | TBD | Distributed (web app) | PCIO
1208 | Alpha Search | 12/31/26 | Maintains customer information by policy at the customer name and address level | Application | No | Yes | TBD | No | Yes | No | 912 Mainframe Package Control | Claims, PCIO, SA, Bonds | TBD | PCIO
1213 | Microfilm Indexing | 03/31/26 | Maintains location of stored Micro Filmed policies | Application | No | Yes | TBD | No | Yes | No | Other |  | TBD | PCIO
1214 | Error Message | 12/31/26 | Maintains a VSAM based common message file for the Service Avantage policy systems. The policy system requests a type of message and gets back a specific error correctly worded. | Application | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | PCIO
1220 | Policy Reload | 12/31/26 | Central point for customers to request a policy to be reloaded from back up files onto online policy systems. | Application | No | No | TBD |  |  |  | 912 Mainframe Package Control | PCIO, SA | TBD | PCIO
1418 | Policy Expirations | 03/31/26 | Process expiring policies. EXP on a monthly basis(end of month processing(EOM)) selects policies that are 105 days or less from expiring and generates reports such as NON-RENEWLs list, EXPIRATION list, etc. EXP also creates a monthly file of expiring policies that gets processed daily and any policy that is 73 days or less from expiring is written to EFILE and EFILE is sent to Columbus for further processing. | Application | No | Yes | TBD |  |  |  | 912 Mainframe Package Control | PCIO, eFile | TBD | PCIO
1551 | Farm Bureau | 12/31/25 | Maintains Farm Bureau application information and sends it to Farm Bureaus, keeps membership information from Farm Bureaus for the purpose of giving discounted rates to members. | Application | Yes | No | TBD |  |  |  | 912 Mainframe Package Control | TBD | DB2 Tables | PCIO
1660 | Commercial Umbrella | 03/31/26 | Online calculator for Commercial Umbrella policies. This application is being used by Commercial Underwriters in PCIO Exclusive and Independent. | Application | Yes | Yes | TBD | Yes | Yes | Yes |  |  | SQL Server | PCIO
2887 | Commercial Rate Step Maintenance | 03/31/26 | Rate Step Maintenance Application used by Commercial to maintain rate Steps for BOP, BA, & Farm. Also, this project may go with a Minor Release sometime after the PC4.0-08 Release. | IT Service | Yes | Yes | MF PCIO - PAK | No | No | No | 912 Mainframe Package Control |  | TBD | PCIO
2918 | CCRF Agent Center | 12/31/26 | Allows agents to submit Commercial Change Requests via the Agent Center. | Application | Yes | No | CCRF Agent Center |  |  |  | 912 Mainframe Package Control |  | TBD | PCIO
4245 | Commercial Mainframe COI | 12/31/26 | Commercial Mainframe COI processing/printing. | Infrastructure Service | No | No | MF PCIO - PAK | Yes | No | Yes | 912 Mainframe Package Control |  | TBD | PCIO
4260 | Commercial Renewal Reporting DB | 03/31/26 | PCIO - Stores the U/W renewal rules and statistics to report against it. The database we own is for business driven Brio Reports measuring policies that Renew without being touched by underwriters. It also measures renewal errors that are triggering Underwriter activities to determine if the renewal rules need to be adjusted to meet the business needs. There are also reports that measure regional office renewal volume and premium. | Component | Yes | No | TBD |  |  |  | 912 Mainframe Package Control | TBD | TBD | PCIO
4261 | Commercial Underwriting DB | 03/31/26 | Marketing/Pricing/Underwriting Database - Monitors IA Agents productivity and IA Agents Quote to Issue Premium Variations. Owned by Underwriting. Web front-end that is owned by CIQ. Also produces and stores reports for Marketing, Pricing and Underwriting. Includes several BRIO queries. Underwriting owns BRIO queries | Component | Yes | TBD | TBD | TBD | TBD | TBD | 912 Mainframe Package Control | TBD | TBD | PCIO
5281 | HV-Accounts Receivable | 04/01/27 | Accounts Receivable Also known as Agent Balance and Reconciliation Recieves feeds from Billing System and PNC lockbox | Application | Yes | Yes | 5281 HV-Accounts Receivable | No | Yes | No | 5296 HV Legacy Billing Systems | 5296 HV-Legacy Billing Systems | TBD | HV
5282 | HV-Agency Bill Account Current | 04/01/27 | This application is used to bill agents (monthly) and track their balances due the company. | Application | No |  | 5296 HV-Legacy Billing |  |  |  | 5296 HV Legacy Billing Systems | 5281 HV- Accounts Receivable | TBD | HV
5283 | HV-Agency Systems | 04/01/27 | Includes Agency Performance, Agency Commissions, Agency Master, Expiration, and Mainframe Portion of Agency Download | Application | Yes | Yes | 5283 HV Agency Systems | 5479 HV AQS | all HV systems | TBD | HV
5284 | HV-Bank Reconciliation | 04/01/27 | Application that matches and compares figures from accounting records against those presented on bank statements | Application | No |  | 5302-HV-Online Draft |  |  |  | 5296 HV Legacy Billing Systems |  | TBD | HV
5285 | HV-CCMS & Score | 04/01/27 | Used for assignment of policy numbers for manual policies and to link them in the Insured Account Database. In addition, if any of these policies are brought into automation at renewal, CCMS would be used to set up the renewal conversion. | Application | Yes | Yes | 5285-HV-CCMS & Score | No | No | No | 5303 HV Stat | HV-Midstream Stat | TBD | HV
5287 | HV-Checkwriter | 04/01/27 | Application used to create and log check printing information for claims, direct bill refund, and direct bill commission statement checks | Application | Yes |  | 5302-HV-Online Draft | No | Yes | No | 5297 HV Legacy Claims | Nationwide GL, HV Claims | TBD | HV
5290 | HV-Direct Bill Commission | 04/01/27 | Monthly application that creates agent's commission payments for Direct Bill policies. | Application | No | [5 empty] | 5303 HV Stat | HV-Stat | TBD | HV
5292 | HV-Documerge | 04/01/27 | Oracle document generation product that supports legacy output from mainframe | Application | Yes | TBD | AQS, Billing, Claims, NF(Life), Finance, PL Legacy | No | Yes | No | 5479 HV AQS | Imageright, AQS, DCT, Billing, Claims, NF(Life), Finance, PL Legacy | HV Mainframe | HV
5294 | HV-FRS | 04/01/27 | Application that handles policy by policy facultative reinsurance | Application | No | No |  |  |  |  | 5303 HV Stat | HV-Stat | TBD | HV
5296 | HV-Legacy Billing Systems | 04/01/27 | The Agency bill system supports the monthly billing and collection from each agent on a net premium basis (premium less commission). The agency bill premiums are for accounts of $50,000 or more. The system provides a history of collection activity and provides detailed Information on all outstanding unpaid premium by agent.The Direct Bill system supports the billing and collection directly from the customer, of P&C insurance premium written by Harleysville Insurance operations. | Application | Yes | Yes | 5296 HV-Legacy Billing | No | Yes | No | 5296 HV Legacy Billing Systems | Policy Systems Agent Portal | TBD | HV
5297 | HV-Legacy Claims | 04/01/27 | Harleysville Claims System that supports the entry of claims from all lines of business for Harleysville policies. | Application | Yes | Yes | 52970HV-Legacy Claims | No | Yes | No | 5479 HV AQS | HV-AQS, HV-Duck Creek, HV-PL legacy | TBD | HV
5302 | HV-Online Draft | 04/01/27 | Application which keeps track of the status of checks (issued, cashed, stop pays, etc) | Application | Yes | Yes | HV-Online Draft | No | Yes | No | 5297 HV Legacy Claims | HV- Claims, HV- Checkwriter | TBD | HV
5303 | HV-STAT | 04/01/27 | Acct/Stat edit and HUB Monthly premiums and losses ISO and CAR reporting Data Calls Tax TACT | Application | Yes | Yes | 5303-HV Stat | No | No | No | 5479 HV AQS | HV- AQS, HV-Duck Creek, HV- PL Legacy, HV-Stat Browser | TBD | HV
5305 | HV-TACSTAT/STAT | 04/01/27 | Application that creates files for Actuarial that contain a subset of the data fully stored on the monthly premium and loss stat files | Utility | Yes | No | 5303-HV Stat | No | No | No | 5303 HV Stat | HV-Stat, HV-Agency Systems | TBD | HV
5306 | HV-Personal Lines Legacy | 04/01/27 | Policy adminstration for Personal lines Homeowners, Automobile, Blanket Excess, Inland Marine, and Shipmate on the mainframe | Application | Yes | Yes | HV-Personal Lines Legacy | Yes | Yes | Yes | Mainframe Retirement Holistically | TBD | MF | HV
5307 | HV-Commercial Lines Legacy | 04/01/27 | App will be decom with MF. | Application | Yes | Yes | HV-Commercial Lines Legacy | Yes | Yes | Yes | Mainframe Retirement Holistically | HV-Commerial Lines Legacy | MF | HV
5308 | HV-Commercial Lines DMV | 04/01/27 | Used for reporting vehicle information to various state DMV agencies | Utility | Yes | No | 5307 - HVCommercial Lines |  |  |  | 5479 HV AQS | TBD | TBD | HV
5309 | HV-Midstream Stat Creation | 04/01/27 | Creation of Accouting/Stat to be processed downstream systems | Application | No | No |  |  |  |  | 5479 HV AQS | HV-AQS, HV-Claims, HV-Duckcreek, HV PL Legacy | TBD | HV
5385 | HV-AccessWeb - UWRulesEngineWeb App | 12/31/26 | User interface for accepting and responding to binding authority questions an rules. | IT Service | Yes | Yes | HV-URE, HV-Quote, IADB | No | No | No | 5479 HV AQS | HV-AQS | TBD | HV
5390 | HV-Audit Upload Manager | 12/31/26 | Audits discrepancies in policy premium caused by quote and billing date issues. | Application | Yes | No | AQS |  |  |  | 5479 HV AQS | ACE Audit Upload, HV-AQS, Batch Cycle | win2012, SQL 2012 | HV
5395 | HV-Claims Portal | 12/31/26 | Web based portal to interface with the mainframe to report on claims, provide notifications, diary entries and a group of shortcuts for claims personnel. | Application | Yes | No | 5395-HV-Claims Portal |  |  |  | 5297 HV Legacy Claims | HV-ClLegacyService | Win2019, SQL 2019 | HV
5405 | HV-Policy Browser | 07/01/27 | Claims adjuster views into consolidated policy data for both commercial and personal lines | Application | No | No | HV-Policy ODS (Services and Database) |  |  |  | 5297 HV Legacy Claims | HV-Claims | TBD | HV
5406 | HV-Policy ODS (Services ad DB) | 07/01/27 | Set of web services for searching the Policy ODS and retrieving policy data in standard Acord format. Originally built for HV Guidewire project for coverage verification. | Component | Yes | Yes | HV AQS, HV PL Legacy, HV Duck Creek, HV Expiration | No | No | No | 5297 HV Legacy Claims | HV-Claims, HV-ServiceCenter, HV Policy Browser | TBD | HV
5408 | HV-Renewal Automation | 04/01/27 | Renewal automation is a batch process (.net/sq.) that runs in the background on a nightly basis. The job gathers data from both legacy and AQS and flags 90 day expiration candidates for renewal. Some can issue automatically, others are flagged for manual intervention. Web Methods is the intermediary link between all the function. | Component | Yes | No | AQS |  |  |  | 5479 HV AQS | HV-AQS, Batch Cycle | win 2019 SQL and Windows, batch | HV
5412 | HV-Underwriter Awareness Form | 12/31/26 | Tool for claims to notify underwriters to review policies with large losses | Application | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | HV
5413 | HV-Underwriting Rules Engine (URE) | 12/31/26 | The tool used to assign rules around potential customer's provided information. This rules engine will determine if the policy can be bindable, determining account-level renewal authority, determing applicable product, system and line of business.. | Application | Yes | No | HV-URE, HV-Quote, IADB | No | Yes | No | 5479 HV AQS | HV-AQS, HV-Agent Portal | Win2019, SQL 2019 | HV
5415 | HV-ACE - Premium Audit | 12/31/26 | Premium audit. Commercial policy so much for the year. Premium is estimated. Your premium should be or less or more. Feeds from policy systems | Third Party Application | Yes | Yes | HV AQS | No | No | No | 5479 HV AQS | HV-AQS, HV-AuditWin Plus - Premium Audit Folder in ImageRight | Win2019, SQL 2019 | HV
5418 | HV-Agency Download | 04/01/27 | Nightly process that sends policy data (PL and CL) or Claims data to an agencies' management system. Monthly process that send direct bill commission statement data to an agencies' management system. | Application | Yes | No | HV-Legacy Claims (5297) |  |  |  | 5297 HV Legacy Claims | HV - Legacy Claims | .NET, SQL 2016 | HV
5426 | HV-Clarify | 04/01/27 | CRM Tool for Contact Center and Service Center | Utility | Yes | No | HV - Billing | Yes | No | Yes | 5296 Legacy Billing System | AQS, DCT, Billing, | WIN 2016, SQL 2019 | HV
5427 | HV-COGNOS | 04/01/27 | Query report and analysis capabilities for all type of data. A component of COGNOS is Analyst Studio, which also needs to be tested whenever any type of upgrade occurs. | Application | Yes | No | HV-Legacy Claims (5297) |  |  | Yes - feeds to Cognos | 5297 HV Legacy Claims | HV - Legacy Claims, Policy ODS | WIN 2016, SQL 2016 | HV
5432 | HV-DocuMaker | 04/01/27 | Document management system supporting output from Commercial and Personal lines (non-mainframe). It is used to create agency bill schedules, claims FNOL, audit mailers, and personal lines output (decs, forms, cancellations, ID cards, etc.). | Application | Yes | TBD | AQS, DCT, and Claims |  |  |  | 5479 HV AQS | AQS, DCT, and Claims | Distributed | HV
5442 | HV-ImageRight | 07/01/27 | Imaging and workflow management system from Vertafore. This system is used to capture policy, underwriting and claims workflow and documentation. Images can be introduced into this system in various ways such as scanning, printing, and email. | Third Party Application | Yes | Yes | ImageRight | Yes | Yes | Yes | 5479 HV AQS, DCT, Billing, Claims, ACE Premium Audit | AQS, DCT, Billing, Claims, ACE Premium Audit | Win2019, SQL2019 | HV
5444 | HV-Informatica | 07/01/27 | ETL Tool | Third Party Application | Yes | No | HV - Informatica | Yes | Yes - Admin Interface | Yes | 5479 HV AQS, DCT, Billing, Claims, Stat. Actuarial | Processes all HV Data | Win2019, SQL2019 | HV
5454 | HV-Rules Maintenance Application (RMA) | 12/31/26 | Development platform to write business rules. These rules are then used by the URE application. | Desktop Application | Yes | Yes | HV-URE | No | Yes | No | 5479 HV AQS | HV-URE | Desktop | HV
5458 | HV-Stat Browser | 04/01/27 | View all premium accounting and stat and loss stat records. Also allows for manual entry of premium records. Additional phases include manual loss stat entry, error correction, and real time editing of entered and corrected records. | Application | Yes | No | HV-Stat | No | Yes | Yes | 5303 HV Stat | HV-Stat | Win2019, SQL2019 | HV
5463 | HV-UWWB - Underwriter WorkBench | 12/31/26 | This is a Workbench for task completion. documentation, and making underwriting decisions for Underwriters. Processing uses this workbench for task completion and documentation as well. | Application | Yes | Yes | 5463-HV-UWWB - Underwriter WorkBench | No | Yes | No | 5479 HV AQS | HV-Cognos, HV-Underwriting Rules Engine (URE), SSRS Reports, HV-Core Integration Svcs, HV-Image Right, HVAIS | TBD | HV
5464 | HV-VOIP Services | 04/01/27 | Web service to provide insured and agent data back to the agent or call center representative. | IT Service | No | No | HV -Clarify | Yes | No | No | 5296 Legacy Billing System | Clarify | WIN2019 | HV
5465 | HV-webMethods | 07/01/27 | webMethods is the backbone of Harleysville SOA- and EDA-enablement and provides support for HTTP/s, FTP/s and SMTP transport protocols, messaging, SOAP web service, synch/asynch, service orchestration, logging, standardized error handling, etc. The webMethods Integration Platform enables realime and batch service integration between Harleysville's core insurance applications on both the Windows and IBM mainframe environments. SOA application. | 3rd Party | Yes | No | HV - All | Yes | Yes - Developer IDE | No | HV-Duck Creek, HV-AQS, HVAgency Portal, HV-ImageRight | HV-Duck Creek, HV-AQS, HV-Agency Portal, HV-ImageRight | WIN2022, SQL2019 | HV
5478 | HV-Agent Portal | 12/31/26 | Portal for agents to view his book of business, begin new business transaction and launch into applicable policy systems, gather agency reports, etc. | Application | Yes | Yes | HV AQS | Yes | Yes | Yes | 5479 HV AQS | HV-Agent Portal, HV-IADB, HVImageRight, HV-AIS, HV-U279, HVUnderwriting Rules Engine (URE), HV - Harleysville Underwriting Guide, Claims Service, SSRS Reports, Account Propsal Services, Policy Holder Reports DB, HV Duck Creek, HV AQS, HVMainframe CL, HV-WebMethods, HVMelissa, HV Informatica, HV Legacy Billing, | Win2019, SQL2019 | HV
5479 | HV-AQS | 12/31/26 | Policy administration for commercial lines. | Application | Yes | Yes | TBD | Yes | Yes | Yes | 5479 HV AQS | Policy Migration Services, HV Access Express, webMethods, agent portal | Win2019, SQL2019 | HV
5567 | HV-Starteam | 12/31/26 | Source management product that we have licensed for AQS. Need to save the source code. | 3rd Party | Yes | Yes | Starteam | Yes | Yes | No | 5479 HV AQS | AQS | Win2019, SQL2019 | HV
5570 | HV-Predictive Modeling | 12/31/26 | Provides underwriting scoring on accounts based on policy information | Application | Yes | No | HV-Predictive Modeling | Yes | No | Yes | 5479 HV AQS | HV-AQS, HV-Quote Services, HV-Agent Portal | Win2019, SQL2019 | HV
5666 | HV-AIS | 12/31/26 | Agency SQL database and services used throughout organization for agency validation. | Component | Yes | No | HV- Agency Systems | Yes | No | Yes | 5479 HV AQS | AQS, DCT, Agent Portal. | Win2019, SQL2019 | HV
5668 | HV-Harleysville Enterprise Web Services (HEWS) | 12/31/26 | Grouping of services, an application service function provided using network address over the web enabling communication between two systems. | IT Service | No | No |  | Yes | No | No | 5479 HV AQS | HV-IADB, | Win2019, SQL2019 | HV
5670 | HV-Question Answer Service | 12/31/26 | Main service component for the URE application to determine questions to ask and then save responses Dependent on adding products. | Component | Yes | Yes | HV-Question Answer Service | Yes | Yes | No | 5479 HV AQS | HV-AQS, Agent Portal, HV URE | Win2019, SQL2019 | HV
5712 | HV-Proxix (Corelogic) | 12/31/26 | Vendor supplied Geo coding and territory information used by Duck Creek (Core Logic) and Commercial Lines (AQS) | Third Party Application | Yes | No | HV-Proxix (Corelogic) |  |  |  | HV - Commercial Lines Legacy | HV - AQS | SQL 2019 | HV
5713 | HV-Melissa (address check) | 12/31/26 | Vendor supplied information used to validate and scrub addresses for Duck Creek quotes and policies. | 3rd Party | No |  | HV-Melissa | Yes | No | No | 5479 HV AQS | HV-Duck Creek, HV-AQS | Win2016 | HV
5717 | HV-Active PDF | 12/31/26 | HV-Active PDF | Component | Yes | No | HV-AQS | Yes | No | Yes | 5479 HV AQS | HV-Question Answer Service, HV Bill Matrix, HV EFT Services, HV BL registration DB, HV ISOMatrixHGM DB, HV ASPSessionState DB, Account Register(Global IADB), Clear quote, Agent Center, Policy Center, Experian, Recaptcha | Win2019, SQL2019 | HV
5720 | HV-UW Assignment | 12/31/26 | Web application for updating workflow routing within Image Right for Commercial Lines | Component | Yes | No | HV-Imageright | Yes | Yes | No | 5479 HV AQS | TBD | Win2019, SQL2019 | HV
6010 | HV-Expiration | 04/01/27 | Policy / Renewal tracking application | Application | Yes | No | 6010-HV-Expiration | Yes | Yes | Yes | 5479 HV AQS | most HV systems | MF, VSAM, CICS | HV
6096 | HV-AQS Batch Print | 12/31/26 | This is a custom .net application to package HVAQS Policy Output utilizing Active PDF. This component provides the bar coding on documents for Finishing. It also generates a transactional cover letter per Billing Account,applies the NY ID Card PDF417 bar code and packages new business and renewal output with the Agency Bill Schedule | Component | Yes | No | HV-AQS | No | No | Yes | 5479 HV AQS | HV-AQS , HV-QDIRECT | Win2019, SQL2019 | HV
6105 | HV- Service Center Workbench | 11/30/25 | Application used by internal users in the Customer service center as Servicing representatives on behalf of our agents. | Application | Yes | Yes | HV-AQS | Yes | Yes | Yes | 5479 HV AQS | HV-Cognos and SSRS reports, HV-Core Integration Svcs, HV-Billing Svcs, PolicyODS service, Claims Service, getAgencyPerformanceInfo (ETL Service) | Win2019, SQL2019 | HV
6393 | HV-Agency Licensing | 04/01/27 | Capturing of agency and producer information from CMS G2 onto a SQL database, which is enriched with demographic and banking info from the Harleysville Agency Master file, providing agency licensing validation to Harleysville systems and a regular ETL feed to Nationwide DPIM and AMF systems | Component | No | No | ThirdParty Vertofore |  |  |  | 5479 HV AQS | AQS, DCT, Agent Portal. | Win2019, SQL2019 | HV
6394 | HV-ISO Reporting | 04/01/27 | Insurance Service Organizations | Utility | No |  | AQS | No | No | Yes | 5303 HV Stat | HV-Stat | MF VSAM, SFTP | HV
6395 | HV-Table Monitor | 04/01/27 | Mainframe system which enables users to maintain master data such as comany code, company name, company address, state abbreviations, agencies and branches. | Application | Yes | No | 6395-HV-Table Monitor | No | No | Yes | All MF Apps | All MF Apps | DB2 | HV
6397 | HV-ISO PPC | 12/31/26 | 3rd Party data source that integrates with Duck Creek and CL AQS to supply Property Protection Class base on geographic information | Third Party | Yes | No | HV-ISO PPC | Yes | No | Yes | 5479 HV AQS | HV-AQS HV-Duck Creek | Win2019, SQL2019 | HV
6401 | HV-Ivans | 12/31/26 | Agents' mailboxes & software tool used to build DL scripts | Utility | No | No | HV-Claims | No | No | Yes | 5297 HV Legacy Claims | HV-Agency Download HV-Billing | Win2016 | HV
6405 | HV-CoreLogix Quarterly Update | 12/31/26 | Comparison Utility CoreLogix is a leading provider of consumer, financial and property information, analytics and services to business and government | Third Party | No | No | HV-Proxix (Corelogic) | No | No | Yes | 5397 HV Duck Creek | HV-AQS HV-Duck Creek | Win2019 | HV
6408 | HV-Bill Matrix | 04/01/27 | 3rd Party Vendor for on line payments -- an online payment system operated by BillMatrix Corporation that is designed to accept payments | Third Party | No |  |  | No | No | Yes | 5479 HV AQS | HV-Direct Bill 5478 HV-Agent Portal | SFTP, VSAM | HV
6422 | HV-Account Proposal | 12/31/26 | Application that generates Account Proposal for CL agents | Component | Yes | No | HV-AQS | Yes | No | No | 5479 HV AQS | HV-DOCUMAKER, AQS, HIEDMS | HV
6424 | HV-AuditWin Plus | 12/31/26 | Utility software used by field auditors to manage audit assignments, inventory and scheduling. Audit assignments are downloaded to the AuditWin Plus (formerly known as Field Manager) from Audit Control Environment (ACE). | Component | No | No | HV - ACE Premium Audit | No | No | Yes | 5479 HV AQS | HV- ACE \ - Premium Audit | Download | HV
6447 | HV-STAT loss triangles | 04/01/27 | Series of programs and calculations using webFocus and other tools to calculate IBNR and loss picks. IBNR, or incurred but not reported losses, are an estimate of the amount of an insurer's liability for claim-generating events that have taken place but have not yet been reported to the insurer or self-insurer. | Utility | No |  |  | No | Yes | No | 5303 HV Stat | HV-Stat | CICS, Cobol | HV
6452 | HV-ACCESS Collections | 04/01/27 | 3rd Party Vendor for collections agency -- With Access Collections, LLC you'll have the skill and expertise needed to collect your consumer debt, delivering improved cash flow and reduced days outstanding. | Third Party | No |  |  | No | No | Yes | 5296 HV Legacy Billing Systems | HV- Accounts Receivable | SFTP, Flat File | HV
6453 | HV-PNC Bank Feed | 04/01/27 | 3rd Party Vendor for agent sweep screens - PNC/Wells Fargo Bank | Third Party | No | [5 empty] | 5296 HV Legacy Billing Systems | HV-Direct Bill, HV-Life | SFTP, Flat File | HV
6500 | HV-AQS User SecurityLoad | 12/31/26 | Utility to load new NW/Harleysville agents as Users to AQS. | Component | Yes | No | AQS | Yes | Yes | Yes | 5479 HV AQS | HV-AQS | CICS, win2019, SQL2019 | HV
6512 | HV-AQS - Doc Utility | 12/31/26 | Doc Utility is used by AQS Configuration Analysts and Developers for adding and updating document data. | Component | Yes | No | AQS | Yes | Yes | No | 5479 HV AQS | HV-AQS | win2019, SQL2019 | HV
6591 | HV-Miscellaneous CICS Applications | 04/01/27 | Various CICS Applications includingTable MonitorCommission ErrorsUnderwriter AssignmentPolicyholderPolicy Number AssignmentHLS/MFC/Penn Mutual ArchiveRMV SystemSMMI File Maintenance | Application | No | No | HV-Miscellaneous CICS Applications | Yes | Yes | Yes | 5479 HV AQS | Various CICS Applications including: Table Monitor Underwriter Assignment Policyholder Policy Number Assignment HLS/MFC/Penn Mutual Archive SMMI File Maintenance. Operator Control System (OPID File) Also included are SHRD and SYSP ChangeMan members. | CICS, COBOL, VSAM, DB2 | HV
6650 | HV-WC Reporting | 12/31/26 | Used for reporting WC commercial policy to NCCI and other rating bureaus twice per week. | Application | Yes | No | AQS | Yes | No | Yes | 5479 HV AQS | HV-AQS, Informatica, Prod Cycle, NonRenew web service | win2019, SQL2019 | HV
6859 | HV - eForms Generation App | 12/31/26 | Generates ACORD COI (Certificate of Insurance) and EOP (Evidence of Property) forms currently used by the Service Center group. Minimal user entry required for form completion | Application | Yes | Yes | HV-eForms Generation App | Yes | Yes | No | 5479 HV AQS |  | win2019, SQL2019 | HV
7558 | HV-Hazard Grade Matrix (HGM) | 12/31/26 | Application used by underwriters to get the Matrix Grade; also used by Product staff to update information for use in Underwriting decisions via an admin page. | Component | Yes | Yes | HV-HGM | Yes | Yes | No | 5479 HV AQS |  | win2019, SQL2019 | HV
7625 | HV-OpenText AFP Index-TiffConvertView | 04/01/27 | Utility to View AFP files to configure indexing, create index file and convert afp files to tiff image for import into HV-ImageRight. | Utility | No | No | ImageRight | No | Yes | No | 5479 HV AQS | Documerge, ImageRight | win11 | HV
7725 | HV-SQLSERVERSERVICES | 04/01/27 | SSRS, SSIS, SSAS | Utility | Yes | No | AQS | Yes | Yes | Yes | 5479 HV AQS | AQS, Informatica, Claims, Billing | SQL2019, Win2019, | HV
7814 | HV-CL Insured Account search tool | 12/31/26 | CL Insured Account name search tool used by processing groups for a lookup of account and billing account \# info. A Link to Image Right is included | Utility | No |  | CL Insured Account DB (IADB) | Yes | Yes | No | 5479 HV AQS | AQS, Agent Portal, Workbench, | SQL2019, Win2019 | HV
7866 | HV-U279 Processing Form | 12/31/26 | New business and renewal communication tool between Underwriting and Processing. Supports instructions for setting up billing and policies. Tool to generate a form for completion and save to Image Right for future updates. | Utility | No | No | N/A | Yes | Yes | No | 5479 HV AQS | HV-Underwriter Workbench | SQL2019, Win2019 | HV
7944 | HV-PowerShell-BuildDeployment-Scripts | 12/31/26 | Jenkins is the tool we use for developers to initiate the PowerShell scripts to do the build/deployment - This will be used to deploy AQS and WebMethods code (confirm if this is already gone, switch to urban code deploy) | Component | No | No | N/A | Yes | No | No | 5479 HV AQS | AQS, Starteam | win2019 | HV
7952 | HV-HIEDMS | 12/31/26 | The go-between (entry & exit points) component used by applications that want documaker to generate a document. Used by Agent Portal, UWWB, DCT and Upload | IT Service | No | No | N/A | Yes | No | No | 5479 HV AQS | Documaker | SQL2019, Win2019 | HV
7954 | HV-Core Integration Svc | 12/31/26 | Collection of web services utilized by numerous applications. A large number are used by UWWB and AQS NB and Renewal process | IT Service | No | N/A | N/A | Yes | No | No | 5479 HV AQS | AQS, HV-IADB, Quote Service | SQL2019, Win2019 | HV
7955 | HV-MVR Services | 04/01/27 | Used by AQS and UWWB to request/access driver MVR records. MVR records are then stored in ImageRight. Also contains a batch component, that calls an external service, that scans public records for additional driver data that is then stored in a local database | IT Service | Yes | No | AQS | Yes | No | Yes | 5479 HV AQS | HV-UWWB; webMethods; HV-AQS, Stat | SQL2019, Win2019 | HV
7956 | HV-Core Logic Svc | 12/31/26 | Services that handle Hazard data for Property policies. Used by NB and Renewal processes | IT Service | No | No | N/A | Yes | No | No | 5479 HV AQS | AQS | SQL2019, Win2019 | HV
7957 | HV-Billing Svc | 12/31/26 | Services that support Billing | IT Service | No | N/A | N/A | Yes | yes | No | 5479 HV AQS | HV-Core Integration Svcs, HV-IADB, CL Legacy Service, Agent Portal | SQL2019, Win2019 | HV
7959 | HV-Update AQS Stat Feed | 04/01/27 | nightly batch job (EDR0090 | Component | No | No | N/A | Yes | No | Yes | 5479 HV AQS | Proxix service, webMethods | SQL2019, Win2019 | HV
8039 | HV-CLManuscripts | 12/31/26 | HV-CLManuscripts CL Manuscripts (or CL Corporate Form) templates publish from CL Forms Sharepoint library to AgentPortal, UWWB, and AQS.Agent Portal –Supplemental applications and Questionaires, versions, and link to retrieve those forms once selected UWWB – Manuscript Templates – Forms/endorsements, versions, and a link to retrieve forms (same forms used for AQS) AQS – Manuscript endorsement titles and wording is used for AQS forms | IT Service | No | No | N/A | Yes | No | No | 5479 HV AQS | same as HV-AQS | SQL2019, Win2019 | HV
8319 | CIS BATCH Apps | 9/30/25 | CIS Batch Apps (CA RCE, Farm Credit, and IRPM Worksheets) | Application | Yes | Yes | TBD | TBD | TBD | TBD | TBD | TBD | TBD | PCIO
9999 | Commercial Auto | 12/31/26 | All policy and quote data in BA, this is a supporting app with rates. | Application | Yes | Yes | TBD | Yes | Yes | Yes | 912 Mainframe Package Control | Mainframe Business Auto | DB2, VSAM, COBOL | PCIO
0000 | Policy Management System (PMS) CalFarm | 03/31/26 | Old CalFarm company acquired. | Application | Yes | Yes | TBD | No | No | No | 912 Mainframe Package Control | Claims | DB2 | PCIO

## Reference - to hide (hidden)
Category | Current Status | App type |  | Age of application | Scale | Application life | Application Being Decommissioned | Active Users | Level of Documentation | Level of Knowledge | FTEs Spent from SME's | FTEs Spent from Contractor | Application Type | No of Servers | Duration | Scale | Data treatment options | Database backup frequency |  | Data treatment | Age | Scale | Size
Custom developed | Run-Off Mode | Front end | Yes | 0 -5 years | 1 | < 3 Months | Drop Off Business Functionality | 1 - 10 Users | No Documentation | Has only basic information | < 5 SMEs | < 10 SMEs | Custom Developed | 1 | 1-12 Months | 1 | Archive | Daily | Yes | Active | 0 to 5 Years | Very High | less than 10GB
3rd party/COTs | Inquiry Mode | Back end | No | 5 -10 years | 2 | 3-6 Months | Modernization | 10 - 15 Users | Minimal Documentation | Has only operational knowledge | 5 - 10 SMEs | 10 - 20 SMEs | Acquired | 2 | 13-24 Months | 2 | Purge | Weekly | No | Purge | 5 to 10 Years | High | 10-30GB
| Not - in - Use | Both | Not Known | 10 - 15 years | 3 | 6-12 Months | Other | 15 - 20 Users | Outdated Documentation | Has only business knowledge | 10 - 15 SMEs | 20 - 30 SMEs | 3rd Party | 3 | 25-36 Months | 3 | Retain | Monthly | Others | Retain | 10-15 Years | Medium | 30-70GB
| Post Run off Mode |  |  | 15 - 20 years | 4 | 12-18 Months |  | 20 - 30 Users | Well Documented | Has operational & business knowledge | 15 - 20 SMEs | 30 - 40 SMEs | Not known | 4 | 37-60 Months | 4 |  | Fortnightly |  |  | 15-20 years | Low | 70-100GB
| Not Known |  |  | >20 years | 5 | > 18 Months |  | > 30 Users |  |  | > 20 SMEs | > 40 SMEs |  | >4 | > 60 Months | 5 |  |  |  |  | >20 Years | Very Low | more than 100GB

## Sheet 1
Row Labels | Count of Application Name
In progress | 74
(blank)
Grand Total | 74